## 20% IRA 1st qtr 2018
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2018
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks | completion
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Different variety of plants for Clean and Green |  | Asingan | 6720 | 2018-02-28 |  | 2018-02-28 | 100% | 6720
ECONOMIC DEVELOPMENT
no transaction
ENVIRONMENTAL MANAGEMENT
no transaction
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [7 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [7 empty] | Acting Municipal Mayor