## 20% IRA 1st qtr 2020
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Tarpaulin to be used by the republic act no 9003 or the ecological solid waste management act 2001 |  | Asingan, Pangasinan | 780 | 2020-01-13 |  | 2020-01-14 | 100% | 780
Tarpaulin wghich are distributed to different Barangay and posted at different Area in the Municipality of Asingan |  | Asingan, Pangasinan | 12700 | 2020-02-07 |  | 2020-02-13 | 100% | 12700
Construction of MRF fence at Toboy Asingan Pangasinan |  | Toboy, Asingan, Pangasinan | 49953.5 | 2020-02-06 |  | 2020-02-12 | 100% | 49953.5
Installation of CCTV at Brgy. Coldit Asingan Pangasinan |  | Coldit, Asingan, Pangasinan | 149780 | 2020-02-05 |  | 2020-02-12 | 100% | 149780
Construction/Rehabilitation of CR at Gym/Evacuation Center, Asingan Pangasinan |  | Poblacion East, Asingan, Pangasinan | 1199323.05 | 2020-02-03 |  | 2020-05-02 | 50% | 179898.45
Construction of Multi-purpose Hall at Ariston West Asingan Pangasinan |  | Ariston East, Asingan, Pangasinan | 2499170.96 | 2020-02-03 |  | 2020-06-11 | 15% | 374875.64
Construction of Lined Canal at P. Ramos St. Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 999558.82 | 2020-02-03 |  | 2020-04-02 | 100% | 149933.82
Rehabilitation of Line Canal at Municipal Plaza Brgy. Poblacion East & Poblacion West, Asingan, Pangasinan |  | Poblacion East/West, Asingan, Pangasinan | 198888.08 | 2020-02-24 |  | 2020-03-05 | 100% | 198888.08
Purchase/Installation of CCTV at Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 199750 | 2020-02-25 |  | 2020-03-06 | 100% | 199750
Repair and Maintenance of Municipal Building in this Municipality of Asingan |  | Asingan, Pangasinan | 59831 | 2020-03-11 |  | 2020-03-13 | 100% | 59831
0
0
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Date Started = [Target Completion Date]-10