## 20% IRA 1st qtr 2020 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
3 units submersible pump & other material use to replace submersible pump for the fountain beside of the Municipal Building |  | Asingan, Pangasinan | 21518.75 | 2021-01-29 | 14 | 2021-02-12 | 100% | 21518.75
1 unit water pump 3x3, 1 unit portable welding machine inverter, 8 ft flexible hose 3", 4 pcs brush cutter blade, 2 rolls trimmer line and 20 pcs Battery Clamp |  | Asingan, Pangasinan | 23900 | 2021-02-23 | 14 | 2021-03-09 | 100% | 23900
Side Carrier to be used for the Solid Waste at Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 27850 | 2021-03-11 |  | 2021-04-20 | 100% | 27850
1 unit of side carrier to be used for Solid Waste at Brgy. Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 27850 | 2021-03-11 |  | 2021-04-20 | 100% | 27850
Siphoning of Septic Tank of PNP Building in this Municipality of Asingan |  | Asingan, Pangasinan | 30000 | 2021-02-11 |  | 2021-02-16 | 100% | 30000
Siphoning of Septic Tank of Municipality Hall Building in this Municipality of Asingan |  | Asingan, Pangasinan | 30000 | 2021-02-11 |  | 2021-02-16 | 100% | 30000
Continuation of concreting of feeder road at Sitio Hacienda Brgy. Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 49950 | 2021-03-09 |  | 2021-03-17 | 100% | 49950
Continuation of concreting of feeder road at Sitio Centro Brgy. Toboy, Asingan, Pangasinan- |  | Toboy, Asingan, Pangasinan | 49950 | 2021-03-09 |  | 2021-03-17 | 100% | 49950
Installation of Playground for the Child Development Center at Brgy. Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 49964 | 3/09/2021 |  | 2021-03-16 | 100% | 49964
1 unit motorcycle to be used for waste collection of Brgy. Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 51400 | 2021-03-16 |  | 2021-03-24 | 100% | 51400
Replacement of PVC Drain pipes for the wet market and concrete cover at Asingan Public Market |  | Asingan, Pangasinan | 66431.24 | 2021-01-16 |  | 2/16/2021 | 100% | 66431.24
Installation of Solar Powered Lights of Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 99500 | 03/09/2021 |  | 2021-03-23 | 100% | 99500
Construction of road-thresher situated at Macalong-Domanpot Farm to Market Road at Brgy. Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 99726.64 | 2021-02-23 |  | 2021-03-03 | 100% | 99726.64
Continuation concreting of feeder road going to Material Recovery Facility (MRF) Sitio Centro , Brgy. Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 99947 | 2021-03-09 |  | 2021-03-15 | 100% | 99947
Rip-rapping of Caocan Local Access Road at Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 99979 | 2021-03-09 |  | 2021-03-18 | 100% | 99979
Construction of Perimeter Fence al Multi-Purpose Hall of Brgy. Palaris, Asingan Pangasinan |  | Palaris, Asingan, Pangasinan | 299513.17 | 2/24/2021 |  | 2021-03-24 | 100% | 299513.17
Construction of Barangay Health Center Extension at Brgy. San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 299545.85 | 2021-02-24 |  | 2021-03-19 | 100% | 299545.85
Continuation of the Construction of Multi-purpose Hall at Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 299716.74 | 2021-02-26 |  | 2021-03-19 | 100% | 299716.74
Construction of Picnic Sheds, Handwash Facility, Pagoda Hanging Bridge at Farmer's Village, Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 499558.61 | 2/26/2021 |  | 2021-05-02 | 50% | 74933.79
Construction of Multi-Purpose Hall at Brgy. Macalong,Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 999427.87 | 2021-02-24 | 53 | 2021-04-18 | 70% | 700060.38
Construction of Barangay Health Center at Brgy. San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan, Pangasinan | 999429.08 | 2021-02-24 | 76 | 2021-05-11 | 30% | 303926.38
Construction of Covered Court at Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 1199482.68 | 2021-02-24 | 70 | 2021-05-05 | 55% | 179922.4
Construction of Covered Court at Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 1199482.68 | 2021-02-24 | 70 | 2021-05-05 | 55% | 479913.02
Purchase of Mini Dump Truck for use at Solid Waste Program |  | San Vicente East, Asingan, Pangasinan | 1995000 | 2021-03-09 | 14 | 2021-03-23 | 100% | 1995000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor