## 20% IRA 1st qtr 2022 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 1ST QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Widening of Bobonan Zone 7 Farm to Market Road at Bobonan, Asingan |  | Barangay Bobonan, Asingan Pangasinan | 999682.58 | 2022-01-31 | 45 | 2022-03-17 | 85% | 149952.39
Continuation of the Construction of Palaris Irrigation Road at Zone 4, Palaris, Asingan, Pang (RID: 0113050160008) |  | Barangay Palaris, Asingan Pangasinan | 499723.32 | 2022-01-31 |  | 2022-02-18 | 100% | 499723.32
Contract for the Construction of Local Access Road at Calepaan Zone 2, Asingan Pangasinan (RID: 0113050090018) |  | Barangay Calepaan, Asingan Pangasinan | 499745.19 | 2022-01-31 |  | 2022-02-23 | 100% | 499745.19
Contract for the Continuation of the Construction of Coldit-San Vicente West Local Access Road at Coldit, Asingan (RID: 0113050120004) |  | Barangay Coldit, Asingan Pangasinan | 2999649.44 | 2022-01-31 | 35 | 2022-03-07 | 85% | 2258684.5
Construction of Ciriaco Altura Farm to Market Road at Domanpot, Asingan, Pangasinan |  | Barangay Domanpot, Asingan Pangasinan | 1999646.58 | 2022-01-31 | 25 | 2022-02-25 | 100% | 1799681.67
Continuation of Construction of Don Luis Butao Farm to Market Rd at Domanpot, Asingan |  | Barangay Domanpot, Asingan Pangasinan | 999573.55 | 2022-01-31 | 25 | 2022-02-25 | 100% | 899829.75
Construction of Feeder Road at Zone 7, Macalong, Asingan, Pangasinan - Road ID: 0113050150004 |  | Barangay Macalong, Asingan Pangasinan | 997409.27 | 2022-01-31 |  | 2022-02-18 | 100% | 997409.27
Backfilling of Carabao Ranch at Samahang Nayon MPC, Bantog, Asingan, Pangasinan |  | Bantog, Asingan, Pangasinan | 99790 | 2022-02-08 |  | 2022-02-14 | 100% | 99790
Continuation of the Construction of Solar Dryer at Sitio Hacienda 2, Toboy, Asingan, Pangasinan |  | Barangay Toboy, Asingan Pangasinan | 199868 | 2022-02-18 |  | 2022-02-27 | 100% | 199868
Installation of Solar Power Streetlights at Zone I Barangay Palaris, Asingan Pangasinan |  | Barangay Palaris, Asingan Pangasinan | 149885 | 2022-02-15 |  | 2022-03-01 | 100% | 149885
Installation of Solar Streetlights at Brgy. Carosucan Norte, Asingan, Pangasinan |  | Barangay Carosucan Norte, Asingan Pangasinan | 99835 | 2022-03-08 |  | 2022-03-16 | 100% | 99835
Installation of Solar Streetlights at Calepaan, Asingan Pangasinan |  | Barangay Calepaan, Asingan Pangasinan | 999753.68 | 2022-01-31 | 45 | 2022-03-17 | 100% | 899778.31
Continuation for the construction of Farmer's Village Facilities(CR,Bridge,Pergola,etc) Macalong, Asingan |  | Engineering's Office | 999734.79 | 2022-01-31 | 35 | 2022-03-07 | 90% | 701452.45
Payment of Materials used for Municipal Building Maintenance in this Municipality of Asingan, Pangasinan |  | Engineering's Office | 51299.13 | 2022-01-19 |  | 2022-02-03 | 100% | 51299.13
Payment for the materials and repair of CR Fixtures at Municipal Hall Building in this Municipality of Asingan, Pangasinan |  | Engineering's Office | 18690 | 2022-01-27 |  | 2022-02-04 | 100% | 18690
Rehabilitation of Drainage Canal and Concreting Beside PNP Building at Poblacion West, Asingan, Pangasinan, |  | Engineering's Office | 69930 | 2022-03-01 |  | 2022-03-09 | 100% | 69930
Construction of Multi-Purpose Hall at Poblacion West, Asingan, Pangasinan - |  | Barangay Poblacion West, Asingan Pangasinan | 2499677.86 | 2022-01-31 | 120 | 2022-05-31 | 65% | 1593662.35
Construction of Multi-Purpose Hall at Poblacion East, Asingan, Pangasinan |  | Barangay Poblacion East, Asingan Pangasinan | 2499573.42 | 2022-01-31 | 120 | 2022-05-31 | 65% | 374936.01
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor