## 20% IRA 2nd qtr 2018
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2ND QUARTER, CY 2018
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks | completion
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Construction of CHB Lined Canal at BRGY. Domanpot, Asingan, Pangasinan |  | Domanpot, Asingan, Pangasinan | 139405 | 2018-04-12 |  | 2018-04-19 | 100% | 139405
Concreting of road shoulder at soloria street, poblacion east |  | Poblacion East, Asingan, Pangasinan | 199560 | 2018-04-17 |  | 2018-04-24 | 100% | 199560
Construction of CHB Lined Canal at Cabalitian,Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 199551.5 | 2018-04-25 |  | 2018-05-02 | 100% | 199551.5
Construction of Irrigated Line Canal Brgy. Ariston West, Asingan, Pangasinan |  | Ariston East, Asingan | 99513 | 2018-05-30 |  | 2018-06-06 | 100% | 99513
Concreting of Road Shoulder Ariston West, Asingan, Pangasinan |  | Ariston West, Asingan, Pangasinan | 199496.5 | 2018-05-02 |  | 2018-05-09 | 100% | 199496.5
Concreting column for Covered Court at BRGY. Bobonan, Asingan, Pangasinan |  | Bobonan, Asingan, Pangasinan | 199487 | 2018-05-16 |  | 2018-05-23 | 100% | 199487
Concreting of road shoulder at Brgy. Calepaan Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 199416 | 2018-05-11 |  | 2018-05-18 | 100% | 199416
Construction of Covered Court infront of Multi-Purpose Hall at brgy. Carosucan norte |  | Carosucan Norte, Asingan, Pangasinan | 199410.92 | 2018-05-15 |  | 2018-05-22 | 100% | 199410.92
Covered Court, Brgy. Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 198516 | 2018-05-11 |  | 2018-05-18 | 100% | 198516
Concreting of Road Shoulder at Zone 1, Brgy. Dupac, Asingan, Pangasinan |  | Dupac, Asingan, Pangasinan | 198789 | 2018-05-11 |  | 2018-05-18 | 100% | 198789
Continuation of the Concreting of Road shoulder at Brgy. Macalong Asingan Pangasinan |  | Macalong, Asingan | 140080.5 | 2018-05-07 |  | 2018-05-14 | 100% | 140080.5
Replacement of Roofing at Segregain Area MRF, asingan, Pangasinan |  | MRF, Asingan | 119690.5 | 2018-05-04 |  | 2018-05-11 | 100% | 119690.5
Concreting of Road Shoulder at Brgy. Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 99714 | 2018-06-01 |  | 2018-06-08 | 100% | 99714
Construction of Stone Masonry of Local Access Road at Sitio Caniogan, Ariston West, Asingan, Pangasinan |  | Sitio Caniogan, Ariston West, Asingan, Pangasinan | 99819.4 | 2018-06-04 |  | 2018-06-11 | 100% | 99819.4
Renovation of Multi Purpose Hall at Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 199721 | 2018-06-04 |  | 2018-06-11 | 100% | 199721
Continuation of irrigated line canal at Brgy. Ariston West, Asingan Pangasinan |  | Ariston West, Asingan Pangasinan | 49851.5 | 2018-06-08 |  | 2018-06-15 | 100% | 49851.5
Construction of Local Access Road at Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 199809 | 2018-06-08 |  | 2018-06-15 | 100% | 199809
Concreting of Local Access Road at Zone 3, Brgy. Coldit, Asingan, pangasinan |  | Coldit, Asingan, Pangasinan | 199684 | 2018-06-08 |  | 2018-06-15 | 100% | 199684
Concreting of road shoulder @ Rizal Ave., Brgy. Bantog, Asingan, Pangasinan |  | Bantog, Asingan, Pangasinan | 199536 | 2018-06-18 |  | 2018-06-25 | 100% | 199536
Construction of perimeter fence (Phase II) at Teofilo Gante Elementary School, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 101762 | 2018-06-21 |  | 2018-06-28 | 100% | 101762
Structural Floor Slab of Brgy. Hall Brgy. San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan | 199622 | 2018-06-06 |  | 2018-06-13 | 100% | 199622
Concreting of local access road at Brgy. San Vicente east, asingan, Pangasinan |  | San Vicente east, Asingan | 197285 | 2018-06-08 |  | 2018-06-15 | 100% | 197285
Concreting of pavement and road shoulder besides Sport Center, Soloria Street, Poblacion East, Asingan, Pangasinan |  | Soloria Street, Poblacion East, Asingan, | 199477 | 2018-06-08 |  | 2018-06-15 | 100% | 199477
Concreting of road shoulder at brgy. Palaris, Asingan |  | Palaris, Asingan, | 99544 | 2018-06-08 |  | 2018-06-15 | 100% | 99544
Rehabilitation of ceiling of the Brgy. Health Center at Palaris, Asingan, Pangasinan |  | Palaris, Asingan, | 99432 | 2018-06-08 |  | 2018-06-15 | 100% | 99432
Fabrication of steel rack of storage room at Sports Center, Asingan, Pangasinan |  | Asingan | 199665 | 2018-06-21 |  | 2018-06-28 | 100% | 199665
ECONOMIC DEVELOPMENT
ENVIRONMENTAL MANAGEMENT
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [7 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [7 empty] | Acting Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+7