## 20% IRA 2nd qtr 2020
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2nd QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks | completion
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Construction/Rehabilitation of CR at Gym/Evacuation Center, Asingan Pangasinan |  | Poblacion East, Asingan, Pangasinan | 837020.05 | 2020-02-07 |  | 2020-07-11 | 71.68% | 600000.41 |  | on going
Construction of Multi-purpose Hall at Ariston West Asingan Pangasinan |  | Ariston East, Asingan, Pangasinan | 2499170.96 | 2020-02-07 |  | 2020-08-20 | 60% | 374875.64 |  | on going
Construction of Lined Canal at P. Ramos St. Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 999558.82 | 2020-02-03 |  | 2020-06-01 | 100% | 999558.82 |  | completed
To payment for the repair and maintennace of air conditioning units at HON. FRANCISCO A. Sapigao Memorial Sports and Cultural Center in the Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 24600 | 2020-04-17 |  | 2020-04-24 | 100% | 24600 |  | completed | 0
To payment for the Installation of Public Address Paging System at Public Market, Asingan, Pangasinan |  | Asingan, Pangasinan | 199500 | 2020-05-20 |  | 2020-05-27 | 100% | 199500 |  | completed | 0
To payment of Materials used for the Installation of Electrical and Water Supply System of Asingan Tourism and Recreation Center (to be used as Quarantine Facility) at Barangay Macalong |  | Macalong, Asingan, Pangasinan | 46610 | 2020-05-13 |  | 2020-05-20 | 100% | 46610 |  | completed | 0
To payment for the Installation of Additional CCTV Cameras at Public Market, Asingan Pangasinan |  | Asingan, Pangasinan | 197550 | 2020-05-19 |  | 2020-05-26 | 100% | 197550 |  | completed | 0
To payment of one (1) Unit motorcycle for use of waste collection at Brgy. Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 87500 | 2020-05-26 |  | 2020-06-02 | 100% | 87500 |  | completed | 0
To payment of his contract for the construction of BOX Culvert along Mayor's Boulevard, Asingan Pangasinan |  | Asingan, Pangasinan | 348238.8 | 2020-02-07 |  | 2020-06-05 | 100% | 348238.8 |  | completed | 0
To payment of supplies used at MRF |  | Asingan, Pangasinan | 9660 | 2020-06-03 |  | 2020-06-08 | 100% | 9660 |  | completed | 0
To payment for the Purchase/Installation of CCTV Cameras at Zone 4 of Brgy. Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 199700 | 2020-06-04 |  | 2020-06-11 | 100% | 199700 |  | completed | 0
To payment for the Repair of Roofing at Municipal Agriculture Office Storage Building, Asingan, Pangasinan |  | Asingan, Pangasinan | 4760 | 2020-06-12 |  | 2020-06-17 | 100% | 4760 |  | completed | 0
to payment of Meter Socket for the Energization of MDRRMO Building in this Municipality of Asingan Pangasinan |  | Asingan, Pangasinan | 7063.71 | 2020-06-18 |  | 2020-06-23 | 100% | 7063.71 |  | completed | 0
To payment for upgrading of power service entrance and installation of wall partition and 3-units Air Conditioning system of DILG Building |  | Asingan, Pangasinan | 40950 | 2020-06-16 |  | 2020-06-23 | 100% | 40950 |  | completed | 0
To partial payment of his contract for the Construction of Lined Canal at Zone I of Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 499458.37 | 2020-02-07 |  | 06/19/2020 | 100% | 449512.533 |  | completed
To payment of materials used for the Installation of Partition for the Isolation Are of Quarantine Facility at Brgy. Macalong Asingan Pangasinan |  | Macalong, Asingan, Pangasinan | 74773.5 | 2020-04-22 |  | 2020-04-29 | 100% | 74773.5 |  | completed
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [7 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [7 empty] | Municipal Mayor
Formulas:
Date Started = [Target Completion Date]-7
Note on D12: Contract Amount less amount charged to Continuing appropriation - P363,303.00