## 20% IRA 2ND qtr 2021 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2ND QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Construction of Covered Court at Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 1199482.68 | 2021-02-24 | 1900-03-10 | 2021-05-05 | 100% | 1199482.68 | 0
Construction of Evacuation Center/Isolation Facility at Barangay Cabalitian, Asingan, Pangasinan | Barangay Cabalitian | Cabalitian, Asingan, Pangasinan | 999800 | 2021-02-24 |  | 2021-04-28 | 100% | 999800 | 0
Construction of Multi-Purpose Hall at Brgy. Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 999427.87 | 2021-02-24 | 1900-02-21 | 2021-05-12 | 100% | 999427.87 | 0
Construction of Barangay Health Center at Brgy. San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan, Pangasinan | 999429.08 | 2021-02-24 | 1900-03-16 | 2021-05-11 | 75.78% | 757335.96 | 242093.12 | 695502.7
Construction of Covered Court at Multi-purpose hall , Brgy. Sanchez, Asingan, Pangasinan | Barangay Sanchez | Sanchez, Asingan, Pangasinan | 499483.05 | 2021-02-26 |  | 2021-03-25 | 100% | 499483.05 | 0
Materials used for Municipal Building Maintenance in this Municipality Of Asingan, Pangasinan | Engineering Office | Asingan, Pangasinan | 33541.48 | 2021-03-01 |  | 2021-03-01 | 100% | 33541.48 | 0
Installation of Solar Lighting System at Domanpot Community School at Barangay Domanpot, Asingan Pangasinan | Barangay Domanpot | Domanpot, Asingan, Pangasinan | 199745.58 | 2021-03-01 |  | 03/15/2021 | 100% | 199745.58 | 0
Construction of CHB Lined Canal at Zone 2, Brgy. Cabalitian, Asingan, Pangasinan | Barangay Cabalitian | Cabalitian, Asingan, Pangasinan | 99952.5 | 2021-03-09 |  | 2021-03-19 | 100% | 99952.5 | 0
filling materials for the opening/regravelling of new Farm to Market Road at Barangay Zone III, Carosucan Sur, Asingan, Pangasinan | Barangay Carosucan Sur | Carosucan Sur, Asingan, Pangasinan | 9000 | 2021-03-15 |  | 2021-03-17 | 100% | 9000 | 0
Payment for the installation of Solar Lights at Zone III, Zone IV at Barangay Carosucan Sur, Asingan, Pangasinan | Barangay Carosucan Sur | Carosucan Sur, Asingan, Pangasinan | 49880 | 2021-03-17 |  | 2021-03-24 | 100% | 49880 | 0
Installation of Solar Power Street Lights at Brgy. Calepaan Asingan Pangasinan | Barangay Calepaan | Calepaan, Asingan, Pangasinan | 199865.34 | 2021-03-23 |  | 2021-04-07 | 100% | 199865.34 | 0
Installation of Solar Power Street Lights at Brgy. Carosucan Norte Asingan Pangasinan | Barangay Carosucan Norte | Carosucan Norte, Asingan, Pangasinan | 149966.76 | 2021-03-23 |  | 2021-04-05 | 100% | 149966.76 | 0
Installation of Solar Power Street Lights at Zone 3 & 4 of Brgy. Coldit Asingan Pangasinan | Barangay Coldit | Coldit, Asingan, Pangasinan | 99959.99 | 2021-03-23 |  | 2021-03-31 | 100% | 99959.99 | 0
Construction of Local Access Road at Purok Capia, Barangay Domanpot, Asingan, Pangasinan | Barangay Domanpot | Domanpot, Asingan, Pangasinan | 199820 | 2021-03-23 |  | 2021-04-07 | 100% | 199820 | 0
Installation of Solar Power Street Lights at Brgy. Palaris Asingan Pangasinan | Barangay Palaris | Palaris, Asingan, Pangasinan | 175000 | 2021-03-23 |  | 2021-04-07 | 100% | 175000 | 0
Installation of Public Pump Well at Brgy. Poblacion East, Asingan, Pangasinan | Barangay Poblacion East | Poblacion East, Asingan, Pangasinan | 34498.25 | 2021-03-23 |  | 2021-03-29 | 100% | 34498.25 | 0
Regravelling of Don Mariano C. Sapigao Farm to Market Road at Barangay Carosucan Sur, Asingan, Pangasinan | Barangay Carosucan Sur | Carosucan Sur, Asingan, Pangasinan | 30000 | 2021-03-25 |  | 2021-03-29 | 100% | 30000 | 0
Installation of Solar Power Streetlights at Brgy. Ariston East, Asingan, Pangasinan | Barangay Ariston East | Ariston East, Asingan, Pangasinan | 59885 | 2021-03-29 |  | 2021-04-07 | 100% | 59885 | 0
Installation of Solar Streetlights w/o stand at Brgy. Cabalitian | Barangay Cabalitian | Cabalitian, Asingan, Pangasinan | 29978.75 | 2021-03-29 |  | 2021-04-05 | 100% | 29978.75 | 0
Installation of Solar Streetlights w/o stand at Brgy. Bantog, Asingan, Pangasinan | Barangay Bantog | Bantog, Asingan, Pangasinan | 29978.75 | 2021-03-30 |  | 2021-04-07 | 100% | 29978.75 | 0
Filling materials/sand & gravel for the opening/construction of the new farm to market road Zone III, Car.Sur, Asingan, Pangasinan - PO Date:03/30/21 SWA:03/31/21(100%) | Barangay Carosucan Sur | Carosucan Sur, Asingan, Pangasinan | 11850 | 2021-03-30 |  | 2021-03-31 | 100% | 11850 | 0
continuation of backfilling along the Farm-to-Market Road at Barangay Carosucan Norte, Asingan, Pangasinan | Barangay Carosucan Norte | Carosucan Norte, Asingan, Pangasinan | 9687.5 | 2021-03-31 |  | 2021-04-05 | 100% | 9687.5 | 0
Continuation of concrete fence of Material Recovery Facility (MRF) at Zone II Barangay Sachez, Asingan Pangasinan | Barangay Sanchez | Sanchez, Asingan, Pangasinan | 99660 | 2021-03-31 |  | 2021-04-08 | 100% | 99660 | 0
Construction of CHB Lined Drainage Canal at Carosucan Norte, Asingan, Pangasinan | Barangay Carosucan Norte | Carosucan Norte, Asingan, Pangasinan | 999662.83 | 2021-04-13 |  | 65 days | 100% | 999662.83 | 0
Construction of Farm to Market Road at Zone 1 to Zone 4 of Brgy. Palaris, Asingan, Pangasinan | Barangay Palaris | Palaris, Asingan, Pangasinan | 499688.89 | 2021-04-13 |  | 2021-05-03 | 100% | 499688.89 | 0
Construction of Pathways and Rehabilitation of Streetlights at Poblacion West, Asingan, Pangasinan | Barangay Poblacion West | Poblacion West, Asingan, Pangasinan | 999457.2 | 2021-04-13 |  | 53 days | 15% | 149918.58 | 849538.62
Installation of Load Bearing Canal Cover along P. Ramos St., Brgy. Poblacion West, Asingan, Pangasinan | Barangay Poblacion West | Poblacion West, Asingan, Pangasinan | 296503.2 | 2021-04-13 |  | 2021-05-05 | 100% | 296503.2 | 0
Concreting of Farm to Market Road at Brgy. Baro, Asingan, Pangasinan | Barangay Baro | Baro, Asingan, Pangasinan | 299704.82 | 2021-04-14 |  | 2021-04-28 | 100% | 299704.82 | 0
Concreting of Farm to Market Road at Masikiyaw, Carosucan Norte, Asingan, Pangasinan | Barangay Carosucan Norte | Carosucan Norte, Asingan, Pangasinan | 299704.82 | 2021-04-14 |  | 2021-05-03 | 100% | 299704.82 | 0
Concreting of Farm to Market Road(Nambilingan) Sobol, Asingan, Pangasinan | Barangay Sobol | Sobol, Asingan, Pangasinan | 499688.89 | 2021-04-14 |  | 2021-05-03 | 100% | 499688.89 | 0
To payment of his contract for the Concreting of Farm to Market Road at Sitio Sokok, Toboy, Asingan, Pangasinan | Barangay Toboy | Toboy, Asingan, Pangasinan | 299704.82 | 2021-04-14 |  | 2021-05-03 | 100% | 299704.82 | 0
Regravelling at Zone II, Sobol in this Municipality of Asingan, Pangasinan | Barangay Sobol | Sobol, Asingan, Pangasinan | 31700 | 2021-04-16 |  | 2021-04-21 | 100% | 31700 | 0
Rehabilitation of ceiling and roofing and construction of wall partition of Multi-Purpose Hall at Barangay Baro, Asingan, Pangasinan | Barangay Baro | Baro, Asingan, Pangasinan | 100000 | 2021-04-17 |  | 2021-04-21 | 100% | 100000 | 0
Installation of Additional Solar Streetlights at Poblacion West, Asingan, Pangasinan | Barangay Poblacion West | Poblacion West, Asingan, Pangasinan | 49987.43 | 2021-04-19 |  | 2021-04-26 | 100% | 49987.43 | 0
Reinforced concrete pipe at Sobol, Asingan, Pangasinan | Barangay Sobol | Sobol, Asingan, Pangasinan | 44938 | 2021-04-19 |  | 2021-04-28 | 100% | 44938 | 0
Concreting of road shoulder at Zone III & Zone IV Barangay Coldit, Asingan, Pangasinan | Barangay Coldit | Coldit, Asingan, Pangasinan | 119900.84 | 2021-04-21 |  | 2021-04-28 | 100% | 119900.84 | 0
Installation of solar streetlights at Brgy. Carosucan Norte, Asingan, Pangasinan | Barangay Carosucan Norte | Carosucan Norte, Asingan, Pangasinan | 99959.99 | 2021-04-26 |  | 2021-05-05 | 100% | 99959.99 | 0
Installation of One Jet-matic Pump for Mun. Material Recovery Facility at Sitio Cabaruan, Brgy. Bantog, Asingan, Pangasinan - | Material Recovery Facility | Asingan, Pangasinan | 25460 | 2021-04-27 |  | 2021-05-03 | 100% | 25460 | 0
Regravelling at Zone II, Barangay Sobol, Asingan, Pangasinan | Barangay Sobol | Sobol, Asingan, Pangasinan | 9992.5 | 2021-05-05 |  | 2021-05-07 | 100% | 9992.5 | 0
Nylon rope 16MM for use at Parking Lot infront of Asingan Sports Complex | Asingan | Asingan, Pangasinan | 4000 | 2021-05-06 |  | 2021-05-11 | 100% | 4000 | 0
Payment of Materials used for Municipal Building Maintenance in this Municipality of Asingan, Pangasinan | Engineering Office | Asingan, Pangasinan | 16549.9 | 2021-05-07 |  | 2021-06-10 | 100% | 16549.9 | 0
Construction of CHB Lined Canal at Sitio Aragaag, Bantog, Asingan, Pangasinan | Brgy. Bantog | Bantog, Asingan, Pangasinan | 79950 | 2021-05-14 |  | 2021-05-26 | 100% | 79950 | 0
Installation of Solar Streetlights at Brgy. Poblacion East, Asingan, Pangasinan | Barangay Poblacion East | Poblacion East, Asingan, Pangasinan | 24915 | 2021-05-25 |  | 2021-05-31 | 100% | 24915 | 0
Installation of Solar Streetlights at Brgy. Ariston West, Asingan, Pangasinan | Barangay Ariston West | Ariston West, Asingan, Pangasinan | 199850 | 2021-05-31 |  | 2021-06-09 | 100% | 199850 | 0
2 units Robin Gas Engine water pump for use of the Farmers of Sitio Lipit, Bantog, Asingan, Pangasinan |  | Bantog, Asingan, Pangasinan | 22000 | 2021-06-10 |  | 2021-06-18 | 100% | 22000 | 0
To payment of Solar Streets Light w/ post at Barangay Palaris, Asingan, Pangasinan | Barangay Palaris | Palaris, Asingan, Pangasinan | 34947.65 | 2021-06-16 |  | 2021-06-22 | 100% | 34947.65 | 0
Repair of ceiling and sliding window of Child Development Center at Brgy. Palaris Asingan, Pangasinan | Barangay Palaris | Palaris, Asingan, Pangasinan | 84955 | 2132-08-05 |  | 04/05/21 | 100% | 84955 | 0
Renovation of Health Center at Brgy. Coldit, Asingan, Pangasinan) | Barangay Coldit | Coldit, Asingan, Pangasinan | 99964.6 | 02-02-2021 |  | 2021-02-17 | 100% | 99964.6 | 0
Installation of new roofing for the Child Development Center at Barangay Poblacion West, Asingan, Pangasinan | Barangay Poblacion West | Poblacion West, Asingan, Pangasinan | 149790.32 | 03/25/2021 |  | 2021-04-07 | 100% | 149790.32 | 0
Installation of Solar Power Street Lights at Brgy. Pob. West, Asingan, Pangasinan ) | Barangay Poblacion West | Poblacion West, Asingan, Pangasinan | 39970 | 03/30/2021 |  | 2021-04-06 | 100% | 39970 | 0
Installation of Solar Streetlights at Barangay Cabalitian, Asingan, Pangasinan | Barangay Cabalitian | Cabalitian, Asingan, Pangasinan | 99800 | 03/30/2021 |  | 2021-04-08 | 100% | 99800 | 0
Installation of Solar Streetlights at Brgy. Palaris, Asingan, Pangasinan | Barangay Palaris | Palaris, Asingan, Pangasinan | 49810 | 05/31/2021 |  | 2021-06-09 | 100% | 49810 | 0
Construction of Picnic Sheds, Hand wash Facility, Pagoda Hanging Bridge at Farmer's Village, Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 499558.61 | 2/26/2021 |  | 2021-05-02 | 15% | 74933.79 | 424624.82
Installation of Load Bearing Canal Cover at Barangay Bantog, Asingan, Pangasinan | Brgy. Bantog | Bantog, Asingan, Pangasinan | 299930 | 04/14//2021 |  | 2021-05-05 | 100% | 299930 | 0
Concreting of Farm to Market Road at Zone 3, Barangay Dupac, Asingan, Pangasinan | Barangay Dupac | Dupac, Asingan, Pangasinan | 299829 | 04/14//2021 |  | 2021-05-05 | 100% | 299829 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor