## 20% IRA 2nd qtr 2022 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 2ND QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Contract for the Widening of Bobonan Zone 7 Farm to Market Road at Bobonan, Asingan - NTP Date: 01/31/2022 SWA: 03/17/2022 (100%) RD ID: 0113050070005 CP: 999682.58 |  | Bobonan, Asingan Pangasinan | 999682.58 | 2022-01-31 | 45 | 2022-03-17 | 100% | 899714.32 | 99968.26
Contract for Installation of Solar Streetlights at Calepaan, Asingan, Pangasinan - NTP:01/31/2022 SWA: 03/02/2022(100.%) CP: 999753.68 |  | Calepaan, Asingan, Pangasinan | 999753.68 | 2022-01-31 | 45 | 2022-03-02 | 100% | 999753.68 | 0
Contract for Continuation of Construction of Coldit-San Vicente West Local Access Road at Coldit, Asingan NTP: 01/31/2022 SWA:03/07/2022 (100%) RD ID: 0113050120004 CP:2999649.44 |  | Coldit, Asingan Pangasinan | 2999649.44 | 2022-01-31 | 35 | 2022-03-07 | 100% | 2999649.44 | 0
Contract for Continuation of Contruction of Ciriaco Altura Farm to Market Road at Domanpot, Asingan, Pangasinan - NTP:01/31/2022 SWA: 2/24/2022(100.%) CP:1999646.58 |  | Domanpot, Asingan, Pangasinan | 1999646.58 | 2022-01-31 | 25 | 2022-02-24 | 100% | 1999646.58 | 0
Contract for Continuation of Contruction of Don Luis Butao Farm to Market Road at Domanpot, Asingan, Pangasinan - NTP:01/31/2022 SWA: 2/25/2022(100.%) CP: 999573.55 |  | Domanpot, Asingan, Pangasinan | 999573.55 | 2022-01-31 | 25 | 2022-02-25 | 100% | 999573.55 | 0
Continuation for the construction of Farmer's Village Facilities(CR,Bridge,Pergola,etc) Macalong, Asingan |  | Engineering's Office | 999734.79 | 2022-01-31 | 35 | 2022-03-07 | 100% | 701452.45 | 298282.34
Contract for the Contruction of Multi-Purpose Hall at Poblacion East, Asingan, Pangasinan - NTP:1/31/2022 SWA: 6/8/2022(70.36%) CP: 2499573.42 |  | Poblacion East, Asingan, Pangasinan | 2499573.42 | 2022-01-31 | 180 | 2022-06-08 | 70.36% | 1758654.75 | 740918.67
Contract for the Construction of Multi-Purpose Hall at Poblacion West, Asingan, Pangasinan - PO Date: 01/31/2022 SWA: 06/20/2022(85.07%) CP: 2499677.86 |  | Poblacion West, Asingan, Pangasinan | 2499677.86 | 2022-01-31 | 180 | 2022-06-20 | 85.07% | 2126379.28 | 373298.58
Payment for the Construction of Auditorium Backstage Extension in this Municipality of Asingan, Pangasinan- PO Date: 2/3/2022 SWA: 2/17/2022 |  | Asingan, Pangasinan | 199904.4 | 2022-02-03 | 20 | 2022-02-17 | 100% | 199904.4 | 0
To payment for the Continuation of the Concreting of Gym (MFASSCC), Asingan, Pangasinan - PO Date: 02/15/2022 SWA: 03/02/2022(100%) |  | Asingan, Pangasinan | 199930.66 | 2022-02-15 | 20 | 2022-03-02 | 100% | 199930.66 | 0
To payment for the concreting of Farm to Market road at Barangay Baro-Dumaquit, Asingan, Pangasinan - RD ID: 0113050130007 PO Date: 2/15/2022 SWA: 3/1/2022 (100%) |  | Baro - Dumaquit, Asingan, Pangasinan | 199941.36 | 2022-02-15 | 20 | 2022-03-01 | 100% | 199941.36 | 0
To payment for the Concreting of Farm to Market Road at Toboy Bagong Baryo, Asingan, Pangasinan -RD ID: 0113050210002 PO Date:2/15/2022 SWA: 03/01/2022(100%) |  | Toboy, Asingan, Pangasinan | 199941.36 | 2022-02-15 | 20 | 2022-03-01 | 100% | 199941.36 | 0
To reimbursed the payment of solid waste tipping dated 2/25/2022,4/8/2022,4/27/2022,4/29/2022 - PO Date: 2/25/2022 |  | Asingan, Pangasinan | 10183 | 2022-02-25 |  |  | 100% | 10183 | 0
To payment for the Construction of Perimeter Fence at Baragay Sobol, Asingan, Pangasinan - PO Date: 03/01/2022 SWA: 03/16/2022 (100%) |  | Sobol, Asingan, Pangasinan | 149885 | 2022-03-01 | 15 | 2022-03-16 | 100% | 149885 | 0
To payment for the Continuation of the Concreting of Road Shoulder at Zone 4 and Zone 5 of Brgy. Bobonan, Asingan, Pangasinan -RD: 0113050070005 PO: 3/7/2022 SWA: 03/18/2022 (100%) |  | Bobonan, Asingan, Pangasinan | 99934 | 2022-03-07 | 12 | 2022-03-18 | 100% | 99934 | 0
To payment for the Installation of Solar Streetlights at Brgy. Coldit, Asingan, Pangasinan- PO: 03/7/2022 SWA: 3/17/2022 (100%) |  | Coldit, Asingan, Pangasinan | 99835 | 2022-03-07 | 10 | 2022-03-17 | 100% | 99835 | 0
To payment for the Continuation of the Concreting of Feeder Road at Sitio Centro, Brgy. Toboy, Asingan, Pangasinan - PO: 3/7/2022 SWA: 03/16/2022 (100%) RD: 0113-05-02-10010 |  | Toboy, Asingan, Pangasinan | 49890 | 2022-03-07 | 10 | 2022-03-16 | 100% | 49890 | 0
To payment for the Concreting of Feeder Road at Sitio Libtong West, Brgy. Toboy, Asingan, Pangasinan - PO: 3/7/2022 SWA: 03/16/2022 (100%) RD: 0113050210021 |  | Toboy, Asingan, Pangasinan | 49890 | 2022-03-07 | 5 | 2022-03-16 | 100% | 49890 | 0
To payment for the Concreting of Feeder Road at Sitio Hacienda II, Brgy. Toboy, Asingan, Pangasinan - PO: 3/7/2022 SWA: 03/16/2022 (100%) RD: 0113050210005 |  | Toboy, Asingan, Pangasinan | 49890 | 2022-03-07 | 10 | 2022-03-16 | 100% | 49890 | 0
To payment for the Concreting of Feeder Road at Sitio Centro, Brgy. Toboy, Asingan, Pangasinan - PO: 3/7/2022 SWA: 03/16/2022 (100%) RD: 0113050210011 |  | Toboy, Asingan, Pangasinan | 49890 | 2022-03-07 | 10 | 2022-03-16 | 100% | 49890 | 0
To payment for the Installation of Solar Streetlights at Brgy. Dupac, Asingan, Pangasinan- PO: 03/15/2022 SWA: 3/21/2022 (100%) |  | Dupac , Asingan, Pangasinan | 99835 | 2022-03-15 | 10 | 2022-03-21 | 100% | 99835 | 0
To payment for the Construction of Material Recovery Facility (MRF) at San Vicente East, Asingan, Pangasinan - PO: 03/16/2022 SWA: 03/21/2022 |  | San Vicente East, Asingan, Pangasinan | 119922 | 2022-03-16 | 12 | 2022-03-21 | 100% | 119922 | 0
To payment of the concreting of road shoulder along the road of Barangay San Vicente West, Asingan, Pangasinan Road ID:0113050190001 - PO Date: 3/23/22 SWA: 03/30/22 (100%) |  | San Vicente West, Asingan, Pangasinan | 49990 | 2022-03-23 | 8 | 2022-03-30 | 100% | 49990 | 0
To payment of concreting of farm to market road along Zone 1-4 at Barangay Palaris, Asingan, Pangasinan Road ID: 0113050160008 - PO date: 03/24/2022 SWA: 04/04/2022(100%) |  | Palaris, Asingan, Pangasinan | 119922 | 2022-03-24 | 12 | 2022-04-04 | 100% | 119922 | 0
To payment for the Installation for Solar Streetlights at Brgy. Palaris, Asingan, Pangasinan - PO Date: 3/25/2022 SWA:4/1/2022(100%) |  | Palaris, Asingan, Pangasinan | 49875 | 2022-03-25 | 8 | 2022-04-01 | 100% | 49875 | 0
Payment for the rewiring materials for the MATERIAL RECOVERY FACILITY in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 34993 | 2022-04-18 |  | 2022-04-19 | 100% | 34993 | 0
Payment for the Fabrication and Installation of Stainless Handrails for PWD's at MSWD and Women Center Building in this Municipality of Asingan, Pangasinan - PO Date: 4/19/2022 SWA: 4/26/2022 |  | Asingan, Pangasinan | 39052.5 | 2022-04-19 | 9 | 2022-04-26 | 100% | 39052.5 | 0
To payment of 2 units fiber glass extension ladder for use at Office warehouse and maintenance personnel - PO Date: 4/21/2022 |  | Asingan, Pangasinan | 34348.75 | 2022-04-21 |  | 2022-05-24 | 100% | 34348.75 | 0
To reimbursed the payment of solid waste tipping dated 5/6/2022, 5/11/2022 - PO Date:5/6/22 |  | Asingan, Pangasinan | 4794 | 2022-05-06 |  |  | 100% | 4794 | 0
To payment of 6 units cement buggy use for collection waste within the Vicinity of Municipal Plaza |  | Asingan, Pangasinan | 25800 | 2022-05-06 |  | 2022-05-19 | 100% | 25800 | 0
To payment for the Installation of Solar Streetlights at Sitio Pannagidan, Brgy. Baro, Asingan, Pangasinan- PO Date: 5/23/2022 SWA: 06/06/2022(100%) |  | Baro, Asingan, Pangasinan | 149880 | 2022-05-23 | 15 | 2022-06-06 | 100% | 149880 | 0
To payment of tipping fee for this MUNICIPALITY OF ASINGAN - JO Date: 05/27/2022 |  | Asingan, Pangasinan | 7769 | 2022-05-27 |  |  | 100% | 7769 | 0
To payment for the purchase of 6 units of solar streetlights at Barangay Toboy and Barangay Ariston East, Asingan, Pangasinan - PO Date: 06/03/2022 Cert. of Accepatance: 06/03/2022 |  | Ariston East, Asingan, Pangasinan | 44988 | 2022-06-03 |  | 2022-06-03 | 100% | 44988 | 0
To payment for the purchase of 6 units Solar Streetlights at Barangay Ariston West, Barangay Calepaan,and Barangay Carosucan Norte, Asingan, Pangasinan- PO Date: 6/3/22 Cert. of Acceptance: 6/13/22 |  | Calepaan, Asingan, Pangasinan | 44988 | 2022-06-03 |  | 2022-06-13 | 100% | 44988 | 0
To payment for the construction of Canal Lining at Zone 3, Barangay Dupac, Asingan, Pangasinan- PO Date: 06/07/2022 SWA:06/21/2022(100%) |  | Dupac , Asingan, Pangasinan | 99950.84 | 2022-06-07 | 15 | 2022-06-21 | 100% | 99950.84 | 0
To partial payment of his Contract for the Contruction of Bahay Silangan at Asingan, Pangasinan - NTP:6/9/2022 SWA: 6/20/2022(50.13%) CP: 999807.87 |  | Asingan, Pangasinan | 999807.87 | 2022-06-09 | 50 | 2022-06-20 | 50.13% | 501251.78 | 498556.09
To payment for the concreting of road shoulder at Zone 1 Barangay Bobonan, Asingan, Pangasinan - RD ID: 011300070001 PO Date: 6/2/2022 SWA: 6/6/2022 (100%) |  | Bobonan, Asingan, Pangasinan | 34977 | 6/2/2022 | 7 | 2022-06-06 | 100% | 34977 | 0
17317299.64
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor