## 20% IRA 3rd qtr 2020 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3rd QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Construction of Multi-purpose Hall at Ariston West Asingan Pangasinan |  | Ariston East, Asingan, Pangasinan | 2499170.96 | 2020-02-03 | 130 | 2020-06-12 | 100% | 2499170.96
Rehabilitation of Fountain near Sports Complex Asingan, Pangasinan |  | Asingan, Pangasinan | 499501.8 | 2020-05-19 | 60 | 2020-06-26 | 100% | 499501.8
Construction of Box Culvert along Mayor's Boulevard, Asingan, Pangasinan |  | Asingan, Pangasinan | 348049.8 | 2020-05-19 | 45 | 2020-07-03 | 100% | 348049.8
Construction/Rehabilitation of C.R. at Gym Evacuation Center, Asingan Pangasinan |  | Asingan, Pangasinan | 1199323.05 | 2020-05-19 | 90 | 2020-08-17 | 100% | 1199323.05
Construction of Lined Canal at Zone 1 of Brgy. Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 499458.37 | 2020-05-19 | 45 | 2020-07-03 | 100% | 499458.37
To payment of his contract for the Installation of Solar Streetlights at Brgy. Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 499910 | 2020-05-19 | 30 | 2020-06-18 | 100% | 499910
To payment of full his contract for the Concreting of Road Shoulder at Brgy. Dupac, Asingan, Pangasinan |  | Dupac, Asingan, Pangasinan | 249645.69 | 2020-06-23 | 25 | 2020-07-18 | 100% | 249645.69
Concreting of Farm to Market Road at Centro Barangay Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 249645.69 | 2020-06-23 | 25 | 2020-07-18 | 100% | 249645.69
To payment of Additional Gravel Backfilll of People Park at Public Plaza in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 35100 | 2020-06-27 | 10 | 2020-07-07 | 100% | 35100
To payment of 2 Units Brush Cutter,4 Stroke and 1 PC Puller 10",3 ARMS |  | Asingan, Pangasinan | 15700 | 2020-06-27 | 10 | 2020-07-07 | 100% | 15700
To payment of 50 Bags Cement for use of Barangay Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 13250 | 2020-06-27 | 10 | 2020-07-07 | 100% | 13250
To payment of his contract for the Continuation of the Construction of Multi-Purpose Hall at Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 299514.6 | 2020-06-29 | 45 | 2020-08-13 | 100% | 299514.6
To payment for the repair of male cr and installation of additional convinience outlet at DILG Building |  | Poblacion East, Asingan, Pangasinan | 15805 | 2020-07-02 | 10 | 2020-07-12 | 100% | 15805
To payment of continuation of construction of CHB Lined Canal at Zone III, Barangay Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 49955.68 | 2020-07-04 | 10 | 2020-07-14 | 100% | 49955.68
To payment for the Repair of Kitchen Sink at Mayor's Office of Municipal Hall, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 5910 | 2020-07-04 | 10 | 2020-07-14 | 100% | 5910
To payment of side carrier of Motorcycle to be used of waster collection at Barangay Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 27900 | 2020-07-04 | 10 | 2020-07-14 | 100% | 27900
To partial payment of his contract for the Improvement of Municipal Slaughterhouse , Asingan, Pangasinan |  | Asingan, Pangasinan | 649298.47 | 2020-07-08 | 50 | 2020-09-15 | 100% | 649298.47
To payment for the waterproofing of Gymnasium Façade inside firewall |  | Poblacion East, Asingan, Pangasinan | 25320 | 2020-07-09 | 10 | 2020-07-19 | 100% | 25320
To payment for the Installation of Solar Lights Around/ Near the Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 199730 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199730
To payment for the Concreting of FMR along CSNHS Barangay Carosucan Sur, Asingan Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 199987 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199987
To payment for the Construction of MRF at brgy. Carosucan Sur Asingan Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 99792 | 2020-07-10 | 10 | 2020-07-20 | 100% | 99792
To payment for the ocnstruction of FMR at Zone 2 of Brgy. Macalong Asingan Pangasinan |  | Macalong, Asingan, Pangasinan | 199750 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199750
To payment for the concreting of Farm To market Road at Zone 4 of Brgy. Palaris Asingan Pangasinan |  | Palaris, Asingan, Pangasinan | 199750 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199750
To payment for the Construction of Kitchen at Evacuation Center in this Municipality of Asingan |  | Poblacion East, Asingan, Pangasinan | 199651 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199651
To payment for the Concreting of Road Shoulder at Zone 5 of Brgy. Sobol Asingan Pangasinan |  | Sobol, Asingan, Pangasinan | 199750 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199750
To payment for the concreting of Farm to Market Road at Sitio Socok of brgy. Toboy Asingan Pangasinan |  | Toboy, Asingan, Pangasinan | 199750 | 2020-07-10 | 10 | 2020-07-20 | 100% | 199750
To payment for the energization of MDRRMO Building in this Municipality of Asigan Pangasinan |  | Asingan, Pangasinan | 16795.3 | 2020-07-17 | 10 | 07/24/2020 | 100% | 16795.3
To full payment of his contract for the Installation of Solar Streetlights at Barangay Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 299977 | 2020-07-22 | 30 | 2020-08-21 | 100% | 299977
To payment of Materials used for the Fabrication of Steel Grills of the Kitchen at MFASS Memorial Sports Cultural Center, Asingan, Pangasinan |  | Asingan, Pangasinan | 39780 | 2020-07-23 | 10 | 2020-08-02 | 100% | 39780
To 1st partial payment of his contract for the Installation of Solar Streetlights at Barangay Domanpot |  | Domanpot, Asingan, Pangasinan | 999205 | 2020-07-23 | 10 | 2020-08-02 | 100% | 802134
To payment for the installation of RC pipe at Zone 1, Baro Intersection, Asingan . Pangasinan |  | Baro, Asingan, Pangasinan | 99880 | 2020-07-25 | 10 | 2020-08-04 | 100% | 99880
To full payment of his contract for the Concreting of Farm to Market Road at Barangay Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 249645.69 | 2020-07-25 | 10 | 2020-08-04 | 100% | 249645.69
To full payment of his contract for the Construction of Farm to Market Road at Brgy. Domanpot, Asingan, Pangasinan |  | Domanpot, Asingan, Pangasinan | 249645.69 | 2020-07-25 | 10 | 2020-08-04 | 100% | 249645.69
To payment of the continuation of Construction of CHB lined Canal at Zone III Brgy. Cabalitian, Asingan Pangasinan |  | Cabalitian, Asingan, Pangasinan | 49887 | 2020-07-26 | 10 | 2020-08-05 | 100% | 49887
To payment for the Installation of Solar Street Lights at Brgy. Cabalitian Asingan Pangasinan |  | Cabalitian, Asingan, Pangasinan | 99835 | 2020-07-26 | 10 | 2020-08-05 | 100% | 99835
To payment of various Materials for the Municipal Building Maintenance in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 113684 | 2020-07-28 | 10 | 2020-08-28 | 100% | 113684
To partial payment of his contract for the Construction of Lined Canal with Load Bearing Cover at J. Millan and Market, Asingan, Pangasinan |  | Asingan, Pangasinan | 449495.15 | 2020-07-28 | 45 | 2020-09-04 | 100% | 449495.15
To full payment of his contract for the Construction of Solar Drinking Station in various Barangays, Asingan Pangasinan, |  | Asingan, Pangasinan | 499823.1 | 2020-07-28 | 35 | 2020-09-01 | 100% | 499823.1
To payment of his contract for the construction of Farm to Market Road at Zone 2 of Brgy. San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 299558.02 | 2020-07-28 | 25 | 2020-08-22 | 100% | 299558.02
To payment for the installation of Door Enclosure RHU at Ground Floor |  | Poblacion East, Asingan, Pangasinan | 56300 | 2020-07-31 | 10 | 2020-08-10 | 100% | 56300
To payment for the concreting of road at Zone VI at Barangay Ariston West, Asingan, Pangasinan |  | Ariston West, Asingan, Pangasinan | 147358.64 | 2020-08-01 | 10 | 2020-08-11 | 100% | 147358.64
To payment of 1 unit motorcycle to be used of Waste Collection at Brgy. Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 87000 | 2020-08-01 | 10 | 2020-08-11 | 100% | 87000
To payment of 1 Unit Motorcycle to be used of Waste Collection at Brgy. Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 87000 | 2020-08-01 | 10 | 2020-08-11 | 100% | 87000
To payment for the Construction of Solar Dryer at Brgy. Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 199755 | 2020-08-02 | 10 | 2020-08-12 | 100% | 199755
To payment of janitorial supplies use to maintain the cleanliness of Comfort Rooms of Municipal Town Hall |  | Asingan, Pangasinan | 22329.04 | 2020-08-05 | 10 | 2020-08-15 | 100% | 22329.04
To payment for the concreting of Cross Drainage at Brgy. San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 349562.12 | 2020-08-05 | 10 | 2020-08-15 | 100% | 349562.12
To payment for the Installation of Fabricated Solar Lighting at Barangay San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 99970 | 2020-08-05 | 10 | 2020-08-15 | 100% | 99970
To payment for the construction of FMR at Zone 6,Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 199480 | 2020-08-06 | 10 | 2020-08-16 | 100% | 199480
To payment of regravelling of newly open-FMR Zone III Barangay Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 21000 | 2020-08-06 | 10 | 2020-08-16 | 100% | 21000
To payment for the Installation of Fabricated Solar Lighting at Barangay Dupac, Asingan, Pangasinan |  | Dupac, Asingan, Pangasinan | 99970 | 2020-08-06 | 10 | 2020-08-16 | 100% | 99970
To payment for the installation of Fabricated Solar Lighting at Barangay San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan, Pangasinan | 99970 | 2020-08-06 | 10 | 2020-08-16 | 100% | 99970
To payment for the Concreting of Pavement near Cabalitian Multi-Purpose Hall, Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 199500 | 2020-08-07 | 10 | 2020-08-17 | 100% | 199500
To payment of Concreting Feeder Road (Phase II) at Sitio Centro, Barangay Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 99910 | 2020-08-07 | 10 | 2020-08-17 | 100% | 99910
Payment of Solar Power Streetlights at Sitio Sucok, Barangay Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 29987 | 2020-08-07 | 10 | 2020-08-17 | 100% | 29987
To payment for the Concreting of Feeder Road going to Material Recovery Facility (MRF) at Sitio Centro, Barangay Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 99910 | 2020-08-07 | 10 | 2020-08-17 | 100% | 99910
To payment for the installation of Glass Window at Dental Clinic of RHU-I |  | Asingan, Pangasinan | 6156 | 2020-08-15 | 10 | 2020-08-20 | 100% | 6156
To payment for the Construction of Wash Area at Material Recovery Facility (MRF), Asingan, Pangasinan |  | Asingan, Pangasinan | 149850 | 2020-08-16 | 10 | 2020-08-26 | 100% | 149850
To payment for the Renovation of Multi-Purpose Building/Evacuation Center at Brgy. San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan, Pangasinan | 199755 | 2020-08-16 | 10 | 2020-08-26 | 100% | 199755
To payment for the Construction of Kitchen at STAC, Asingan, Pangasinan |  | Asingan, Pangasinan | 34820 | 2020-08-17 | 10 | 2020-08-24 | 100% | 34820
To cash advance the paymentof his contract for the Construction/ Beautification of Public Plaza and Auditorium, Asingan Pangasinan |  | Asingan, Pangasinan | 1199490.48 | 2020-08-18 | 95 | 2020-11-21 | 15% | 179923.57
To payment of his Constract for the Improvement of Pathways along NRRES, L. Millan and P. Ramos St., Poblacion West, Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 249815.66 | 2020-08-18 | 20 | 2020-09-07 | 100% | 249815.66
To payment for the Concreting of Road Shoulder at Zone 1, Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 29993 | 2020-08-26 | 7 | 2020-09-07 | 100% | 29993
To payment for the installation of CCTV at Barangay Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 99960 | 2020-08-26 | 10 | 2020-09-04 | 100% | 99960
To payment of Projector for the Supreme Student Council of Pangasinan State University, Asingan, Pangasinan |  | Asingan, Pangasinan | 29897 | 2020-08-26 | 10 | 2020-09-05 | 100% | 29897
To payment of uniform for the Barangay Councils of Carosucan Norte, Asingan, Pangasinan |  | Carosucan Norte, Asingan, Pangasinan | 4140 | 2020-08-27 | 10 | 2020-09-06 | 100% | 4140
To payment for the Continuation of the Construction of CHB Line Canal at Sitio Capampangan, Ariston West, Asingan, Pangasinan |  | Ariston West, Asingan, Pangasinan | 99970 | 2020-08-29 | 10 | 2020-09-08 | 100% | 99970
To payment for the Construction of FMR at Sitio Kapampangan, Ariston West, Asingan, Pangasinan |  | Ariston West, Asingan, Pangasinan | 199987 | 2020-09-02 | 10 | 2020-09-12 | 100% | 199987
To payment of Backfill for the opening of New FMR Zone III, Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 11880 | 2020-09-02 | 10 | 2020-09-12 | 100% | 11880
To paqyment for the regravelling other parts of Barangay Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 29742.57 | 2020-09-02 | 10 | 2020-09-12 | 100% | 29742.57
To payment for the repair/replacement of piping systems of RHU-I comfort rooms, urinals at Government Center & Municipal Hall Buildings in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 14700 | 2020-09-03 | 10 | 2020-09-09 | 100% | 14700
To payment of materials for the backfilling of New FMR for Aragaag Farmers SWISA, Inc. at Sitio Aragaag, Brgy. Bantog, Asingan, Pangasinan |  | Bantog, Asingan, Pangasinan | 110880 | 2020-09-04 | 10 | 2020-09-14 | 100% | 110880
Payment of Labor and materials for the Construction of Shed for STAC at the Back of Women Center in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 24950 | 2020-09-09 | 10 | 2020-09-19 | 100% | 24950
To payment of Fabrication/Installation of Kitchen Gate at Barangay Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 19955 | 2020-09-09 | 10 | 2020-09-19 | 100% | 19955
To payment of Installation of Solar Streetlights at Barangay Car. Norte Asingan, Pangasinan |  | Carosucan Norte, Asingan, Pangasinan | 129963.38 | 2020-09-09 | 10 | 2020-09-18 | 100% | 129963.38
To payment for the rehabilitation of Multi-purpose hall at Brgy. Coldit Asingan Pangasinan |  | Coldit, Asingan, Pangasinan | 149860 | 2020-09-09 | 10 | 2020-09-19 | 100% | 149860
To payment for the rehabilitation/concreting of barangay road at Zone 4, 5 and 6 of Barangay Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 149795 | 2020-09-10 | 10 | 2020-09-20 | 100% | 149795
To payment of his contract for the Procurement of Vehicle for use at Brgy. Bobonan, Asingan, Pangasinan |  | Bobonan, Asingan, Pangasinan | 300000 | 2020-09-12 | 10 | 2020-09-22 | 100% | 300000
To payment for the replacement Submersible Pumps for Fountains infront, Left and Right Sides of the Municipal Hall Building, Asingan, Pangasinan |  | Asingan, Pangasinan | 16640 | 2020-09-17 | 10 | 2020-09-18 | 100% | 16640
To payment of 10 Rolls trimmer line; 3 pcs trimmer head and 5 units cement buggy (Wheel Barrow) for use at MRF |  | Asingan, Pangasinan | 22450 | 2020-09-18 | 10 | 2020-09-20 | 100% | 22450
17331481.95
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Note: Date started was moved due to the ECQ (COVID-19 pandemic)
Note on D48: Date of project was started only after the Enchance Community Quarrantine - May 19,2020