## 20% IRA 3RD qtr 2021 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3RD QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Construction of Barangay Health Center at Brgy. San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan, Pangasinan | 999429.08 | 2021-02-24 | 1900-03-16 | 2021-05-11 | 100% | 999429.08 | 0 | 453409.58
(2) Pitcher pumps & four (4) G.I. Pipes to be installed at Purok Capia & Inanama at Brgy. Domanpot, Asingan, Pangasinan |  | Domanpot, Asingan, Pangasinan | 14890 | 2021-03-05 |  | 2021-03-08 | 100% | 14890 | 0
Continuation of Concreting of road shoulder at Zone III, Barangay Dupac, Asingan, Pangasinan |  | Dupac, Asingan, Pangasinan | 99946 | 2021-03-23 |  | 2021-03-30 | 100% | 99946 | 0
Concreting of farm to market road at Zone 1 & 2, Brgy. Carosucan Sur, Asingan, Pangasinan (100%) |  | Carosucan Sur, Asingan, Pangasinan | 199820 | 2021-03-24 |  | 2021-04-08 | 100% | 199820 | 0
Contract for the Concreting of Local Access Road at Sitio Departe Ariston West, Asingan Pangasinan |  | Ariston West, Asingan, Pangasinan | 299704.82 | 2021-04-13 |  | 2021-05-05 | 100% | 299704.82 | 0
Contract for the Concreting of Farm to Market Road at Sitio Capampangan Ariston West, Asingan Pangasinan |  | Ariston West, Asingan, Pangasinan | 299704.82 | 2021-04-13 |  | 2021-05-05 | 100% | 299704.82 | 0
Construction of Pathways and Rehabilitation of Streetlights at Poblacion West, Asingan, Pangasinan | Barangay Poblacion West | Poblacion West, Asingan, Pangasinan | 999457.2 | 2021-04-13 |  | 2021-06-05 | 100% | 999457.2 | 0
Regravelling of Farm to Market Road at Tanggal Malong Zone I to Zone IV of Barangay San Vicente West (100%) |  | San Vicente West, Asingan, Pangasinan | 93750 | 2021-04-15 |  | 2021-04-22 | 100% | 93750 | -206023.33
Road Widening at Zone VII, Brgy. Bobonan Asingan Pangasinan |  | Bobonan, Asingan, Pangasinan | 299773.33 | 2021-04-23 |  | 2021-05-10 | 100% | 299773.33 | #REF!
Rehabilitation of Streetlights infront of Asingan North Central School, Barangay Dupac, Asingan, Pangasinan - (100%) |  | Dupac, Asingan, Pangasinan | 9993.24 | 2021-05-06 |  | 2021-05-10 | 100% | 9993.24 | 0
Floor tiling and windows screen for the Child Development Center at Barangay Carosucan Sur, Asingan, Pangasinan - PO Date: 05/21/2021 SWA: 06/02/2021 (100%) |  | Carosucan Sur, Asingan, Pangasinan | 59985 | 2021-05-21 |  | 2021-06-02 | 100% | 59985 | 0
Solar Power Street Lights at Purok Tibker, Brgy. Domanpot, Asingan, Pangasinan - (100%) |  | Domanpot, Asingan, Pangasinan | 149829.81 | 2021-05-28 |  | 06/07/2021 | 100% | 149829.81 | 0
Finishing works of the deep well Installation at Zone 2, Sanchez, Asingan - (100%) |  | Zone 2, Sanchez, Asingan | 14928 | 2021-06-04 |  | 2021-06-11 | 100% | 14928 | 0
Construction of Picnic Sheds, Hand wash Facility, Pagoda Hanging Bridge at Farmer's Village, Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 499558.61 | 2021-06-04 |  | 2021-08-08 | 15% | 74933.79 | 424624.82
Construction of Pathways/ Improvement and Landscaping of the Frontage of Public Plaza, Asingan Pangasinan (SWA 90%) |  | Asingan, Pangasinan | 499818.44 | 2021-06-04 |  | 2021-09-02 | 100% | 499818.44 | 0
Repair of gutter and downspout of Municipal Public Market Buildings (100%) |  | Asingan, Pangasinan | 199940 | 2021-06-07 |  | 2021-06-22 | 100% | 199940 | 0
Regravelling of Barangay Road at Purok Isem, Domanpot, Asingan |  | Domanpot, Asingan, Pangasinan | 49700 | 2021-06-08 |  | 2021-06-18 | 100% | 49700 | 0
Repair of PAO Local Access Road of Barangay Ariston East, Asingan, Pangasinan (100%) |  | Ariston East, Asingan, Pangasinan | 99945 | 2021-06-09 |  | 2021-06-21 | 100% | 99945 | 0
1 pc ordinary top converter (tent), 6x10 meters; 1 roll nylon rope 12mm; and 2 packs surf powder 2.2 kg to be used at Material Recovery Facility |  | Asingan, Pangasinan | 2552 | 2021-06-16 |  | 2021-06-16 | 100% | 2552 | 0
Materials used for Municipal Building Maintenance in this Municipality of Asingan, Pangasinan |  | Municipality of Asingan, Pangasinan | 23404.9 | 2021-06-18 |  | 2021-06-21 | 100% | 23404.9 | 0
ten (10) loads of Sand at Zone 2, Brgy. Calepaan, Asingan, Pangasinan-(100%) |  | Calepaan, Asingan, Pangasinan | 19800 | 2021-06-22 |  | 2021-06-25 | 100% | 19800 | 0
Installation of Solar Streetlights at Barangay Bantog, Asingan, Pangasinan- (100%) |  | Bantog, Asingan, Pangasinan | 99910 | 2021-06-23 |  | 2021-07-01 | 100% | 99910 | 0
Construction of Roofing/Trusses of the Multi-Purpose Building/Evacuation Center of Brgy. San Vicente West, Asingan, Pangasinan - (100%) |  | San Vicente West, Asingan, Pangasinan | 99905 | 2021-06-30 |  | 2021-07-12 | 100% | 99905 | 0
Installation of Solar Streetlights w/o stand at Rizal Avenue, Asingan-Tayug Provincial Road, Bantog, Asingan, Pangasinan- (100%) |  | Bantog, Asingan, Pangasinan | 199850 | 2021-07-01 |  | 2021-07-05 | 100% | 199850 | 0
Construction of Concrete Emblem (I LOVE CAR. NORTE) Brgy. Carosucan Norte, Asingan Pangasinan (SWA 100%) |  | Carosucan Norte, Asingan, Pangasinan | 87942 | 2021-07-02 |  | 2021-07-12 | 100% | 87942 | 0
Solar Lamps to be used at Barangay San Vicente West Asingan Pangasinan |  | San Vicente West, Asingan, Pangasinan | 69850 | 2021-07-02 |  | 2021-08-16 | 69.94% | 48850 | 21000
Installation of Solar Streetlights at Barangay Macalong, Asingan, Pangasinan- (100%) |  | Macalong, Asingan, Pangasinan | 199865 | 2021-07-07 |  | 2021-07-13 | 100% | 199865 | 0
payment of waste management at Metro Clark Waste Management Corporation |  | Asingan, Pangasinan | 2142 | 2021-07-08 |  | 2021-07-08 | 100% | 2142 | 0
Procurement of Barangay Patrol Vehicle (Mitsubishi L300 Deluxe ) for use at Brgy. Calepaan, Asingan Pangasinan |  | Calepaan, Asingan, Pangasinan | 480000 | 2021-07-21 |  | 2021-08-17 | 100% | 480000 | 0
3pcs Hard Cap, 3 pcs High Visibility vest, 1 roll nylon 122mm rope 20 meters, Tolda 6 meters x 10 meters for use at Material Recovery Facility (MRF) |  | Asingan, Pangasinan | 11895 | 2021-07-27 |  | 2021-08-17 | 100% | 11895 | 0
Concreting of Farm to Market Road at Zone 3, Carosucan Sur Asingan Pangasinan (SWA 100%) |  | Carosucan Sur, Asingan, Pangasinan | 299777.55 | 2021-07-28 |  | 2021-08-18 | 100% | 299777.55 | 0
Construction of Load Bearing Canal Cover and Pathways at Mayor's Blvd. Asingan Pangasinan |  | Asingan, Pangasinan | 1999583.31 | 2021-07-28 |  | 2021-10-17 | 90% | 1799624.98 | 199958.33
Construction of kitchen sink for Child Development Center of Barangay Ariston West, Asingan, Pangasinan ( SWA 100%) |  | Ariston West, Asingan, Pangasinan | 39954 | 2021-07-30 |  | 2021-08-04 | 100% | 39954 | 0
4 Floor Mounted Carrier Aircon 3 Toner 4 HP Inverter and 1 Unit Ceiling Mounted 3 Toners 4 HP Non- Inverter installed at MFASS Memorial Cultural and Sports Center |  | Asingan, Pangasinan | 799859.09 | 2021-08-05 |  | 2021-08-11 | 100% | 799859.09 | 0
materials used for the Municipal Building Maintenance (plywood, nails, bidet, paint thinner, roller brush and additional materials) in this Municipality of Asingan |  | Asingan, Pangasinan | 42448.06 | 2021-08-09 |  | 2021-08-10 | 100% | 42448.06 | 0
Regravelling of Farm-to-Market Road of Barangay Sobol, Asingan, Pangasinan - (100%) |  | Sobol, Asingan, Pangasinan | 11991.98 | 2021-08-09 |  | 2021-08-11 | 100% | 11991.98 | 0
Regravelling of Barangay Road at Sitio Aragaag, Bantog, Asingan, Pangasinan- PO Date: 08/11/2021 SWA: 08/19/2021 (100%) |  | Bantog, Asingan, Pangasinan | 49700 | 2021-08-11 |  | 2021-08-19 | 100% | 49700 | 0
construction of CHB Line Canal at Brgy. Cabalitian, Zone 5, Asingan, Pangasinan- (100%) |  | Cabalitian, Asingan, Pangasinan | 49966.48 | 2021-08-23 |  | 2021-09-01 | 100% | 49966.48 | 0
Solid Waste Tipping Fee |  | Asingan, Pangasinan | 7395 | 2021-08-31 |  | 2021-08-31 | 100% | 7395 | 0
Installation of Solar Power Streetlights at Brgy. Carosucan Norte, Asingan, Pangasinan - (100%) |  | Carosucan Norte, Asingan, Pangasinan | 99835 | 2021-09-01 |  | 09/07/2021 | 100% | 99835 | 0
Solid Waste Tipping Fee |  | Asingan, Pangasinan | 2278 | 2021-09-10 |  | 2021-09-10 | 100% | 2278 | 0
Solid Waste Tipping Fee |  | Asingan, Pangasinan | 5423 | 2021-09-17 |  | 2021-09-17 | 100% | 5423 | 0
Concreting of pathways going to houses at Zone 7, Brgy. Bobonan, Asingan, Pangasinan- (100%) |  | Bobonan, Asingan, Pangasinan | 199950 | 06/25/202 |  | 2021-07-12 | 100% | 199950 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+76
Target Completion Date = [Date Started]+45+45