## 20% IRA 3rd qtr 2022 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3RD QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Contract for the Widening of Bobonan Zone 7 Farm to Market Road at Bobonan, Asingan - NTP Date: 01/31/2022 SWA: 03/17/2022 (100%) RD ID: 0113050070005 CP: 999682.58 |  | Bobonan, Asingan Pangasinan | 999682.58 | 2022-01-31 | 45 | 2022-03-17 | 100% | 899714.32
Continuation for the construction of Farmer's Village Facilities(CR,Bridge,Pergola,etc) Macalong, Asingan |  | Engineering's Office | 999734.79 | 2022-01-31 | 35 | 2022-03-07 | 100% | 999734.79
Contract for the Construction of Multi-Purpose Hall at Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 2499573.42 | 2022-01-31 | 180 | 2022-06-08 | 100% | 2499573.42
Contract for the Construction of Multi-Purpose Hall at Poblacion West, Asingan, Pangasinan - PO Date: 01/31/2022 SWA: 06/20/2022(85.07%) CP: 2499677.86 |  | Poblacion West, Asingan, Pangasinan | 2499677.86 | 2022-01-31 | 180 | 2022-06-20 | 85.07% | 2499677.86
Construction of Farm to Market Road at Zone 2 Ariston East, Asingan, Pangasinan Road ID 011305003 0005 |  | Ariston East, Asingan, Pangasinan | 498147.3 | 2022-03-09 | 23 | 2022-04-01 | 100% | 498147.3
Continuation of the Construction of Don Mariano Sapigao Farm to Market Road at Carosucan Sur, Asingan -RD ID: 0113050110001 |  | Carosucan Sur, Asingan, Pangasinan | 498928.5 | 2022-03-09 | 16 | 2022-03-25 | 100% | 498928.5
Continuation of Construction of Dusan Farm to Market Road at Dupac, Asingan, Pangasinan Road ID: 0113050140009 |  | Dupac, Asingan, Pangasinan | 799596 | 2022-03-09 | 24 | 2022-04-02 | 100% | 799596
continuation of construction of Nambilingan- Alvarado Road at Sobol, Asingan, Pangasinan Road ID: 0113050200007 |  | Sobol, Asingan, Pangasinan | 499319.1 | 2022-03-09 | 16 | 2022-03-25 | 100% | 499319.1
Repair/replacement of analok door closer(RHU)/Stair Marble Tiles at Municipal Hall, Comfort Room Door &Water Closet Fixture(Women Center) in this Municipality |  | Asingan, Pangasinan | 15200 | 2022-03-14 | 4 | 2022-03-18 | 100% | 15200
To payment of materials used for Municipal Building Maintenance in this Municipality of Asingan |  | Asingan, Pangasinan | 169902.8 | 2022-05-23 | 0 | 2022-05-23 | 100% | 169902.8
Replacement of door at Storage Room at Women Center |  | Asingan, Pangasinan | 29900 | 2022-06-03 | 7 | 2022-06-10 | 100% | 29900
To partial payment of his Contract for the Construction of Bahay Silangan at Asingan, Pangasinan - NTP:6/9/2022 SWA: 6/20/2022(50.13%) CP: 999807.87 |  | Asingan, Pangasinan | 999807.87 | 2022-06-09 | 50 | 2022-06-20 | 85.1% | 999807.87
Payment of solid waste tipping |  | Ariston East, Asingan, Pangasinan | 13515 | 2022-06-10 | 28 | 2022-07-08 | 100% | 13515
Installation of Solar Streetlights at Zone 2 and Zone 7, Brgy. Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 129885 | 2022-06-21 | 8 | 2022-06-29 | 100% | 129885
Payment of Three (3) unit of Solar Streetlights at Barangay Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 22494 | 2022-06-23 | 5 | 2022-06-28 | 100% | 20000
construction of additional canal lining at Zone 7 Brgy. Sobol, Asingan, Pangasinan. |  | Sobol, Asingan, Pangasinan | 39987 | 2022-06-27 | 1 | 06/28/2022 | 100% | 39987
Payment of Ten (10) units of Solar Streetlights at Barangay Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 74980 | 2022-06-28 | 10 | 2022-07-08 | 100% | 74980
Installation of Solar Lights at Zone 1 Barangay Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 49990 | 2022-06-28 | 10 | 2022-07-08 | 100% | 49990
Continuation of construction of Senior Citizens and PWD Office Building at San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 199815 | 2022-07-04 | 18 | 2022-07-22 | 100% | 199815
regravelling of Farm to Market Road at Zone 4,Brgy. Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 99800 | 2022-07-05 | 10 | 7/15/2022 | 100% | 99800
Installation of Solar Lights infront of Municipal Cemetery, Asingan, Pangasinan |  | Asingan, Pangasinan | 199890 | 2022-07-14 | 6 | 2022-07-20 | 100% | 199890
Solar Streetlights at Barangay Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 99900 | 2022-07-14 | 0 | 2022-07-14 | 100% | 99900
Solid waste tipping fee |  | Asingan, Pangasinan | 32929 | 2022-07-15 | 63 | 2022-09-16 | 100% | 32929
Concreting of Farm to Market Road along Zone 1 to Zone IV at Brgy. Palaris, Asingan, Pangasinan. ROAD ID: 0113050070003 |  | Palaris, Asingan, Pangasinan | 59980.82 | 2022-07-19 | 15 | 08/03/222 | 100% | 9980.82
Concreting of Farm to Market Road along Zone 1 to Zone IV at Brgy. Palaris, Asingan, Pangasinan. ROAD ID: 0113050070003 |  | Palaris, Asingan, Pangasinan | 59980.82 | 2022-07-19 | 15 | 08/03/222 | 100% | 50000
Construction of Walls of the Waste Material Storage Room at the Back of Auditorium Stage in the Municipality of Asingan Pangasinan |  | Asingan, Pangasinan | 61402.5 | 2022-07-20 | 12 | 2022-08-01 | 100% | 61402.5
Repair/rehabilitation of gutters and downspouts, installation of canopy and fabrication of steel canal cover at Asingan Public Market, Asingan, Pangasinan |  | Asingan, Pangasinan | 199860 | 2022-07-26 | 8 | 2022-08-03 | 100% | 199860
Concreting of Feeder Road going to Material Recovery facility (MRF) at Sitio Centro Brgy, Toboy, Asingan, Pangasinan ROAD ID NO:0113050210018 |  | Toboy, Asingan, Pangasinan | 99966.62 | 2022-07-29 | 12 | 2022-08-10 | 100% | 99966.62
Construction/Rehabilitation of PWD Building, Asingan, Pangasinan |  | Asingan, Pangasinan | 1999724.86 | 2022-08-03 | 106 | 2022-08-26 | 70.53% | 1410388.24
Construction of NEGO/ Pasalubong Center, Asingan, Pangasinan |  | Asingan, Pangasinan | 599575.9 | 2022-08-03 | 37 | 2022-08-26 | 80.29% | 481406.11
Concreting of Road shoulder at Zone 1, Brgy. Bobonan, Asingan, Pangasinan. ROAD ID: 0113050070001 |  | Bobonan, Asingan Pangasinan | 49974.71 | 2022-08-03 | 7 | 2022-08-10 | 100% | 49974.71
Concreting of Pathway at Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 999738.43 | 2022-08-03 | 30 | 2022-08-26 | 80.69% | 806690.81
Purchase deep well pump (Jetmatic) and pipe for the residents of Sitio Riverside at Barangay Toboy, Asingan,. Pangasinan |  | Toboy, Asingan, Pangasinan | 21611.5 | 2022-08-03 | 1 | 08/04/2022 | 100% | 21611.5
installation of Solar Streetlights at Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 149885 | 2022-08-08 | 3 | 2022-08-11 | 100% | 149885
Concreting of Road Shoulder at Zone 1, Brgy. Bobonan, Asingan, Pangasinan RD ID: 0113050070001 |  | Bobonan, Asingan Pangasinan | 49974.71 | 2022-08-09 | 8 | 2022-08-17 | 100% | 49974.71
Concreting of road shoulder at Zone 7 Barangay Bobonan, Asingan, Pangasinan |  | Bobonan, Asingan Pangasinan | 49941 | 2022-08-09 | 9 | 2022-08-18 | 100% | 49941
repair of Hanging Bridge at Zone 6 Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 99975.64 | 2022-08-09 | 10 | 2022-08-19 | 100% | 99975.64
Construction of Road Shoulder at Zone V Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 99975 | 2022-08-09 | 43 | 2022-09-21 | 100% | 99975
Installation of Solar Streetlights at Barangay Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 49765 | 2022-08-10 | 6 | 2022-08-16 | 100% | 49765
Installation of Solar lights at Brgy. Toboy, Asingan, Pangasinan |  | Toboy, Asingan, Pangasinan | 49945 | 2022-08-16 | 7 | 2022-08-23 | 100% | 49945
Concreting of road shoulder at Zone 1 Barangay Bobonan, Asingan, Pangasinan |  | Bobonan, Asingan Pangasinan | 49970 | 2022-08-17 | 9 | 2022-08-26 | 100% | 49970
construction of canal lining at Zone VII, Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 49966.75 | 2022-08-17 | 9 | 2022-08-26 | 100% | 49966.75
Concreting of Farm to Market Road along Zone I and Zone IV Barangay Palaris Asingan, Pangasinan ROAD ID:0113050070003 |  | Palaris, Asingan, Pangasinan | 119987.94 | 2022-08-22 | 9 | 2022-08-31 | 100% | 119987.94
Ten sets of pumpwell w/ complete accessories to be used of Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 43950 | 2022-08-23 | 31 | 2022-09-23 | 100% | 43950
Payment of materials used for the Municipal Building Maintenance in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 91748.41 | 2022-08-24 | 1 | 2022-08-25 | 100% | 91748.41
Painting of Balay Silangan Repatriation Center in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 54900 | 2022-09-01 | 6 | 2022-09-07 | 100% | 54900
4units of Submersible pump to be used at old fountain near MDRRMO Building, Asingan, Pangasinan |  | Asingan, Pangasinan | 27996 | 2022-09-06 | 21 | 2022-09-27 | 100% | 27996
Installation of Culvert and Concreting of Farm to Market Road (Nayaknak Road) at Zone 7, Calepaan, Asingan, Pangasinan ROAD ID#:0113050090017 |  | Calepaan, Asingan, Pangasinan | 199914 | 2022-09-07 | 8 | 2022-09-15 | 100% | 199914
Installation of 4sets of Solar Streetlights at Sitio MasiCampo Brgy. Dupac, Asingan, Pangasinan |  | Dupac, Asingan | 99974.76 | 2022-09-08 | 6 | 2022-09-14 | 100% | 99974.76
continuation of canal lining at Zone 3, Brgy. Dupac, Asingan, Pangasinan |  | Dupac, Asingan, Pangasinan | 99965.84 | 2022-09-09 | 0 | 2022-09-09 | 100% | 99965.84
Installation of 3 Solar Streetlights at Zone 3,Brgy. Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 124880 | 8/11/2022 | 6 | 2022-08-17 | 100% | 124880
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor