## 20% IRA 4th qtr 2019
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE4TH QUARTER, CY 2019
Pangasinan, Municipality of Asingan
Program or Project | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Concreting of pathway of the hanging bridge at Zone II Barangay Baro Asingan Pangasinan | Baro, Asingan, Pangasinan | 159161 | 2019-09-18 |  | 2019-10-02 | 100% | 159161
Construction/Completion of Materials Recovery Facility for the Sangguniang Brgy. Of Bobonan, Asingan, Pangasinan | Bobonan, Asingan, Pangasinan | 74368 | 2019-09-18 |  | 2019-09-30 | 100% | 74368
Regravelling of Barangay Calepaan, Asingan, Pangasinan | Calepaan, Asingan, Pangasinan | 11500 | 2019-09-19 |  | 2019-09-19 | 100% | 11500
Improvement of Multi-Purpose hall at Brgy. Calepaan Asingan Pangasinan | Calepaan, Asingan, Pangasinan | 99819 | 2019-09-24 |  | 2019-10-04 | 100% | 99819
Concreting of Road Shoulder at Zone 5, Barangay Ariston East, Asingan, Pangasinan | Ariston East, Asingan, Pangasinan | 49913 | 2019-09-25 |  | 2019-09-30 | 100% | 49913
Concreting of road shoulder at Zone 2 of Brgy. Ariston East Asingan Pangasinan | Ariston East, Asingan, Pangasinan | 49836 | 2019-09-25 |  | 2019-10-04 | 100% | 49836
2019 Municipal Tourism Month on September 26-27, 2019 | Asingan | 9600 | 2019-09-25 |  | 2019-09-27 | 100% | 9600
10 sets of trash bin used at Municipality of Asingan | Asingan | 163220 | 2019-09-25 |  | 2019-10-02 | 100% | 163220
Roofing and Tiling of Multi-purpose Hall/ Evacuation Center at Brgy. Coldit, Asingan Pangasinan | Coldit, Asingan, Pangasinan | 199750 | 2019-09-25 |  | 2019-10-14 | 100% | 199750
Enhancement of Two (2) PWD Friendly Comfort Rooms at multi- Purpose Hall of barangay Dupac, Asingan Pangasinan | Dupac, Asingan, Pangasinan | 99842.5 | 2019-09-25 |  | 2019-10-24 | 100% | 99842.5
Construction of CHB Lined Canal at Brgy. Palaris, Asingan Pangasinan | Palaris, Asingan, Pangasinan | 149812.5 | 2019-09-25 |  | 2019-10-11 | 100% | 149812.5
Construction of ceiling of stage of the barangay Social hall of San Vicente East, Asingan, Pangasinan | San Vicente East, Asingan, Pangasinan | 99816 | 2019-09-25 |  | 2019-10-04 | 100% | 99816
Regravelling of Farm to Market Road at Zone 7 of Brgy. Macalong, Asingan, Pangasinan | Macalong, Asingan, Pangasinan | 78660 | 2019-09-28 |  | 2019-09-30 | 100% | 78660
for the repair/ rehabilitation of Multi-purpose hall at Brgy. Coldit,, Asingan Pangasinan | Coldit, Asingan, Pangasinan | 49865.5 | 2019-10-02 |  | 2019-10-10 | 100% | 49865.5
Construction of Multi Purpose Hall @ Brgy. San Vicente East, Asingan, Pangasinan | San Vicente East, Asingan, Pangasinan | 2500000 | 2019-10-07 |  | 2020-02-29 | 100% | 2127439.6
Regravelling of Farm to Market Road at Sitio Mangar-Aroan of Brgy. San Vicente West, Asingan Pangasinan | San Vicente West, Asingan, Pangasinan | 24949.02 | 2019-10-08 |  | 2019-10-11 | 100% | 24949.02
construction of material recovery facility (MRF) at Brgy. Coldit Asingan Pangasinan | Coldit, Asingan, Pangasinan | 74642 | 2019-10-11 |  | 2019-11-08 | 100% | 74642
Concreting of Pathwalk at Zone 7, Brgy. Bobonan Asingan Pangasinan | Bobonan, Asingan, Pangasinan | 99332 | 2019-10-14 |  | 2019-10-25 | 100% | 99332
To payment of continuation of concreting of feeder road at (PHASE II) sitio Riverside Toboy, Asingan Pangasinan | Toboy, Asingan, Pangasinan | 50000 | 2019-10-14 |  | 2019-10-17 | 100% | 50000
To payment of continuation of concreting of feeder road at (PHASE II) sitio Riverside Toboy, Asingan Pangasinan | Toboy, Asingan, Pangasinan | 29977.56 | 2019-10-14 |  | 2019-10-17 | 100% | 29977.56
To payment of enhancement of Vice Mayors Office at Asingan Municipal Hall Asingan Pangasinan | Asingan | 80000 | 2019-10-15 |  | 2019-11-06 | 100% | 80000
Concreting of Road Shoulder along Zone 4 of Brgy. Ariston West, Asingan Pangasinan | Ariston West, Asingan, Pangasinan | 99864 | 2019-10-24 |  | 2019-11-08 | 100% | 99864
To payment of his contract for the Construction of Business One Stop Shop at Asingan Municipal Hall, Asingan Pangasinan | Asingan | 299538.55 | 2019-10-25 |  | 2019-11-14 | 100% | 299538.55
installation of Tiles and Main Door of the Multi-Purpose Hall Extension of Barangay Bobonan, Asingan, Pangasinan | Bobonan, Asingan, Pangasinan | 19982 | 2019-10-25 |  | 2019-10-28 | 100% | 19982
Concreting of Multi Purpose Pavement at Brgy. San Vicente East, Asingan Pangasinan | San Vicente East, Asingan, Pangasinan | 129856.3 | 2019-10-25 |  | 2019-11-08 | 100% | 129856.3
Continuation of the Construction of CHB Lined Canal at Sitio Capampangan Ariston West, Asingan Pangasinan | Ariston West, Asingan, Pangasinan | 59911 | 2019-10-28 |  | 2019-11-04 | 100% | 59911
Continuation of the Construction of CHB Lined Canal at Sitio Capampangan Ariston West, Asingan Pangasinan | Ariston West, Asingan, Pangasinan | 40000 | 2019-10-28 |  | 2019-11-04 | 100% | 40000
sand & gravel for the Regravelling at Brgy. Toboy Asingan Pangasinan | Toboy, Asingan, Pangasinan | 14193.3 | 2019-10-29 |  | 2019-11-05 | 100% | 14193.3
installation of solar powered streetlights at Brgy. Carosucan Sur Asingan Pangasinan | Carosucan Sur, Asingan, Pangasinan | 39910 | 2019-10-30 |  | 2019-11-04 | 100% | 39910
materials and labor for the Assembly of Two (2) Jet-Matic Pump at Zone 1 of Brgy. Dupac, Asingan Pangasinan | Dupac, Asingan, Pangasinan | 15890 | 2019-11-05 |  | 2019-11-06 | 100% | 15890
Continuation of Brgy. Hall Covered Court at Carosucan Norte Asingan Pangasinan | Carosucan Norte, Asingan, Pangasinan | 81920 | 2019-11-06 |  | 2019-11-18 | 100% | 81920
Concreting of road shoulder at Zone II & Zone III Brgy. Dupac Asingan Pangasinan | Dupac, Asingan, Pangasinan | 4388.4 | 2019-11-11 |  | 2019-11-15 | 100% | 4388.4
Assembly of 2nd Floor Terrace Grills of Barangay Multi-purpose Hall Bobonan, Asingan Pangasinan | Bobonan, Asingan, Pangasinan | 19900 | 2019-11-14 |  | 2019-11-22 | 100% | 19900
Ten truck loads of sand and gravel river mixed for the backfilling of farm to market at barangay Carosucan Sur Asingan Pangasinan | Carosucan Sur, Asingan, Pangasinan | 11900 | 2019-11-20 |  | 2019-11-25 | 100% | 11900
Construction of Apartment Type Cemetery Building at Brgy. Macalong Asingan Pangasinan | Macalong, Asingan, Pangasinan | 3998699.22 | 2019-11-20 |  | 2020-04-18 | 65% | 3998699.22
Ambulance to Transport Patients and to be used during Calamity | Asingan | 1500000 | 2019-11-21 |  | 2019-11-25 | 100% | 1500000
Repair and repainting of Two (2) Sign Boards of MRF at Bantog Asingan Pangasinan | Bantog, Asingan, Pangasinan | 4979 | 2019-11-23 |  | 2019-11-28 | 100% | 4979
Backfilling of farm-to-market road at Brgy. Carosucan Sur, Asingan Pangasinan | Carosucan Sur, Asingan, Pangasinan | 23656.65 | 2019-11-26 |  | 2019-11-29 | 100% | 23656.65
Installation of Two (2) jet matic Pump at Municipal Plaza | Asingan | 19250 | 2019-11-28 |  | 2019-12-03 | 100% | 19250
Construction and Repair of Box Culvert along G. Velasco St. Poblacion West, Asingan Pangasinan | Poblacion West, Asingan, Pangasinan | 99966 | 2019-11-28 |  | 2019-12-03 | 100% | 99966
Continuation of concreting of feeder road at Sitio Centro Toboy | Toboy, Asingan, Pangasinan | 49947.54 | 2019-11-28 |  | 2019-12-05 | 100% | 49947.54
Rehabilitation of comfort room beside the multi-purpose and drying pavement at Zone 6, Brgy, Coldit Asingan Pangasinan | Coldit, Asingan, Pangasinan | 77511 | 2019-12-06 |  | 2019-12-13 | 100% | 77511
Installation of CCTV at Public Plaza, Poblacion West Asingan Pangasinan | Poblacion West, Asingan, Pangasinan | 398979 | 2019-12-06 |  | 2019-12-06 | 100% | 398979
Installation of tiles and main door at the extension of Multi-Purpose Hall @ Brgy, Bobonan, Asingan Pangasinan | Bobonan, Asingan, Pangasinan | 19726.68 | 2019-12-09 |  | 2019-12-29 | 100% | 19726.68
Regravelling of farm-to-market at Brgy. Macalong, Asingan, Pang. | Macalong, Asingan, Pangasinan | 62280 | 2019-12-11 |  | 2019-12-13 | 100% | 62280
Installation of Four (4) Sets Spotlights at The Multi- Purpose Hall of Brgy. Bobonan, Asingan, Pangasinan | Bobonan, Asingan, Pangasinan | 33920 | 2019-12-28 |  | 2020-12-28 | 100% | 33920
Rehabilitation of lined canal at Brgy. Bobonan, Asingan, Pangasinan | Bobonan, Asingan, Pangasinan | 49994 | 2019-12-28 |  | 2020-01-11 | 100% | 49994
Regravelling of Barangay road from zone 1 - VI at Brgy. Coldit Asingan Pangasinan | Coldit, Asingan, Pangasinan | 67841 | 2019-12-28 |  | 2020-01-11 | 100% | 67841
Continuation of the Construction of CHB Lined Canal at Brgy. Coldit, Asingan Pangasinan | Coldit, Asingan, Pangasinan | 79849.25 | 2019-12-28 |  | 2020-01-11 | 100% | 79849.25
Expansion of footbridge @ Domanpot Asingan, Pangasinan | Domanpot, Asingan | 129902.6 | 2019-12-28 |  | 2020-01-11 | 100% | 129902.6
Rehabilitation of lined canal at Brgy. Poblacion East, Asingan, Pangasinan | Poblacion East, Asingan, Pangasinan | 99431 | 2019-12-28 |  | 2020-01-11 | 100% | 99431
Electrical Installation of New School Building @ San Vicente West Integrated School Asingan Pangasinan | San Vicente West, Asingan, Pangasinan | 9975.38 | 2019-12-28 |  | 2020-01-11 | 100% | 9975.38
Continuation of the Construction of Perimeter Fence of Child Development Center Sobol Asingan Pangasinan | Sobol, Asingan, Pangasinan | 49961 | 2019-12-28 |  | 2020-01-11 | 100% | 49961
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [5 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [5 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+145
Date Started = [Target Completion Date]-20