## 20% IRA 4th qtr 2020 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks | completion
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
To payment for the repainting of Perimeter Fence along Public Plaza, Asingan, Pangasinan |  | Asingan, Pangasinan | 44230 | 2020-07-20 |  | 2020-07-29 | 100% | 44230
To payment of side carrier of Motorcycle to be used of waste collection at Brgy. Poblacion West, Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 27900 | 2020-08-05 |  | 2020-10-02 | 100% | 27900
To payment of side carrier of motorcycle to be used of waste collection at at Brgy. Cabalitian Asingan Pangasinan |  | Cabalitian, Asingan, Pangasinan | 27900 | 2020-08-05 |  | 2020-10-02 | 100% | 27900
To payment for the construction of MRF at Luciano Millan National High School, Asingan Pangasinan |  | Asingan, Pangasinan | 49965 | 2020-09-10 |  | 2020-09-21 | 100% | 49965
To payment for the Installation & Fabrication of Air Conditioner Bracing at BAC Office Asingan, Pangasinan |  | Asingan, Pangasinan | 4950 | 2020-10-01 |  | 2020-10-05 | 100% | 4950
To payment for the Construction/Widening of Toboy-Coldit Bridge, Asingan, Pangasinan |  | Toboy-Coldit, Asingan, Pangasinan | 99820 | 2020-09-23 |  | 2020-10-02 | 100% | 99820
To payment for the Construction of Lined Canal at P. Ramos St. to Bauzon St., Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 199872.5 | 2020-09-23 |  | 2020-10-06 | 100% | 199872.5
To payment of backfilling of some parts of farm to market road at Barangay Car. Sur, Asingan, Pangasinan |  | Carosucan sur, Asingan, Pangasinan | 11850 | 2020-09-07 |  | 2020-09-10 | 100% | 11850
To payment for the Installation of Solar Power Streetlights at Brgy. Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 99835 | 2020-09-28 |  | 2020-10-07 | 100% | 99835
To payment for the Installation of Solar Street Lights at Brgy. Domanpot, Asingan, Pangasinan |  | Domanpot, Asingan, Pangasinan | 199760 | 2020-09-28 |  | 2020-10-08 | 100% | 199760
To payment for the Installation of Solar Streetlight Lights at Brgy. Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 199760 | 2020-09-25 |  | 2020-10-08 | 100% | 199760
To payment for the Rehabilitation and Concreting of Pavement at Day Care Center at Zone II, Barangay Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 99960 | 2020-09-28 |  | 2020-10-08 | 100% | 99960
To payment of cement for the road shoulder of each barangay in Asingan, Pangasinan |  | Asingan, Pangasinan | 199940 | 2020-08-19 |  | 2020-08-31 | 100% | 199940
To payment for the Construction of Perimeter Fence of the MRF and Solar Drier at Zone II of Brgy. Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 99866 | 2020-10-06 |  | 2020-10-14 | 100% | 99866
To final payment of his contract for the Construction of Multi-Purpose Hall at Brgy. Ariston West, Asingan, Pangasinan |  | Ariston West, Asingan, Pangasinan | 249917.1 | 2020-02-07 |  | 2020-07-20 | 100% | 249917.1
To payment for the laying of reinforced concrete pipe at Zone 7, Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 41527 | 2020-08-17 |  | 2020-08-28 | 100% | 41527
To payment of construction of Gate for the Material Recovery Facility at Zone 3, Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 26937.5 | 2020-09-25 |  | 2020-09-30 | 100% | 26937.5
To payment of Installation of Solar Powered Streetlights at Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 29946.88 | 2020-09-25 |  | 2020-10-01 | 100% | 29946.88
To payment of repainting and repair of hanging bridge at Brgy. Poblacion East, Asingan, Pangasinan |  | Asingan, Pangasinan | 14964.04 | 2020-10-21 |  | 2020-10-23 | 100% | 14964.04
To payment of 20 Units stainless garbage bin with pedal for use at public auditorium and sports complex |  | Asingan, Pangasinan | 19960 | 2020-10-08 |  | 2020-10-05 | 100% | 19960
To payment of 1 unit motorcycle to be used at waste collection at Barangay Baro, Asingan, Pangasinan |  | Baro, Asingan, Pangasinan | 87000 | 2020-11-03 |  | 2020-11-10 | 100% | 87000
To payment for the installation of CCTV Camera for Barangay Bobonan, Asingan, Pangasinan- DPO: 7/28/2020, DC: 8/7/2020 |  | Bobonan, Asingan, Pangasinan | 119914.2 | 2020-07-28 |  | 2020-08-07 | 100% | 119914.2
To payment for the Landscaping of Mayor's Blvd. Center Island, Asingan, Pangasinan- PO Date: 7/7/2020, DC: 07/22/2020 |  | Asingan, Pangasinan | 149775 | 2020-07-07 |  | 2020-07-22 | 100% | 149775
To payment for the Installation of Additional CCTV Cameras (Phase 5) at Brgy. Poblacion West, Asingan, Pangasinan: DPO:10/20/2020, DC: 10/29/2020 |  | Poblacion West, Asingan, Pangasinan | 149900 | 2020-10-20 |  | 2020-10-29 | 100% | 149900
To payment Maintenance Air Conditioning Units at Asingan Municipal Hall |  | Asingan, Pangasinan | 1000 | 2020-10-23 |  | 2020-10-29 | 100% | 1000
To payment of installation of Solar Powered Streetlights at Barangay, Carosucan Norte, Asingan, Pangasinan - DPO:09/01/2020 DC: 09/14/2020 |  | Carosucan Norte, Asingan, Pangasinan | 99909 | 2020-09-01 |  | 2020-09-14 | 100% | 99909
To payment for the 20 truck loads of fillig materials sand & gravel to be used for the opening/construction of the farm-to-market road located at Zone III,Carosucan Sur-DPO:11/5/20 DC:11/10/2020 |  | Carosucan sur, Asingan, Pangasinan | 19734 | 2020-11-05 |  | 2020-11-10 | 100% | 19734
To payment for the Construction of Kitchen at Health Center of Brgy. Carosucan Norte, Asingan, Pangasinan - DPO: 3/17/2020 DC:04/02/2020 |  | Carosucan Norte, Asingan, Pangasinan | 99875 | 2020-03-17 |  | 2020-04-02 | 100% | 99875
To payment for the construction of head quarters of CVO at Carosucan Norte, Asingan, Pangasinan DPO: 05/20/2020 DC:06/03/2020 |  | Carosucan Norte, Asingan, Pangasinan | 99887.5 | 2020-05-20 |  | 2020-06-03 | 100% | 99887.5
To payment for the Construction of Picnic Sheds at Macalong Fishing Ground (SWIP AREA), Asingan, Pangasinan - DPO: 7/7/2020 DC:7/17/2020 |  | Macalong, Asingan, Pangasinan | 166390 | 2020-07-07 |  | 2020-07-17 | 100% | 166390
To payment for the replacement of Glass Windows at LCR & OSCA Office, Asingan, Pangasinan- DPO:11/03/2020 DC: 11/05/2020 |  | Asingan, Pangasinan | 10637 | 2020-11-03 |  | 2020-11-05 | 100% | 10637
To payment of his contract for the Construction of 3-stage water treatment septic tanks at Asingan Public Market - NTP: 09/08/2020, Date SWA:10/16/2020 |  | Asingan, Pangasinan | 499522.49 | 2020-09-08 |  | 2020-10-16 | 100% | 499522.49
To payment of his contract for the Improvement of Public Market, Asingan, Pangasinan- NTP: 09/08/2020 , Date SWA: 10/12/2020 |  | Asingan, Pangasinan | 499562.07 | 2020-09-08 |  | 2020-10-12 | 100% | 499562.07
To payment for the Continuation of the Construction of CHB Lined Canal at Zone 2 Cabalitian Asingan Pangasinan |  | Cabalitian, Asingan, Pangasinan | 99852 | 2020-09-16 |  | 2020-09-28 | 100% | 99852
To payment for the installation of Solar Powered Streetlights at Barangay Coldit, Asingan, Pangasinan- DPO:05/21/2020 DC:06/11/2020 |  | Coldit, Asingan, Pangasinan | 199815 | 2020-05-21 |  | 2020-06-11 | 100% | 199815
To payment of additional installation of Solar Powered Streetlights around Brgy. Poblacion West, Asingan, Pangasinan- DPO: 11/04/2020, DC: 11/16/2020 |  | Poblacion West, Asingan, Pangasinan | 34876.73 | 2020-11-04 |  | 2020-11-16 | 100% | 34876.73
To payment of additional installation of Solar Powered Streetlights around Brgy. Poblacion West, Asingan, Pangasinan- DPO: 11/04/2020, DC: 11/16/2020 |  | Poblacion West, Asingan, Pangasinan | 115000 | 2020-11-04 |  | 2020-11-16 | 100% | 115000
To payment for the Fabrication of Tables at Public Market for Vendors in this Municipality of Asingan- DPO: 7/7/2020 DC: 07/17/2020 |  | Asingan, Pangasinan | 17875 | 2020-07-07 |  | 2020-07-17 | 100% | 17875
To payment of continuation of construction of fence for Child Development Center at Brgy. Sobol, Asingan, Pangasinan- DPO: 11/11/2020, DC:11/17/2020 |  | Sobol, Asingan, Pangasinan | 49950 | 2020-11-11 |  | 2020-11-17 | 100% | 49950
To payment of installation of Solar Powered Streetlights at Barangay Sobol, Asingan, Pangasinan- DPO: 10/28/2020, DC:11/03/2020 |  | Sobol, Asingan, Pangasinan | 49991.43 | 2020-10-28 |  | 2020-11-03 | 100% | 49991.43
To payment of Solar Powered Streetlights at Barangay Sobol, Asingan, Pangasinan- DPO:10/20/2020, DC: 10/29/2020 |  | Sobol, Asingan, Pangasinan | 99915.46 | 2020-10-20 |  | 2020-10-29 | 100% | 99915.46
To payment for the widening of thresher crossing at Macuban, Domanpot, Asingan, Pangasinan- DPO:06/30/2020, DC:07/09/2020 |  | Domanpot, Asingan, Pangasinan | 99804 | 2020-06-30 |  | 2020-07-09 | 100% | 99804
To payment of kuliglig for solid waste collection at Brgy. Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 99500 | 2020-10-16 |  | 2020-10-23 | 100% | 99500
To payment of kuliglig for solid waste collection at Brgy. Carosucan Norte, Asingan, Pangasinan |  | Carosucan Norte, Asingan, Pangasinan | 99500 | 2020-10-16 |  | 2020-10-23 | 100% | 99500
To payment for the Construction of CR at Fish Section of Public Market, Asingan Pangasinan |  | Asingan, Pangasinan | 199718 | 2020-05-20 |  | 2020-06-11 | 100% | 199718
To payment for the construction of concreting of Farm to Market Road at Zone 7 Calepaan, Asingan Pangasinan |  | Calepaan, Asingan, Pangasinan | 69312 | 2020-11-12 |  | 2020-11-16 | 100% | 69312
To payment of 1 unit water pump and 1 ROLL PE TYPE 2" for use ta Public Plaza |  | Asingan, Pangasinan | 8000 | 2020-11-25 |  | 2020-12-01 | 100% | 8000
To Full payment of his contract for the widening and Slope Protection of FMR at Sobol-Calepaan (Nayaknak), Asingan, Pangasinan - NTP: 08/18/2020 , SWA: 11/25/2020 |  | Sobol - Calepaan, Asingan, Pangasinan | 1449729 | 2020-08-18 |  | 2020-11-25 | 100% | 1449729
To payment for the repair of the hanging Bridge at Zone 7 Brgy. Calepaan, Asingan, Pangasinan- PO Date: 11/11/2020 SWA: 12/01/2020 |  | Calepaan, Asingan, Pangasinan | 99171 | 2020-11-11 |  | 2020-12-01 | 100% | 99171
To payment of river mix to be used at Zone 2, Brgy. Coldit, Asingan, Pangasinan - PO Date:11/26/2020 SWA:12/1/2020 |  | Coldit, Asingan, Pangasinan | 7350 | 11/262020 |  | 2020-12-01 | 100% | 7350
To payment for the installation of solar powered streetlights at Brgy. Macalong, Asingan - PO Date:12/01/2020 SWA: 12/11/2020 |  | Macalong, Asingan, Pangasinan | 144826.4 | 2020-12-01 |  | 2020-12-11 | 100% | 144826.4
To payment of Pogpog for solid waster at Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 139900 | 2020-12-03 |  | 2020-12-11 | 100% | 139900
To payment for the installation of solar powered streetlights at Barangay Macalong, Asingan, Pangasinan - PO Date: 10/20/2020 SWA: 10/23/2020 |  | Macalong, Asingan, Pangasinan | 20875 | 2020-10-20 |  | 2020-10-23 | 100% | 20875
To payment for the continuation of Concreting of Road Shoulder at Sitio Nayacnac Zone VII, Brgy. Sobol, Asingan, Pangasinan- PO Date: 12/10/2020 SWA: 12/14/2020 |  | Sobol, Asingan, Pangasinan | 39903.64 | 2020-12-10 |  | 2020-12-14 | 100% | 39903.64
To payment for the Installation of Solar Powered Street Lights at Brgy. Baro, Asingan, Pangasinan - PO Date: 12/2/20 SWA: 12/9/2020 |  | Baro, Asingan, Pangasinan | 49876.43 | 2020-12-02 |  | 2020-12-09 | 100% | 49876.43
To payment for the concreting of Feeder Road at Sitio Libtong East, Barangay Toboy, Asingan, Pangasinan - PO Date: 12/11/2020 SWA: 12/14/2020 |  | Toboy, Asingan, Pangasinan | 20000 | 2020-12-11 |  | 2020-12-14 | 100% | 20000
To payment for the concreting of Feeder Road at Sitio Libtong East, Barangay Toboy, Asingan, Pangasinan - PO Date: 12/11/2020 SWA: 12/14/2020 |  | Toboy, Asingan, Pangasinan | 49950 | 2020-12-11 |  | 2020-12-14 | 100% | 49950
To payment of construction of MRF and Perimeter fence at Brgy Carosucan Sur, Asingan Pangasinan |  | Carosucan sur, Asingan, Pangasinan | 199950 | 2020-12-08 |  | 2020-12-15 | 100% | 199950
To payment for the construction of partition for the police quarters |  | Asingan, Pangasinan | 54780 | 2020-08-10 |  | 2020-08-17 | 100% | 54780
Construction of MRF at Brgy. Bantog, Asingan, Pangasinan |  | Bantog, Asingan, Pangasinan | 199950.1 | 2020-08-25 |  | 2020-09-11 | 100% | 199950.1
Construction of MRF at Brgy. Calepaan |  | Calepaan, Asingan, Pangasinan | 49950 | 2020-05-21 |  | 2020-06-02 | 100% | 49950
Construction of Footbridge at Zone 7, Brgy. Coldit |  | Coldit, Asingan, Pangasinan | 100000 | 2020-12-02 |  | 2020-12-22 | 100% | 100000
Construction of Footbridge at Zone 7, Brgy. Coldit |  | Coldit, Asingan, Pangasinan | 99950 | 2020-12-02 |  | 2020-12-22 | 100% | 99950
Construction of MRF Domanpot |  | Domanpot, Asingan, Pangasinan | 199950 | 2020-08-25 |  | 2020-09-11 | 100% | 199950
Construction of MRF at Pob. East |  | Poblacion East, Asingan, Pangasinan | 199950.1 | 2020-08-25 |  | 2020-09-01 | 100% | 199950.1
1 unit motorcycle used at waste collection at Brgy. Pob. East |  | Poblacion East, Asingan, Pangasinan | 51400 | 2020-12-15 |  | 2020-12-29 | 100% | 51400
Construction of MRF at Brgy. Sanchez |  | Sanchez, Asingan, Pangasinan | 184551.1 | 2020-11-25 |  | 2020-12-14 | 100% | 184551.1
Construction/Beautification of Public Plaza & Auditorium |  | Asingan, Pangasinan | 1199490.48 | 2020-08-18 |  | 2020-12-23 | 100% | 1199490.48
TOTAL |  |  | 9556580.15 |  |  |  |  | 9556580.15
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Note: Construction date was moved due to the ECQ (COVID-19 pandemic)
Formulas:
Target Completion Date = [Date Started]+12
Date Started = [Target Completion Date]-7
Note on D46: Date of project was started only after the Enchance Community Quarrantine - May 19,2020