## 20% IRA 4th qtr 2021 orig
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4TH QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
0
Installation of Solar Power Streetlights at Brgy. Bobonan, Asingan, Pangasinan |  | Bobonan, Asingan, Pangasinan | 199953 | 2021-03-23 |  | 2021-04-08 | 100% | 199953
Construction of concrete slab at San Vicente East ,Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 149790 | 2021-03-23 |  | 2021-03-31 | 100% | 145000
Construction of Farm to Market Road at Carosucan Norte Sitio Dumaquit, Asingan |  | Carosucan Norte - Domanpot, Asingan, Pangasinan | 199917.4 | 2021-03-25 |  | 2021-04-12 | 100% | 199917.4
Construction of Stone Masonry at Brgy. Ariston East, Asingan, Pangasinan- NTP: 04/13/2021 SWA: 05/05/2021 |  | Ariston East, Asingan, Pangasinan | 299879.4 | 2021-04-13 |  | 2021-05-05 | 100% | 299879.4
Installation of Solar Streetlights at Sinapog, Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 299917.8 | 2021-04-14 |  | 05/05/202 | 100% | 299917.8
Concreting of Interior Road at Zone 4, Ignacio St. Brgy Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 149740.16 | 2021-04-26 |  | 2021-05-10 | 100% | 149740.16
cement for the concreting in front the Material Recovery Facility (MRF) at Barangay Carosucan Sur, Asingan Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 9920 | 2021-04-28 |  | 2021-11-24 | 100% | 9920
Construction of Picnic Sheds, Hand wash Facility, Pagoda Hanging Bridge at Farmer's Village, Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 499558.61 | 2021-06-04 |  | 2021-08-08 | 100% | 499558.61
Payment for the filling of sand and gravel for the proposed farm to market road at Sitio Butao, Domanpot in this Municipality of Asingan |  | Domanpot, Asingan, Pangasinan | 49880 | 2021-06-09 |  | 2021-06-16 | 100% | 49880
Concreting of Road Shoulder at Zone 3 to Zone 5 of Brgy. Bobonan, Asingan, Pangasinan- |  | Bobonan, Asingan, Pangasinan | 169878 | 2021-06-16 |  | 2021-06-29 | 100% | 10000
Construction of Local Access road at Purok Tibker-Domanpot |  | Domanpot, Asingan, Pangasinan | 199917.4 | 2021-07-08 |  | 2021-07-27 | 100% | 199917.4
Installation of Solar Powered Potable Water Supply at Sitio Departe, Ariston West/Bantog, Asingan, Pangasinan |  | Ariston West - Bantog , Asingan, Pangasinan | 249958.8 | 2021-07-28 |  | 2021-09-22 | 100% | 249958.8
Construction of Load Bearing Canal Cover and Pathways at Mayor's Blvd. Asingan Pangasinan |  | Asingan, Pangasinan | 1999583.31 | 2021-07-28 |  | 2021-10-05 | 100% | 1999583.31
Installation of Solar Powered Potable Water Supply at Zone 4, Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 249958.8 | 2021-07-28 |  | 2021-09-22 | 100% | 249958.8
Installation of Solar Powered Potable Water System at Sinapog, Brgy. Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 249958.8 | 2021-07-28 |  | 2021-09-22 | 100% | 249958.8
Installation of Solar Powered Potable Water Supply at Zone I, San Vicente West, Asingan, Pangasinan |  | San Vicente West, Asingan, Pangasinan | 249958.8 | 2021-07-28 |  | 2021-09-22 | 100% | 249958.8
Rehabilitation of Monuments (Bonifacio, Del Pilar, etc.) in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 199831 | 2021-08-17 |  | 2021-08-26 | 100% | 199831
Materials( Tanzi,coupling,elbow,pipe,led bulb & others)used for Municipal Building Maintenance in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 56828 | 2021-09-08 |  | 2021-09-10 | 100% | 56828
replacement of analok windows at Municipal Buildings in this Municipality of Asingan, Pangasinan |  | Asingan, Pangasinan | 16593 | 2021-09-28 |  | 2021-10-04 | 100% | 16593
payment for the repair/replacement of water supply, pipes and drainage system and repair of leaking roof at Women Building in this Municipality of Asingan |  | Asingan, Pangasinan | 49342 | 2021-09-28 |  | 2021-11-05 | 100% | 49342
12 sets trash bin 60 liters x 3 w/ steel frame to be used of this Municipality |  | Asingan, Pangasinan | 195864 | 2021-09-29 |  | 2021-10-07 | 100% | 195864
To payment of solid waste tipping fee - PO Date: 10/01/2021 |  | Asingan, Pangasinan | 8653 | 2021-10-01 |  | 2021-10-19 | 100% | 8653
Repair and maintenance of Analok Frame Doors of DILG and Government Center of Asingan, Pangasinan |  | Asingan, Pangasinan | 14826 | 2021-10-05 |  | 2021-10-07 | 100% | 14826
Installation of 100-watts LED streetlights in and around town center streets of Asingan, Pangasinan |  | Asingan, Pangasinan | 199940 | 2021-10-05 |  | 2021-10-22 | 100% | 199940
solid waste tipping fee |  | Asingan, Pangasinan | 6494 | 2021-10-22 |  | 2021-11-08 | 100% | 6494
Payment of materials (door knob, angle valve, 16" flexible hose, good lumber, and other necessary materials) used for the Municipal Building Maintenance Asingan |  | Asingan, Pangasinan | 20344.4 | 2021-10-26 |  | 2021-10-26 | 100% | 20344.4
Installation of CAP Flashing at Women Center and Government Center Buildings in this Municipality of Asingan |  | Asingan, Pangasinan | 55977.44 | 2021-10-26 |  | 11/02/2021 | 100% | 55977.44
Construction of X-Ray Room at RHU I, Asingan, Pangasinan |  | Asingan, Pangasinan | 299772.81 | 2021-10-27 |  | 2021-11-11 | 100% | 299772.81
Repair of Dangay Building (Nagkaisa MPC, Kalipi Display Center, Farmers Conference Center 2nd Floor) |  | Asingan, Pangasinan | 999587.07 | 2021-10-27 |  | 2021-12-01 | 100% | 999587.07
Construction of 2 Check Gates at Brgy. Dupac, Asingan, Pangasinan |  | Dupac, Asingan, Pangasinan | 299652.37 | 2021-10-27 |  | 2021-11-24 | 100% | 299652.37
Construction of Check Gate at Brgy. San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 499477.99 | 2021-10-27 |  | 2021-12-03 | 100% | 499477.99
Replacement of 1 unit panel door & repair of leaking roof at DSWD Building in this Municipality of Asingan, |  | Asingan, Pangasinan | 9480 | 2021-11-02 |  | 2021-11-02 | 100% | 9480
Regravelling of New Opened Road at Barangay Ariston East, Asingan Pangasinan |  | Ariston East, Asingan, Pangasinan | 23750 | 2021-11-04 |  | 2021-11-05 | 100% | 15750
Rehabilitation of kitchen for the Barangay Health Center at Ariston East Asingan Pangasinan (OBR# 006-12-21-101) |  | Ariston East, Asingan, Pangasinan | 24995 | 2021-11-08 |  | 2021-11-12 | 100% | 24995
Contract for the rehabilitation of Material Recovery Facility Building and Portion of MRF Fence at Bantog, Asingan, Pang.- (90%) |  | Bantog, Asingan, Pangasinan | 399817.16 | 2021-11-10 |  | 2021-12-08 | 100% | 59835.44
Installation of Tiles, Kitchen Sink& Painting of Engr. Federico Ganigan, Sr. Child Development Center at Zone 6, Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 49967.57 | 2021-11-10 |  | 2021-11-19 | 100% | 49967.57
Solid waste tipping fee - OR: 11/12/2021 |  | Asingan, Pangasinan | 5236 | 2021-11-12 |  | 2021-11-12 | 100% | 5236
Installation of Floor Tiles and repainting of Multi-Purpose Hall, Barangay Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 99324.3 | 2021-11-17 |  | 11/26/2021 | 100% | 99324.3
Payment of Materials used for Municipal Building Maintenance in this Municipality of Asingan - CoA: 11/23/2021 |  | Asingan, Pangasinan | 40484.5 | 2021-11-23 |  | 2021-11-23 | 100% | 40484.5
Rehabilitation of Concrete Tiles of Pathwalk at Public in this Municipality of Asingan |  | Asingan, Pangasinan | 14940 | 2021-11-24 |  | 2021-11-29 | 100% | 14940
Garden equipment (gasoline sprayer KB Kawasaki 3 RPM 800, 10M Sprayer hose set, IPC Tank 1000Liters) for use at Municipal Plaza -PAR: 12/06/2021 |  | Asingan, Pangasinan | 28700 | 2021-11-24 |  | 2021-12-06 | 100% | 28700
Aggregates Base Coarse Regravelling the Lot at Zone 2, Barangay Sobol, Asingan, Pangasinan |  | Sobol, Asingan, Pangasinan | 23780 | 2021-11-26 |  | 2021-11-29 | 100% | 23780
Payment for the purchase of 4 units replacement LED Floodlights at Public Plaza - CoA: 11/27/2021 |  | Asingan, Pangasinan | 13950 | 2021-11-27 |  | 2021-11-27 | 100% | 13950
Ornamental plants for beautification of Public Plaza Asingan Pangasinan |  | Asingan, Pangasinan | 59951 | 2021-12-01 |  | 2021-12-07 | 100% | 4000
Payment for the replacement of Door Hinges of the MFASS Sport Complex in this Municipality of Asingan -CoA: 12/03/2021 |  | Asingan, Pangasinan | 32560 | 2021-12-02 |  | 2021-12-03 | 100% | 32560
Construction of kitchen beside the Child Development Center Domanpot |  | Domanpot, Asingan, Pangasinan | 39990.58 | 2021-12-21 |  | 2021-12-24 | 100% | 39990.58
Installation of Analok Sliding Window at Carosucan Sur Child Development Center |  | Carosucan Sur, Asingan, Pangasinan | 4985 | 2021-12-22 |  | 2021-12-24 | 100% | 4985
Payment of Construction of Multi-Purpose Hall at Carosucan Norte, Asingan, Pangasinan |  | Carosucan Norte, Asingan, Pangasinan | 199950 | 2021-12-24 |  | 2021-12-31 | 100% | 199950
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+65
Note on I21: 10K was charge to 20%
Note on I44: 15,750 was charged to 20%
Note on I46: 300K - Charged to 20%; 59,835.44 charged to other budget
Note on I55: Only 4K was charge to 20%