## 4th Qtr 20% LDF
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4TH QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date | Remarks
SOCIAL DEVELOPMENT
Contract for the Widening of Bobonan Zone 7 Farm to Market Road at Bobonan, Asingan - NTP Date: 01/31/2022 SWA: 03/17/2022 (100%) RD ID: 0113050070005 CP: 999682.58 |  | Bobonan, Asingan Pangasinan | 999682.58 | 2022-01-31 | 45 | 2022-03-17 | 100% | 999682.58 | 0
To payment of construction of stock room of Barangay Baro, Asingan, Pangasinan | Procurement Office | Baro, Asingan, Pangasinan | 49970 | 2022-07-04 | 9 | 2022-07-13 | 100% | 49970 | 0
Contract for the Landscaping of the Surrounding of Old Fountain, installation of Garden Lights at Pathway going to Auditorium | BARANGAY DUPAC, ASINGAN, PANGASINAN | Asingan, Pangasinan | 999976.5804 | 2022-08-03 | 29 | 2022-09-01 | 55% | 444489.59 | P555,486.22 Obligated
Construction of NEGO/ Pasalubong Center, Asingan, Pangasinan |  | Asingan, Pangasinan | 599575.9 | 2022-08-03 | 37 | 2022-08-26 | 100% | 599575.9 | 0
Construction/Rehabilitation of PWD Building, Asingan, Pangasinan |  | Asingan, Pangasinan | 1999724.86 | 2022-08-03 | 106 | 2022-08-26 | 100% | 1999724.86 | 0
Concreting of Pathway at Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 999738.43 | 2022-08-03 | 30 | 2022-08-26 | 100% | 999738.43 | 0
Installation of Solar Power Street Lights at Barangay Ariston East, Asingan, Pangasinan PO date:8/4/22 SWA Date: 8/12/22 | Barangay Ariston East | Ariston East, Asingan, Pangasinan | 49977.76 | 2022-08-04 | 8 | 2022-08-12 | 100% | 49977.76 | 0
To payment of his contract for the construction of PNP Quarters at Asingan, Pangasinan | BARANGAY DUPAC, ASINGAN, PANGASINAN | Asingan, Pangasinan | 599710.26 | 2022-08-05 | 50 | 2022-09-24 | 100% | 599710.26 | 0
To payment of continuation of concreting of road along Zone 3 Barangay Ariston West, Asingan, Pangasinan - ROAD ID: 0113050040003 | MUNICIPAL ENGINEERING OFFICE | Ariston West, Asingan, Pangasinan | 49970 | 2022-08-17 | 28 | 2022-09-14 | 100% | 49970 | 0
Concreting of Road Shoulder at Zone 1 Barangay Bobonan, Asingan, Pangasinan - ROAD ID: 0113050070001 | Barangay Poblacion East | Bobonan, Asingan Pangasinan | 49985 | 2022-08-22 | 10 | 2022-09-01 | 100% | 49985 | 0
To payment for concreting of Road Shoulder along Zone 3 and Zone 4 Barangay Ariston West, Asingan, Pangasinan ROAD ID:0113050040003 | MUNICIPAL ENGINEERING OFFICE | Ariston West, Asingan, Pangasinan | 74924.66 | 2022-08-26 | 11 | 2022-09-06 | 100% | 74924.66
To payment for the continuation of concreting of road shoulders at Zone 7 Barangay Bobonan, Asingan, Pangasinan ROAD ID: 0113050070004 | MUNICIPAL ENGINEERING OFFICE | Bobonan, Asingan Pangasinan | 49821.5 | 2022-08-26 | 10 | 2022-09-05 | 100% | 49821.5 | 0
Continuation of Construction of Multi-Purpose Hall at Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 149948.7 | 2022-08-27 | 106 | 2022-09-11 | 100% | 149948.7 | 0
To payment for the continuation of construction of Multi-Purpose Hall at Barangay Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan, Pangasinan | 149925 | 2022-09-02 | 37 | 2022-09-14 | 100% | 149925 | 0
Installation of Solar Power Streetlight at Barangay Poblacion East, Asingan., Pangasinan PO: 9/19/22 SWA date: 9/21/22 | Barangay Ariston West | Poblacion East, Asingan, Pangasinan | 24979 | 2022-09-19 | 2 | 2022-09-21 | 100% | 24979 | 0
Solid waste tipping fee for the period of September 21,2022 to November 4,2022(dated: September 21-23,October 7,19,21,26,28,November 4,2022) | MUNICIPAL ENGINEERING OFFICE | Asingan, Pangasinan | 21029 | 2022-09-21 | 44 | 2022-11-04 | 100% | 21029 | 0
To payment for the continuation of road concreting concreting at Sitio Sinapog, Barangay Dupac, Asingan, Pangasinan - ROAD ID # 0113050140005 | Barangay Bobonan | Dupac, Asingan, Pangasinan | 49971.5 | 2022-09-22 | 18 | 2022-10-10 | 100% | 49971.5 | 0
To payment for the Rehabilitation of PWD Ramps Infront of Municipal Hall Building in this Municipality of Asingan, Pangasinan | PNP ASINGAN | Asingan, Pangasinan | 18356.75 | 2022-09-23 | 6 | 2022-09-29 | 100% | 18356.75 | 0
To payment of Materials used for Municipal Building Maintenance in this Municipality of Asingan, Pangasinan | Material Recovery Facility, Bantog, Asingan, Pangasinan | Asingan, Pangasinan | 15350.64 | 2022-09-29 | 0 | 2022-09-29 | 100% | 15350.64 | 0
To payment for the Concreting of Multi-Purpose Pavement at Barangay Baro, Asingan, Pangasinan | MUNICIPAL PUBLIC MARKET | Baro, Asingan, Pangasinan | 49958.46 | 2022-10-03 | 8 | 2022-10-11 | 100% | 49958.46 | 0
To payment for the installation of Solar Streetlights at Barangay Dupac, Asingan, Pangasinan | MUNICIPAL ENGINEERING OFFICE | Dupac, Asingan, Pangasinan | 99988.76 | 2022-10-03 | 9 | 2022-10-12 | 100% | 99988.76 | 0
Construction of road shoulder at Zone 6, Barangay Coldit, Asingan, Pangasinan Road ID: 011305021001 | Barangay Ariston West, Asingan, Pangasinan | Coldit, Asingan, Pangasinan | 97847 | 2022-10-05 | 6 | 2022-10-11 | 100% | 97847 | 0
To payment for the aggregates base course for the regravelling of farm to market road at Barangay Sobol, Asingan, Pangasinan | Barangay Cabalitian | Sobol, Asingan, Pangasinan | 9867 | 2022-10-10 | 2 | 2022-10-12 | 100% | 9867 | 0
To payment for the improvement of Housing for Buffalos at Bantog Samahang Nayon Multi Purpose Cooperative, Bantog, Asingan, Pangasinan | MUNICIPAL ENGINEERING OFFICE | Bantog, Asingan, Pangasinan | 199553 | 2022-10-19 | 8 | 2022-10-27 | 100% | 199553 | 0
To payment of pump well w/ accessories to be used by the residents of Zone 1 Barangay Baro, Asingan, Pangasinan | MUNICIPAL ENGINEERING OFFICE | Baro, Asingan, Pangasinan | 4395 | 2022-10-19 | 16 | 2022-11-04 | 100% | 4395 | 0
To payment of his contract for the repair of MRF Building Roofing Trusses at Material Recovery Facility, Bantog, Asingan, Pangasinan | MUNICIPAL ENGINEERING OFFICE | Bantog, Asingan, Pangasinan | 499744.41 | 2022-10-24 | 15 | 2022-11-08 | 100% | 499744.41 | 0
To payment for the concreting of Mini-Evacuation Center Frontage at Poblacion West Asingan, Pangasinan | Barangay Bobonan | Poblacion West, Asingan, Pangasinan | 199497.72 | 2022-10-25 | 15 | 2022-11-09 | 100% | 199497.72 | 0
To payment for the construction of Multi-Purpose Pavement and Fence of Basketball Court at Sitio Libtong Toboy, Asingan, Pangasinan | Material Recovery Facility, Bantog, Asingan, Pangasinan | Toboy, Asingan, Pangasinan | 169953.65 | 2022-10-25 | 10 | 2022-11-04 | 100% | 169953.65 | 0
To payment of his contract for the Repair and Repaint of Meat and Fish Section at Public Market, Asingan, Pangasinan | Barangay Baro | Asingan, Pangasinan | 299766.6 | 2022-11-08 | 20 | 2022-11-28 | 100% | 299766.6 | 0
To payment of his Contract for the repair of GYM (MFASSCC) Repaint Outside Wall, Replace Broken Windows at MFASSCC, Asingan, Pangasinan |  | Asingan, Pangasinan | 499762.15 | 2022-11-08 | 45 | 2022-11-28 | 100% | 499762.15 | 0
Contract for the construction of Septic Tank and Canal at main Slaughterhouse, Asingan, Pangasinan | Barangay Bobonan | Asingan, Pangasinan | 699660.69 | 2022-11-08 | 23 | 2022-12-01 | 100% | 699660.69 | 0
To payment for the construction of back filling along the farm to market road Primicias Street/Banawang, Zone 7 and 2 Barangay Carosucan Norte, Asingan, Pangasinan | BARANGAY BANTOG, ASINGAN, PANGASINAN | Carosucan Norte, Asingan, Pangasinan | 19848.4 | 2022-11-17 | 5 | 2022-11-22 | 100% | 19848.4 | 0
Regravelling of Road at Zone III Dupac, Asingan, Pangasinan | Bantog Samahang Nayon Multi Purpose Cooperative, Bantog, Asingan, Pangasinan | Dupac, Asingan, Pangasinan | 5450 | 2022-11-17 | 5 | 2022-11-22 | 100% | 5450 | 0
Contract for the Repair and Repainting of the Municipal Hall, Asingan, Pangasinan | Barangay Cabalitian | Asingan, Pangasinan | 599527.88 | 2022-11-22 | 20 | 2022-12-12 | 90% | 150000 | P 180,080.04 non-office + 269447.84 Obligated charge to Non -Office
To payment for the installation of Solar Streetlights at Barangay Bantog Asingan, Pangasinan |  | Bantog, Asingan, Pangasinan | 99960 | 2022-11-23 | 30 | 2022-12-03 | 100% | 99960 | 0
To payment for the purchase of ACSR Drop Wire for Asingan Sheltered Workshop Building (PWD Building) | BARANGAY DUPAC | Asingan, Pangasinan | 5440 | 2022-11-24 | 1 | 2022-11-25 | 100% | 5440 | 0
To payment for the purchase of Two (2) pcs pump well with complete accessories to be used by the residents of Barangay Bobonan, Asingan, Pangasinan | Barangay Baro | Bobonan, Asingan Pangasinan | 11980 | 2022-11-29 | 6 | 2022-12-05 | 100% | 11980 | 0
To payment of additional Christmas decoration for the use at Public Plaza | Barangay Baro | Asingan, Pangasinan | 48900 | 2022-12-02 | 3 | 2022-12-05 | 100% | 48900 | 0
To payment of Electrical Supplies use at Asingan Public Plaza, Asingan, Pangasinan | Barangay Sobol | Asingan, Pangasinan | 12275 | 2022-12-06 | 0 | 2022-12-06 | 100% | 12275 | 0
To payment of materials used for Municipal Building Maintenance | Barangay Carosucan Norte | Asingan, Pangasinan | 95824.44 | 2022-12-08 | 7 | 2022-12-15 | 100% | 95824.44 | 0
To payment for the completion of Construction of the Basketball Court at Barangay Cabalitian, Asingan, Pangasinan | Barangay Toboy, Asingan, Pangasinan | Cabalitian, Asingan, Pangasinan | 49751.52 | 2022-12-09 | 6 | 2022-12-15 | 100% | 49751.52 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Note on I13: Obligated Amount P555,386.22