## 20% IRA 3rd Qtr 2018
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3RD QUARTER, CY 2018
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks | completion
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT | [11 empty] | JEV# | DATE | OBR# | Particulars | Materials | Labor | Total
Repainting of School Bldg. |  | San Vicente West, Asingan, Pangasinan | 11799.98 | 2018-07-02 |  | 2018-07-09 | 100% | 11799.98 |  |  | Completed | 100-18-07-1629 | 2018-07-02 | 100-18-07-1629 | to payment of materials for the repainting of school building at san vicente west integrated school | 11799.98 |  | 11799.98 | 0
Concreting of Road Shoulder |  | Zone 2 & 3 Macalong, Asingan, Pangasinan | 99030 | 2018-07-03 |  | 2018-07-10 | 100% | 99030 |  |  | Completed | 100-18-07-1663/1867 | 2018-07-10 |  |  | 65990 | 33040 | 99030 | 0
Repainting of School Bldg.,Fence, roofs, and plant boxes |  | Toboy Elementary School, Asingan, Pangasinan | 11430.9 | 2018-07-03 |  | 2018-07-10 | 100% | 11430.9 |  |  | Completed | 100-18-07-1771 | 2018-07-16 | 100-18-07-1863 |  | 11430.9 |  | 11430.9 | 0
Repair of bio shedder |  | MRF, Asingan | 4052 | 2018-07-09 |  | 2018-07-16 | 100% | 4052 |  |  | Completed | 100-18-07-1782 | 2018-07-17 |  |  | 4052 |  | 4052 | 0
Paint for the School Classrooms for the Brigada Eskwela |  | Asingan District I | 23320 | 2018-07-09 |  | 2018-07-16 | 100% | 23320 |  |  | Completed | 100-18-07-1700 | 2018-07-11 |  |  | 23320 |  | 23320 | 0
Construction os Solar Dryer |  | Sobol, Asingan, Pangasinan | 99586 | 2018-07-12 |  | 2018-07-19 | 100% | 99522 |  |  | Completed | 100-18-07-1731/1868 | 2018-07-13 |  |  | 76230 | 23292 | 99522 | 0
Concreting of Local Access Road |  | Zone 3, Sobol, Asingan, Pangasinan | 95042 | 2018-07-12 |  | 2018-07-19 | 100% | 95042 |  |  | Completed | 100-18-07-1732/1868 | 2018-07-13 |  |  | 71750 | 23292 | 95042 | 0
Construction of CHB Lined Canal |  | Cabalitian, Asingan, Pangasinan | 14395 | 2018-07-12 |  | 2018-07-19 | 100% | 14395 |  |  | Completed | 100-18-07-1766 | 2018-07-13 |  |  | 14395 |  | 14395 | 0
Construction of Solar Dryer along Zone 1 Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan, Pangasinan | 104512 | 2018-07-24 |  | 2018-07-31 | 100% | 104512 |  |  | Completed | 100-18-07-1822/1910 | 2018-07-24 | 101-18-07-162 |  | 61612 | 42900 | 104512 | 0
Construction of Perimeter Fence |  | Carosucan Sur, Elementary School, Carosucan Sur, Asingan, Pangasinan | 68256.5 | 2018-07-24 |  | 2018-07-31 | 100% | 68256.5 |  |  | Completed | 100-18-07-1823/1911 | 2018-07-24 |  |  | 50148.5 | 18108 | 68256.5 | 0
Repair of Roofing at Fish and Meat Section |  | Asingan Public Market | 193741 | 2018-08-02 |  | 2018-08-09 | 100% | 193741 |  |  | Completed | 100-18-08-1994/2085 | 2018-08-06 | 101-18-08-027/028 | to payment for the materials used for the repair of Roofing at Fish and Meat Section, Asingan, Pangasinan | 133857 | 59884 | 193741 | 0
Jetmatic Pump |  | Carosucan Norte Elementary School, Asingan, Pangasinan | 4700 | 2018-08-06 |  | 2018-08-13 | 100% | 4700 |  |  | Completed | 100-18-08-2020 | 2018-08-06 | 101-18-08-051 | to payment of jetmatic pump for Carosucan Norte Elementary School | 4700 |  | 4700 | 0
Continuation of the Construction of Streetlights |  | Bagong Baryo Hacienda, Toboy,Asingan, Pangasinan | 199291.5 | 2018-08-06 |  | 2018-08-13 | 100% | 199291.5 |  |  | Completed | 100-18-08-2084/2185 | 2018-08-08 | 101-18-08-060/068 | to payment for the materials used for the Continuation of the Construction of Street Lights at Bagong Baryo Hacienda, Toboy, Asingan, Pangasinan | 141227.5 | 58064 | 199291.5 | 0
Regravelling of the proposed site of Child Development Center |  | Sanchez, Asingan, Pangasinan | 61560 | 2018-08-08 |  | 2018-08-15 | 100% | 61560 |  |  | Completed | 100-18-08-2038 | 2018-08-08 | 101-18-08-067 | to payment of materials for the regravelling of the proposed site of Child Development Center at Brgy. Sanchez, Asingan, Pangasinan | 61560 |  | 61560 | 0
3 pcs., 1 1/4 Superior and 1 pc. Pitcher Pump |  | Looban Road, Calepaan, Asingan, Pangasinan | 7000 | 2018-08-08 |  | 2018-08-15 | 100% | 7000 |  |  | Completed | 100-18-08-2059 | 2018-08-08 | 101-18-08-069 | to payment of three (3) pieces 1 1/4 superior and one (1) piece pitcher PUMP for zone 4 (Looban Road) Brgy. Calepaan, Asingan, Pangasinan | 7000 |  | 7000 | 0
Repainting of Roofing, Gutter at Building A & B |  | Asingan Public Market | 117872 | 2018-08-13 |  | 2018-08-20 | 100% | 117872 |  |  | Completed | 100-18-08-2092/2184 | 2018-08-15 | 101-18-08-103/104 | to payment of materials for the repainting of roofing, gutter at building a&b Asingan Public Market | 84350 | 33522 | 117872 | 0
Continuation for the Construction of Multipurpose Bldg. |  | San Vicente West, Asingan, Pangasinan | 99697 | 2018-08-14 |  | 2018-08-21 | 100% | 99697 |  |  | Completed | 100-18-08-2080/2187 | 2018-08-14 | 101-18-08-112/113 | to payment of materials used for Continuation of the Construction of Multipurpose Bldg. at San Vicente West, Asingan, Pangasinan | 74032 | 25665 | 99697 | 0
Concreting of Road Shoulder |  | Sanchez, Asingan, Pangasinan | 199509 | 2018-08-20 |  | 2018-08-27 | 100% | 199509 |  |  | Completed | 100-18-08-2120/2197 | 2018-08-28 | 101-18-08-136/137 | to payment of materials used foe the Concreting of Road Shoulder at Brgy. Sanchez, Asingan, Pangasinan | 127749 | 71760 | 199509 | 0
Construction of Multipurpose Hall |  | San Vicente West, Asingan, Pangasinan | 99707 | 2018-08-20 |  | 2018-08-27 | 100% | 99707 |  |  | Completed | 100-18-08-2142/2188 | 2018-08-20 | 101-18-08-138/139 | to payment of materials used for the continuation of Construction of Multipurpose hall at Brgy. San Vicente West, Asingan, Pangasinan | 67397 | 32310 | 99707 | 0
Construction of Perimeter Fence at Carosucan Norte Elementary School |  | Asingan, Pangasinan | 19754 | 2018-08-30 |  | 2018-09-06 | 100% | 19754 |  |  | Completed | 100-18-08-2175/2193 | 2018-08-30 | 101-18-08-180/181 | to payment of materials for the Construction of Perimeter Fence Particular; Carosucan Norte Elementary School, Asingan, Pangasinan | 14166 | 5588 | 19754 | 0
to 1st payment of his contracts in the Construction of Farm to market Bridge at Zone IV, Coldit, Asingan Pangasinan |  | Coldit, Asingan | 1203462.45 | 2018-04-24 |  | 2018-12-05 | 80.3% | 1203462.45 |  |  | on- going | 100-18-09-2284 | 2018-09-05 | 101-18-09-033 | to 1st payment of his contracts in the Construction of Farm to market Bridge at Zone IV, Coldit, Asingan Pangasinan | 1203462.45 |  | 1203462.45 | 0
Rehabilitation of Caocan Local Access Road |  | Ariston East, Asingan, Pangasinan | 9960 | 2018-09-05 |  | 2018-09-12 | 100% | 9960 |  |  | Completed | 100-18-09-2286 | 2018-09-05 | 101-18-09-034 | to payment of materials used for the rehabilitation of Caocan Local Access, Ariston East, Asingan, Pangasinan | 9960 |  | 9960 | 0
Construction of Perimeter Fence |  | Carosucan East Elementary School, Asingan, Pangasinan | 49988 | 2018-09-06 |  | 2018-09-13 | 100% | 49988 |  |  | Completed | 100-18-09-2315/2434 | 2018-09-06 | 101-18-09-055/56 | to payment of materials used for the Construction of Perimeter Fence of Carosucan East Elementary School at Brgy. Carosucan Norte, Asingan, Pangasinan | 35325.5 | 14662.5 | 49988 | 0
Improvement of Multipurpose Hall |  | Ariston East, Asingan, Pangasinan | 49720.2 | 2018-09-07 |  | 2018-09-14 | 100% | 49720.2 |  |  | Completed | 100-18-09-2329 | 2018-09-07 | 101-18-09-059 | to payment of materials for the Improvement of Multi-purpose Hall at Brgy. Ariston East, Asingan,Pangasinan | 31105.2 | 18615 | 49720.2 | 0
Construction of Motorcyle/Bicycle Parking Shed |  | Poblacion, Asingan, Pangasinan | 156525 | 2018-09-17 |  | 2018-09-24 | 100% | 156525 |  |  | Completed | 100-18-09-2437/2366 | 2018-09-17 | 101-18-09-101/106 | To liquidate the Labor for the Construction of Motorcycle/Bicycle Parking Shed at Poblacion, Asingan, Pang. | 114685 | 41840 | 156525 | 0
Continuation of Multi-purpose Hall |  | San Vicente West, Asingan, Pangasinan | 49840 | 2018-08-20 |  | 2018-08-27 | 100% | 49840 |  |  | Completed | 100-18-09-2419 | 2018-09-20 | 101-18-09-124 | to payment of materials used for the Continuation for the Construction of Multi-purpose Hall at San Vicente West, Asingan, Pangasinan | 49840 |  | 49840 | 0
Repainting of School Buildings, Fence, Roofs and Plant Boxes |  | Narciso R. Ramos Elementary School, Asingan, Pangasinan | 10000 | 2018-09-23 |  | 2018-09-30 | 100% | 10000 |  |  | Completed | 100-18-09-2476 | 2018-09-26 | 101-18-09-160 | to payment of materials for the repainting of school buildings, fence roofs and plant boxes at NRRES, Asingan,, Pangasinan | 10000 |  | 10000 | 0
Materials for the Rehabilitation of Line Canal |  | Baro, Asingan, Pangasinan | 49992.76 | 2018-09-26 |  | 2018-10-03 | 100% | 49992.76 |  |  | Completed | 100-18-09-2514/2486 | 2018-09-26 | 101-18-09-163/162 | To liquidate the Labor for the Rehabilitation of Line Canal at Brgy. Baro, Asingan, Pangasinan | 32871.8 | 17120.96 | 49992.76 | 0
Rehabilitation of Streetlights at Brgy. Carosucan Norte, Asingan, Pangasinan |  | Carosucan Norte, Asingan, Pangasinan | 46200 | 2018-09-27 |  | 2018-10-04 | 100% | 46200 |  |  | Completed | 100-18-09-2488 | 2018-09-27 | 101-18-09-165 | to payment of the materials used for the Rehabilitation of Streetlights at Brgy. Carosucan Norte, Asingan, Pangasinan | 46200 |  | 46200 | 0
[18 empty] | 0 | 0
ECONOMIC DEVELOPMENT
ENVIRONMENTAL MANAGEMENT
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [7 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [7 empty] | Acting Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+7
Target Completion Date = [Date Started]+135+90