## 20% IRA 4th Qtr 2018
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4TH QUARTER, CY 2018
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Continuation of the Construction of Perimeter Fence Carosucan Norte Elementary School |  | Carosucan Norte, Asingan | 19997.76 | 2018-09-28 |  | 2018-10-05 | 100% | 19997.76
Rehabilitation of School Stage at T. Gante Elem. School, Asingan, Pangasinan |  | Asingan | 49891.12 | 2018-10-02 |  | 2018-10-09 | 100% | 49891.12
Rehabilitation of Drainage canal at Brgy. Carosucan Sur, Asingan Pangasinan |  | Carosucan Sur, Asingan | 22960 | 2018-09-24 |  | 2018-10-01 | 100% | 22960
Payment of snacks during orientation and briefing of farmers affected by typhoon Josie regarding the survival and recovery loan assistance (SURE) Program |  | Asingan | 3505 | 2018-10-01 |  | 2018-10-08 | 100% | 3505
Two Span Pathway Shed at AVRNHS Macalong, Asingan Pangasinan |  | Macalong, Asingan | 39905.2 | 2018-10-02 |  | 2018-10-09 | 100% | 39905.2
Rehabilitation of lined Canal and Concrete cover at Brgy. Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan | 39070.5 | 2018-10-02 |  | 2018-10-09 | 100% | 99522
Construction of Perimeter Fence at Carosucan Norte Elem. School, Asingan, Pangasinan |  | Carosucan Norte, Asingan | 147812.76 | 2018-10-02 |  | 2018-10-09 | 100% | 147812.76
Rewiring of streetlights at Brgy. Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan | 46418 | 2018-09-28 |  | 2018-10-05 | 100% | 46418
Construction of CHB Lined Canal at Zone 4, Brgy. Palaris, Asingan Pangasinan |  | Palaris, Asingan | 117345.96 | 2018-10-03 |  | 2018-10-10 | 100% | 117345.96
Installation of pitcher pump at Zone I and Zone 7, Brgy. Calepaan, Asingan, Pang. |  | Calepaan, Asingan | 15891 | 2018-10-02 |  | 2018-10-09 | 100% | 15891
Purchase of backhoe to be use at MRF, Asingan, Pang. |  | MRF, Asingan | 2996000 | 2018-10-02 |  | 2018-10-09 | 100% | 2996000
to 1st partial payment of his contract for the continuation of the Construction of Women's Center (Phase II), Asingan, Pangasinan |  | Asingan | 1199769.25 | 2018-10-02 |  | 2018-10-09 | 100% | 1199769.25
Purchase of Pulverizer machine to be used at MRF |  | Asingan | 1500000 | 2018-10-01 |  | 2018-10-08 | 100% | 1500000
Tiling of one(1) room at Don T. Bauzon Elementary School Asingan, Pangasinan |  | Asingan | 63417 | 2018-10-03 |  | 2018-10-10 | 100% | 63417
Construction of Stone Masonry at Sitio Masicampo Brgy. Dupac, Asingan, Pangasinan |  | Dupac, Asingan | 64527 | 2018-10-10 |  | 2018-10-17 | 100% | 64527
Construction of Holding Center (Curved Roof Outdoor Waiting Area) at NRRESSC Poblacion Asingan |  | NRRESSC, Poblacion, Asingan | 49902.75 | 2018-10-17 |  | 2018-10-24 | 100% | 46200
Construction of perimeter fence at Sanchez-Cabalitian Elem. School |  | Sanchez-Cabalitian, Asingan | 74205.8 | 2018-10-15 |  | 2018-10-22 | 100% | 54840
Construction of covered pathwalk (right wing) at Domanpot Community School, Asingan, Pangasinan |  | Domanpot, Asingan | 89288 | 2018-10-15 |  | 2018-10-22 | 100% | 89288
Payment of planters for the Municipal Hall |  | Asingan | 58000 | 2018-10-15 |  | 2018-10-22 | 100% | 58000
Repair & improvement of the School Social hall at San Vicente East Elementary School |  | San Vicente East, Asingan | 197068.5 | 2018-10-19 |  | 2018-10-26 | 100% | 197068.5
2nd partial payment of contract for the Continuation of the Construction of Women's Center (PHASE II), Asingan, Pangasinan |  | Asingan | 1203642.85 | 2018-10-16 |  | 2018-10-23 | 100% | 1203642.85
Repair / Rehabilitation of Multi Purposed Hall at Brgy. Poblacion West Asingan, Pangasinan |  | Poblacion West, Asingan | 49089 | 2018-10-18 |  | 2018-10-25 | 100% | 46200
Rehabilitation of Perimeter Fence at San Vicente East Elementary School, Asingan, Pangasinan |  | San Vicente East, Asingan | 11952 | 2018-10-10 |  | 2018-10-17 | 100% | 11952
Construction of perimeter fence at Sanchez-Cabalitian Elementary School, Asingan, Pangasinan |  | Sanchez-Cabalitian, Asingan | 75711.5 | 2018-11-02 |  | 2018-11-09 | 100% | 75711.5
Rehabilitation of one Classroom at San Vicente Este Elementary School, Asingan, Pangasinan |  | San Vicente East, Asingan | 29876 | 2018-10-29 |  | 2018-11-05 | 100% | 29876
To 3rd Partial payment of contract for the Continuation of the Construction of Women's Center PHASE II, Asingan, Pangasinan |  | Asingan | 1040540 | 2018-10-29 |  | 2018-11-05 | 100% | 1040540
Filling of the proposed child development center site at Brgy. Sanchez, Asingan, Pangasinan. |  | Sanchez, Asingan | 78150 | 2018-11-13 |  | 2018-11-20 | 100% | 78150
Repainting of Brgy. Multi Purpose hall Poblacion West Asingan Pangasinan |  | Poblacion West, Asingan | 49763 | 2018-11-14 |  | 2018-11-21 | 100% | 49763
Installation of electrical lights for the multipurpose hall Car. Norte National High School, Asingan, Pang. |  | Carosucan Norte, Asingan | 39037 | 2018-11-13 |  | 2018-11-20 | 100% | 39037
To 4th partial payment of contract for the Continuation of the Construction of Women's Center (phase II), Asingan, Pangasinan |  | Asingan | 1256351.25 | 2018-11-21 |  | 2018-11-28 | 100% | 1256351.25
Rehabilitation of perimeter fence at Sobol Elementary School, Asingan Pangasinan |  | Sobol, Asingan | 56471 | 2018-12-16 |  | 2018-12-23 | 100% | 56471
Repainting of roofs, walls, door grills, column and Beams at Sobol Elementary School, Asingan, Pangasinan |  | Sobol, Asingan | 29889 | 2018-11-26 |  | 2018-12-03 | 100% | 29889
Line Canal Cabalitian Asingan, Pangasinan |  | Cabalitian, Asingan | 64817.5 | 2018-11-27 |  | 2018-12-04 | 100% | 64817.5
To payment of materials for the one (1) unit class room / windows fixtures San Vicente West integrated School, Asingan, Pangasinan |  | San Vicente West, Asingan | 64915 | 2018-11-29 |  | 2018-12-06 | 100% | 64915
To payment of materials used for the Rehabilitation of Caoacan Local Access Road at Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan | 29958 | 2018-12-03 |  | 2018-12-10 | 100% | 29958
Rehabilitation of kitchen roof at Toboy Multi-purpose hall Asingan, Pangasinan |  | Toboy, Asingan | 18989 | 2018-12-03 |  | 2018-12-10 | 100% | 18989
Construction of Dog Impounding Facility at Macalong, Asingan, Pangasinan |  | Macalong, Asingan | 599464.51 | 2018-12-05 |  | 2018-12-12 | 100% | 599464.51
To 5th Partial Payment of his contract for the Continuation of the construction of Women's Center (Phase II), Asingan, Pangasinan |  | Asingan | 698850.38 | 2018-12-05 |  | 2018-12-12 | 100% | 698850.38
To payment of Ten(10) pcs. Plastic drums to be used at Asingan, Public Plaza |  | Asingan | 10000 | 2018-12-05 |  | 2018-12-12 | 100% | 10000
To payment of equipment and materials to be used at the Slaughterhouse, Asingan, Pangasinan |  | Asingan | 9750 | 2018-12-05 |  | 2018-12-12 | 100% | 9750
Installation of Streetlights at Sitio Aragaag Brgy. Bantog Asingan Pangasinan |  | Bantog, Asingan | 49815 | 2018-12-05 |  | 2018-12-12 | 100% | 49815
Concreting of pathways of Brgy. Day Cre Center at Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan | 80353.3 | 2018-12-05 |  | 2018-12-12 | 100% | 80353.3
Installation of Pitcher pump (Deep Well) at Angela Valdez Ramos National High School, Asingan Pangasinan |  | Asingan | 6945 | 2018-12-05 |  | 2018-12-12 | 100% | 6945
To payment for the materials used for the Gravelling of Farm to Market Road (Nambilangan) at Brgy. Sobol Asingan Pangasinan |  | Sobol, Asingan | 49054 | 2018-12-14 |  | 2018-12-21 | 100% | 49054
Installation of streetlights at Brgy. Bobonan, Asingan Pang |  | Bobonan, Asingan | 66544 | 2018-12-14 |  | 2018-12-21 | 100% | 66544
Installation of pitcher pumps at Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan | 22000 | 2018-12-21 |  | 2018-12-28 | 100% | 22000
Installation of Steel Barrier Railings at Poblacion East, Asingan |  | Poblacion East, Asingan | 30000 | 2018-12-21 |  | 2018-12-28 | 100% | 30000
Construction of comfort rooms at Sobol Elementary School, Sobol, Asingan |  | Sobol, Asingan | 54297 | 2018-12-21 |  | 2018-12-28 | 100% | 54297
Fabrication of filing cabinets of Senior citizen of Domanpot, Asingan |  | Domanpot, Asingan | 19894.5 | 2018-12-21 |  | 2018-12-28 | 100% | 19894.5
Filling materials for the eroded portion of the local access road at Zone 6, Calepaan, Asingan |  | Calepaan, Asingan | 39704 | 2018-12-21 |  | 2018-12-28 | 100% | 39704
Final Payment of the continuation of the construction of Women Center Building (Phase II) |  | Asingan | 599692.54 | 2018-12-21 |  | 2018-12-28 | 100% | 599692.54
Payment of pitcher pump of Purok Cappia and Inanama, Domanpot, Asingan |  | Domanpot, Asingan | 24750 | 2018-12-21 |  | 2018-12-28 | 100% | 24750
Payment of Cement for the rehabilitation of road at Bobonan, Asingan |  | Bobonan, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
Final payment of the construction of farm to market bridge at Zone IV, Coldit, Asingan |  | Coldit, Asingan | 295296.51 | 2018-12-21 |  | 2018-12-28 | 100% | 295296.51
Payment of Cement for the continuation of concreting of solar dryer in Sobol, Asingan |  | Sobol, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
Payment of Cement for the improvement at Zone V and Zone VI at Ariston West, Asingan |  | Ariston West, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
Cement for the construction of stock room at Calepaan, Asingan |  | Calepaan, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
Cement for the road shoulder at Zone II Dupac, Asingan |  | Dupac, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
Cement for the continuation of road shoulder at Zone I, Palaris, Asingan |  | Palaris, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
Cement for the rehabilitation of multi-purpose drying pavement at Zone IV, Cabalitian, Asingan |  | Cabalitian, Asingan | 10000 | 2018-12-21 |  | 2018-12-28 | 100% | 10000
ECONOMIC DEVELOPMENT
ENVIRONMENTAL MANAGEMENT
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [6 empty] | Acting Municipal Mayor