## TFU 1st qtr 2020
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of Box Culvert, Repair/Dredging and Rehabilitation of Drainage Canal at Brgy. Domanpot, Asingan, Pangasinan. |  | Domanpot, Asingan, Pangasinan | 1511161.03 | 10/11/2019 | 2020-01-01 | 100% | 1511161.03 |  | TF - LDRRMF
Construction/ repair . Dredging and Rehabilitation of Drainage Canal at Poblacion West Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 1011698.25 | 10/11/2019 | 2020-01-01 | 100% | 1011698.25 |  | TF - LDRRMF | 0
Construction of National Child Development Center at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 2498537.5 | 2019-10-23 | 2020-05-20 | 85% | 1166267.5 |  | NCDC | 1332270
Construction of Farm to Market Road at Brgy. Carosucan Norte, Asingan, Pangasinan (Excise Tax) |  | Carosucan Norte, Asingan, Pangasinan | 2678838.79 | 12/3/2019 | 2020-03-05 | 100% | 2678838.79 |  | Excise Tax | 0
Construction of Farm to Market Road and Stone Masonry at Brgy. Carosucan Sur, Asingan, Pangasinan (excise tax under LBM#76) |  | Carosucan Sur, Asingan, Pangasinan | 2677815 | 12/3/2019 | 2020-04-01 | 100% | 2410033.5 |  | Excise Tax | 267781.5
To recognized CM from Department of Agriculture RO1 for the Enhancing Innovative Family Enterprise Development (IFED) on Improved Chicken Production |  | Asingan, Pangasinan | 500000 | 2020-02-05 | 2020-04-30 | 0% |  |  | DA - IFED (delivery was suspended due to Lockdown)
Rehabilitation for the Material Recovery Facility of Asingan, Pangasinan (Funds from DENR-EMB) |  | Asingan, Pangasinan | 500000 |  |  | 0% |  |  | DENR-EMB (not yet started) | 500000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+82