## TFU 1ST qtr 2025
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
REGION: | I |  | CALENDAR YEAR: | 2025
PROVINCE: | PANGASINAN |  | QUARTER: | 1
CITY/MUNICIPALITY: | ASINGAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Construction of a Multi-Purpose Building at Poblacion West, Asingan, Pangasinan, funded under the Local Government Support Fund – Financial Assistance to Local Government Units (LGSF-FA to LGUs) and Support for Capital Outlays and Social Programs, Fiscal Year 2023, General Appropriations Act (GAA), Republic Act No. 11936 | Public Market, Asingan, Pangasinan | 49999331.49 | 2024-06-24 | 2025-01-29 | 90% | 44999398.34 |  | LGSF - FA ₱50M | -4999933.15 | 4999933.15 | 4999933.15 | 2024-08-02 | 2025-01-29
Construction of Asingan Children's Park at the Public Plaza, Poblacion East, Asingan, Pangasinan | Public Plaza, Asingan, Pangasinan | 3240000 | 2024-06-14 | 2024-12-03 | 100% | 3240000 |  | Funds from DILG P1,800,000 (SGLG Incentive Fund) + LGU Counterpart P1,440,000 |  | 0 | 0
Construction of Farm to Market Road in Macalong, Asingan, Pangasinan | Macalong, Asingan, Pangasinan | 26995756.09 | 2024-11-13 | 2025-08-04 | 100% | 26995756.09 |  | Funds from DAR |  | 0 | 0
To advance payment (Mobilization) of his contract for the concreting of Barangay Carosucan Norte Farm to Market Road (Phase 2) | Carosucan Norte, Asingan, Pangasinan | 4912500 | 2025-02-11 | 2025-04-07 | 0% | 736875 |  | Funds from DAR (30M for 6FMR)
To advance payment (Mobilization) of his contract for the concreting of Barangay Domanpot Farm to Market Road (Phase 2) | Domanpot, Asingan, Pangasinan | 4912500 | 2025-02-11 | 2025-04-07 | 0% | 736875 |  | Funds from DAR (30M for 6FMR)
To advance payment (Mobilization) of his contract for the concreting of Barangay Cabalitian Farm to Market Road (Phase 2) | Cabalitian, Asingan, Pangasinan | 4912500 | 2025-02-11 | 2025-04-07 | 0% | 736875 |  | Funds from DAR (30M for 6FMR)
To advance payment (Mobilization) of his contract for the concreting of Barangay Sanchez Farm to Market Road (Phase 2) | Sanchez, Asingan, Pangasinan | 4912500 | 2025-02-11 | 2025-04-07 | 0% | 736875 |  | Funds from DAR (30M for 6FMR)
To advance payment (Mobilization) of his contract for the concreting of Barangay Baro Farm to Market Road (Phase 2) | Baro, Asingan, Pangasinan | 4912500 | 2025-02-11 | 2025-04-07 | 0% | 736875 |  | Funds from DAR (30M for 6FMR)
To advance payment (Mobilization) of his contract for the concreting of Barangay Carosucan Sur Farm to Market Road (Phase 2) | Carosucan Sur, Asingan, Pangasinan | 4912500 | 2025-02-11 | 2025-04-07 | 0% | 736875 |  | Funds from DAR (30M for 6FMR)
Funds from DILG-Regional Office 1 for the payment of SGLG Incentive Fund 2024 Dated 12/23/2024 LBP#1847800 OR#2111625 | Asingan, Pangasinan | 1153000 | [5 empty] | for bidding - Funds from DILG -SGLG Incentive Fund 2024 |  | 1153000 | 1153000
To payment of his contract for the fabrication of two (2) sets Fiber Glass Basketball Board for use at Barangay Bantog, Asingan, Pangasinan NTP: 03/10/2025 SWA: 03/18/2025 100%CP: 299,678.40 | Asingan, Pangasinan | 299678.4 | 2025-03-10 | 2025-03-18 | 100% | 299678.4 |  | Funds from Philippine Sports Commission (PSC) for Sponsorship Assistance for the conduct of their Sports Development Activities per BR No. 879-2024 Dated 12/9/2024 LBP#552290 OR#2111604 |  | 0 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
EMELY S. BADUA |  |  | MARJORIE V. TINTE |  |  | ENGR. CARLOS F. LOPEZ, JR.
Local Budget Officer |  |  | Local Accountant |  |  | Local Chief Executive
Formulas:
Target Completion Date = [CALENDAR YEAR:]+264