## TFU 2nd qtr 2018
FDP Form 6 - Trust Fund Utilization
TRUST FUND UTILIZATION
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [9 empty] | SCHEDULE OF CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2018 | [9 empty] | FOR THE 1ST QUARTER, CY 2014
Pangasinan, Municipality of Asingan
[10 empty] | SF CASH ADVANCE | [6 empty] | LIQUIDATION |  |  | Jover Mangosong
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks |  | Date | JEV | Particulars | Check # | Check Date | Amount | Date | JEV | Amount | Date | JEV | Check # | Check Date | Amount
[6 empty] | % of Completion | Total Cost Incurred to Date |  |  | 1 | 2014-06-23 | 4 | SF on July 2014 | 50121 |  | 45000 |  |  |  | 2014-06-25 | 8 | 50122 |  | 47520
Concreting of Local Access Road at Brgy. Ariston West - Bantog, Asingan (AMP 2018) |  | Ariston West- Bantog, Asingan | 2740325.44 | 2018-05-31 | 2018-08-19 | 60% | 0 | 45 | DILG
Concreting of Local Access Road at Brgy. Carosucan Norte), Asingan (AMP 2018) | [8 empty] | DILG
Concreting of Local Access Road at Brgy. Domanpot - Sobol, Asingan (AMP 2018)
Concreting of Local Access Road at Brgy. Dupac (Sinapog), Asingan (AMP 2018) |  | Dupac, Asingan | 3836455.62 | 2018-05-31 | 2018-07-20 | 75% | 1449332.06 |  | DILG
Concreting of Local Access Road at Brgy. Sobol - Macalong, Asingan (AMP 2018) |  | Sobol - Macalong, Asingan | 5480640.88 | 2018-05-31 | 2018-09-08 | 14.85% | 813834.9 | 45 | DILG
DSWD ROI for viand and rice of 880 children in the implementation of SFP CY 2018 |  |  | 1584000 | [5 empty] | DSWD
SGLG Performance Challenge Fund 2017 |  |  | 2000000 | [5 empty] | SGLG
S.K. Mandatory Training, Federation Orientation and Election |  | Asingan | 278900 | 2018-04-01 | 2018-06-30 | 44.22% | 123318.75 |  | BRGY SK FUND
S.K. and Barangay Election 2018 |  | Asingan | 210000 | 2018-04-01 | 2018-06-30 | 72.7% | 152680.4 |  | BRGY FUNDS
Construction of Day Care Center and Bldg. for the Senior Citizens (1st tranche 50%) |  |  | 3300000 |  |  |  | 0 |  | DSWD RO1
[25 empty] | j | A | May
31
Social Pension Stipend of 1049 Social pension beneficiaries for the 1st and 2nd qtr of 2018 |  | Asingan | 2850000 | 2018-06-01 | 2018-06-30 | 100% | 2850000 |  | DSWD | [15 empty] | 3 | 30
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [6 empty] | Acting Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+35+45
Target Completion Date = [Date Started]+50