## TFU 2nd qtr 2020
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of National Child Development Center at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 2498537.5 | 2019-10-23 | 2020-05-20 | 85% | 1166267.5 |  | NCDC | 1332270
To recognized CM from Department of Agriculture RO1 for the Enhancing Innovative Family Enterprise Development (IFED) on Improved Chicken Production |  | Asingan, Pangasinan | 500000 | 2020-06-11 | 2020-12-31 | 0% |  |  | DA - IFED (staggard delivery of feeds)
Rehabilitation for the Material Recovery Facility of Asingan, Pangasinan (Funds from DENR-EMB) |  | Asingan, Pangasinan | 500000 | 2020-07-28 | 2020-09-01 | 0% |  |  | DENR-EMB (not yet started) | 500000
Social Amelioration program 2020 - 1st tranche |  | Asingan, Pangasinan | 51150000 | 2020-04-01 | 2020-05-31 | 100% | 51150000 |  | DSWD - RO1 | 0
Senior Citizen Social Pension for 1st & 2nd Qtr 2020 |  | Asingan, Pangasinan | 3261000 | 2020-06-03 | 2020-07-31 | 90% | 2934900 |  | DENR-EMB (not yet started) | 326100
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+210