## TFU 2nd qtr 2022
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitaiton/improvement of Coldit Communal Irrigation System (CIS), Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 2985000 | 2022-03-22 | 2022-06-15 | 100% | 2392314.54 |  | Department of Agriculture (DA) under the Irrigation Network Services on the National Rice Program FY 2022 ,RA11639 | -592685.46
National Nutrition Council Allowance for the year 2022 |  | Asingan, Pangasinan | 28800 | 2022-05-31 | 2022-12-31 | 0% |  |  | National Nutrition Council | -28800
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+85

## TFU 1st qtr 2022 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitaiton/improvement of Coldit Communal Irrigation System (CIS), Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 2985000 | 2022-03-22 | 2022-06-15 | 10% | 0 |  | Department of Agriculture (DA) under the Irrigation Network Services on the National Rice Program FY 2022 ,RA11639 | -2985000
0
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+85