## TFU 3rd qtr 2021
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3RD QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Bigasan Livelihood Project |  | Toboy & San Vicente West, Asingan, Pangasinan | 999300 | 2021-05-31 | 2021-06-15 | 98.69% | 986218 |  | DOLE 1 - Bigasan Livelihood Program
Rehabilitation of drainage canal w/ cover and pathwalk along P. Ramos St., Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 8999505.77 | 2021-09-09 | 2022-03-08 | 53.18% | 4785657.02 |  | Local Government Support Fund - Financial Assistance (LGSF-FA)
Continuation of the Construction of Farm to Market Road at Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 2399314 | 2021-03-10 | 2021-04-09 | 100% | 2399314 |  | EXCISE TAX (LBC#81)
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+180