## TFU 4th qtr 2018
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4TH QUARTER, CY 2018
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Concreting of Local Access Road at Brgy. Ariston West - Bantog, Asingan (AMP 2018) |  | Ariston West- Bantog, Asingan | 2740325.44 | 2018-05-31 | 2018-10-03 | 100% | 2740325.4 | 90 | DILG
Concreting of Local Access Road at Brgy. Dupac (Sinapog), Asingan (AMP 2018) |  | Dupac, Asingan | 2876767.13 | 2018-05-31 | 2018-07-20 | 100% | 2876767.13 |  | DILG
Concreting of Local Access Road at Brgy. Sobol - Macalong, Asingan (AMP 2018) |  | Sobol - Macalong, Asingan | 5425566.02 | 2018-05-31 | 2018-10-23 | 100% | 5425566.02 | 90 | DILG
Concreting of Local Access Road at Brgy. Carosucan Norte, Asingan (AMP 2018) |  | Carosucan Norte, Asingan | 2027123.97 | 2018-07-20 | 2018-10-03 | 100% | 2027123.97 | 30 | DILG
Concreting of Local Access Road at Brgy. Domanpot-Sobol, Asingan (AMP 2018) |  | Domanpot- Sobol, Asingan | 1103808 | 2018-07-20 | 2018-11-02 | 100% | 1103808 | 60 | DILG
Construction of one (1) Day Care Center at Brgy. Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan | 799480.35 | 2018-06-25 | 2018-11-15 | 100% | 799480.35 | 80 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan | 794991.91 | 2018-06-25 | 2018-10-26 | 100% | 794991.91 | 60 | DSWD RO1
Construction of Senior Citizen's Multi- Purpose Building at Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan | 998650 | 2018-06-25 | 2018-10-18 | 90% | 898785 | 45 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan | 799382.78 | 2018-06-25 | 2018-10-26 | 100% | 719444.5 | 60 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan | 799382.78 | 2018-06-25 | 2018-10-26 | 100% | 719444.5 | 60 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Domanpot, Asingan, Pangasinan |  | Domapot, Asingan | 799726.12 | 2018-06-25 | 2018-10-26 | 100% | 799726.12 | 60 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan | 799678.77 | 2018-06-25 | 2018-08-27 | 100% | 799678.77 |  | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Bantog, Asingan, Pangasinan |  | Bantog, Asingan | 799480.35 | 2018-06-25 | 2018-10-26 | 100% | 799480.35 | 60 | DSWD RO1
DSWD ROI for viand and rice of 880 children in the implementation of SFP CY 2018 |  | Asingan | 1584000 | 2018-08-01 | 2018-12-31 | 70% | 1108801.95 |  | DSWD
Construction of Riverbank Slope Protection, Calepaan, Asingan Pangasinan (PCF-SGLG 2017) |  | Calepaan, Asingan | 1999038.35 | 2018-09-17 | 2018-12-01 | 89.38% | 1786740.92 | 35 | DILG - SGLG 2017
S.K. Mandatory Training, Federation Orientation and Election |  | Asingan | 278900 | 2018-04-01 | 2018-07-31 | 60.1% | 167628.5 |  | BRGY SK FUND
S.K. and Barangay Election 2018 |  | Asingan | 210000 | 2018-04-01 | 2018-07-31 | 74.61% | 156680.4 |  | BRGY FUNDS
Social Pension Stipend to the 950 Social Pension beneficiaries for 3rd quarter of 2018 |  | Asingan | 1425000 | 2018-10-10 | 2018-10-31 | 100% | 1425000 |  | DSWD
Fund transfer from National Nutrition Council for the travelling allowance of 21 existing Barangay Nutrition Scholar for the period from January- December, 2018 |  | Asingan | 28800 | 2018-12-01 | 2018-12-31 | 100% | 28800 |  | National Nutrition Council
Transfer of Funds for the Social Pension Stipend fund for the 950 Social Pension Beneficiaries for the 4th quarter of C Y 2018 LBP Check # 1486620 dated 9/27/2018 |  | Asingan | 1425000 | 2018-12-01 | 2018-12-31 | 100% | 1425000 |  | DSWD
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [6 empty] | Acting Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+35+45+45
Target Completion Date = [Date Started]+50
Note on A27: dell:4th qtr 2018

## TFU 3rd qtr 2018 (hidden)
FDP Form 6 - Trust Fund Utilization
TRUST FUND UTILIZATION
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [9 empty] | SCHEDULE OF CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3rd QUARTER, CY 2018 | [9 empty] | FOR THE 1ST QUARTER, CY 2014
Pangasinan, Municipality of Asingan
[10 empty] | SF CASH ADVANCE | [6 empty] | LIQUIDATION |  |  | Jover Mangosong
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks |  | Date | JEV | Particulars | Check # | Check Date | Amount | Date | JEV | Amount | Date | JEV | Check # | Check Date | Amount
[6 empty] | % of Completion | Total Cost Incurred to Date |  |  | 1 | 2014-06-23 | 4 | SF on July 2014 | 50121 |  | 45000 |  |  |  | 2014-06-25 | 8 | 50122 |  | 47520
Concreting of Local Access Road at Brgy. Ariston West - Bantog, Asingan (AMP 2018) |  | Ariston West- Bantog, Asingan | 2740325.44 | 2018-05-31 | 2018-10-03 | 60% | 2219800.57 | 90 | DILG
Concreting of Local Access Road at Brgy. Dupac (Sinapog), Asingan (AMP 2018) |  | Dupac, Asingan | 3836455.62 | 2018-05-31 | 2018-07-20 | 100% | 2876767.13 |  | DILG
Concreting of Local Access Road at Brgy. Sobol - Macalong, Asingan (AMP 2018) |  | Sobol - Macalong, Asingan | 5425566.02 | 2018-05-31 | 2018-10-23 | 90% | 4821155.73 | 90 | DILG
Concreting of Local Access Road at Brgy. Carosucan Norte, Asingan (AMP 2018) |  | Carosucan Norte, Asingan | 2027123.97 | 2018-07-20 | 2018-10-03 | 100% | 1824411.57 | 30 | DILG
Concreting of Local Access Road at Brgy. Domanpot-Sobol, Asingan (AMP 2018) |  | Domanpot- Sobol, Asingan | 1103808 | 2018-07-20 | 2018-11-02 | 65% |  | 60 | DILG
Construction of one (1) Day Care Center at Brgy. Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan | 799480.35 | 2018-06-25 | 2018-11-15 | 55% | 439824.02 | 80 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan | 794991.91 | 2018-06-25 | 2018-10-26 | 31% | 211607.51 | 60 | DSWD RO1
Construction of Senior Citizen's Multi- Purpose Building at Brgy. Ariston East, Asingan, Pangasinan |  | Ariston East, Asingan | 998650 | 2018-06-25 | 2018-10-18 | 54% | 539405.1 | 45 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Sobol, Asingan, Pangasinan |  | Sobol, Asingan | 799382.78 | 2018-06-25 | 2018-10-26 | 75% | 598711.21 | 60 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Cabalitian, Asingan, Pangasinan |  | Cabalitian, Asingan | 799382.78 | 2018-06-25 | 2018-10-26 | 50.4% |  | 60 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Domanpot, Asingan, Pangasinan |  | Domapot, Asingan | 799726.12 | 2018-06-25 | 2018-10-26 | 38% | 302023.69 | 60 | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan | 799678.77 | 2018-06-25 | 2018-08-27 | 100% | 719710.89 |  | DSWD RO1
Construction of one (1) Day Care Center at Brgy. Bantog, Asingan, Pangasinan |  | Bantog, Asingan | 799480.35 | 2018-06-25 | 2018-10-26 | 61% | 486829.63 | 60 | DSWD RO1
DSWD ROI for viand and rice of 880 children in the implementation of SFP CY 2018 |  | Asingan | 1584000 | 2018-08-01 | 2018-12-31 | 22.22% | 352001 |  | DSWD
Construction of Riverbank Slope Protection, Calepaan, Asingan Pangasinan (PCF-SGLG 2017) |  | Calepaan, Asingan | 1999038.35 | 2018-09-17 | 2018-12-01 | 15% | 299855.83 | 35 | DILG - SGLG 2017
S.K. Mandatory Training, Federation Orientation and Election |  | Asingan | 278900 | 2018-04-01 | 2018-07-31 | 100% | 167628.5 |  | BRGY SK FUND
S.K. and Barangay Election 2018 |  | Asingan | 210000 | 2018-04-01 | 2018-07-31 | 100% | 148500 |  | BRGY FUNDS
Social Pension Stipend to the 950 Social Pension beneficiaries for 3rd quarter of 2018 |  | Asingan | 1425000 | 2018-10-10 | 2018-10-31 | 100% | 1425000 |  | DSWD
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [6 empty] | Acting Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+35+45+45
Target Completion Date = [Date Started]+50
Note on A30: dell:4th qtr 2018

## TFU 2nd qtr 2018 (hidden)
FDP Form 6 - Trust Fund Utilization
TRUST FUND UTILIZATION
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [9 empty] | SCHEDULE OF CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2018 | [9 empty] | FOR THE 1ST QUARTER, CY 2014
Pangasinan, Municipality of Asingan
[10 empty] | SF CASH ADVANCE | [6 empty] | LIQUIDATION |  |  | Jover Mangosong
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks |  | Date | JEV | Particulars | Check # | Check Date | Amount | Date | JEV | Amount | Date | JEV | Check # | Check Date | Amount
[6 empty] | % of Completion | Total Cost Incurred to Date |  |  | 1 | 2014-06-23 | 4 | SF on July 2014 | 50121 |  | 45000 |  |  |  | 2014-06-25 | 8 | 50122 |  | 47520 | Contract Price
Concreting of Local Access Road at Brgy. Ariston West - Bantog, Asingan (AMP 2018) |  | Ariston West- Bantog, Asingan | 2740325.44 | 2018-05-31 | 2018-08-19 | 60% | 0 | 45 | DILG | [15 empty] | 2466445.08 | 15189716
Concreting of Local Access Road at Brgy. Carosucan Norte), Asingan (AMP 2018) | [8 empty] | DILG
Concreting of Local Access Road at Brgy. Domanpot - Sobol, Asingan (AMP 2018)
Concreting of Local Access Road at Brgy. Dupac (Sinapog), Asingan (AMP 2018) |  | Dupac, Asingan | 3836455.62 | 2018-05-31 | 2018-07-20 | 75% | 1449332.06 |  | DILG | [15 empty] | 2876767.13
Concreting of Local Access Road at Brgy. Sobol - Macalong, Asingan (AMP 2018) |  | Sobol - Macalong, Asingan | 5480640.88 | 2018-05-31 | 2018-09-08 | 14.85% | 813834.9 | 45 | DILG | [15 empty] | 5425566.08
DSWD ROI for viand and rice of 880 children in the implementation of SFP CY 2018 |  |  | 1584000 | [5 empty] | DSWD
SGLG Performance Challenge Fund 2017 |  |  | 2000000 | [5 empty] | SGLG
S.K. Mandatory Training, Federation Orientation and Election |  | Asingan | 278900 | 2018-04-01 | 2018-06-30 | 44.22% | 123318.75 |  | BRGY SK FUND
S.K. and Barangay Election 2018 |  | Asingan | 210000 | 2018-04-01 | 2018-06-30 | 72.7% | 152680.4 |  | BRGY FUNDS
Construction of Day Care Center and Bldg. for the Senior Citizens (1st tranche 50%) |  |  | 3300000 |  |  |  | 0 |  | DSWD RO1
[28 empty] | j | A | May
[27 empty] | 28 | 31
0
Social Pension Stipend of 1049 Social pension beneficiaries for the 1st and 2nd qtr of 2018 |  | Asingan | 2850000 | 2018-06-01 | 2018-06-30 | 100% | 2850000 |  | DSWD | [18 empty] | 3 | 30
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [6 empty] | Acting Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+35+45
Target Completion Date = [Date Started]+50

## TFU 1st qtr 2018 (hidden)
FDP Form 6 - Trust Fund Utilization
TRUST FUND UTILIZATION
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES | [9 empty] | SCHEDULE OF CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2018 | [9 empty] | FOR THE 1ST QUARTER, CY 2014
Pangasinan, Municipality of Asingan
[10 empty] | SF CASH ADVANCE | [6 empty] | LIQUIDATION |  |  | Jover Mangosong
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks |  | Date | JEV | Particulars | Check # | Check Date | Amount | Date | JEV | Amount | Date | JEV | Check # | Check Date | Amount
[6 empty] | % of Completion | Total Cost Incurred to Date |  |  | 1 | 2014-06-23 | 4 | SF on July 2014 | 50121 |  | 45000 |  |  |  | 2014-06-25 | 8 | 50122 |  | 47520
Continuation/completion of Rural Health Unit(RHU) Building at the Municipality of Asingan, Pangasinan |  | Asingan | 4988906.54 | 2016-09-30 | 2017-06-15 | 100% | 4988906.54 |  | Funds from DOH RO1 | [15 empty] | 100%
Fund transfer from DSWD RO1 - Social Pension Fund for the stipend of 657 beneficiaries, 3rd and 4th quarter of 2017 |  |  | 1971000 | 2018-03-01 | 2018-05-31 | 90.56% | 1785000 |  | Funds from DSWD RO1 | [15 empty] | 90.56%
[28 empty] | j | A | May
[27 empty] | 28 | 31
0
[28 empty] | 3 | 30
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ATTY. JOSHUA V. VIRAY
Municipal Accountant | [6 empty] | Acting Municipal Mayor