## TFU 4th qtr 2019
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4TH QUARTER, CY 2019
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Upgrading Local Access Road at Brgy. Carosucan Norte - Carosucan Sur, Asingan, Pangasinan |  | Carosucan Norte - Carosucan Sur, Asingan, Pangasinan | 4597512.74 | 2019-09-27 | 2019-11-21 | 100% | 4597512.74 |  | AM 2019
Upgrading Local Access Road at Brgy. Coldit - San Vicente West, Asingan, Pangasinan |  | Coldit - San Vicente West, Asingan, Pangasinan | 5041694.49 | 2019-09-27 | 2019-11-26 | 100% | 5041694.49 |  | AM 2019
Construction of Footbridge at Brgy. Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 1998774.69 | 2019-09-27 | 2019-12-21 | 100% | 1998774.69 |  | AM 2019
Construction of Box Culvert, Repair/Dredging and Rehabilitation of Drainage Canal at Brgy. Domanpot, Asingan, Pangasinan. |  | Domanpot, Asingan, Pangasinan | 1511161.03 | 10/11/2019 | 2020-01-31 | 100% | 1511161.03 |  | TF - LDRRMF
Construction of Drainage Canal at Brgy's. Dupac - Poblacion East, Asingan, Pangasinan |  | Dupac-Poblacion East, Asingan, Pangasinan | 1009242.36 | 2019-10-11 | 2019-12-21 | 100% | 1009242.36 |  | TF - LDRRMF
Construction/ repair . Dredging and Rehabilitation of Drainage Canal at Poblacion West Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 1011698.25 | 10/11/2019 | 2020-01-31 | 100% | 1011698.25 |  | TF - LDRRMF
Construction of Drainage Canal at Brgy's. Macalong-Dupac, Asingan, Pangasinan |  | Macalong-Dupac, Asingan, Pangasinan | 810337.5 | 2019-10-22 | 2019-12-07 | 100% | 810337.5 |  | TF - LDRRMF
Implementation of Seed Capital Fund for Various Microenterprise Development Projects of Sustainable Livelihood Program Participants of the CY 2018 |  | Asingan, Pangasinan | 2175000 | 2019-12-05 | 2019-12-13 | 100% | 2175000 |  | DSWD - SLP 2018
Construction of National Child Development Center at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 2498537.5 | 2019-10-23 | 2020-05-20 | 70.4% | 1758990.88 |  | NCDC
Construction of Farm to Market Road at Brgy. Carosucan Norte, Asingan, Pangasinan (Excise Tax) |  | Carosucan Norte, Asingan, Pangasinan | 2678838.79 | 12/3/2019 | 2020-03-05 | 100% | 2678838.79 |  | Excise Tax
Construction of Farm to Market Road and Stone Masonry at Brgy. Carosucan Sur, Asingan, Pangasinan (excise tax under LBM#76) |  | Carosucan Sur, Asingan, Pangasinan | 2677815 | 12/3/2019 | 2019-07-10 | 15% | 401672.25 |  | Excise Tax
Traveling allowance of 24 existing BNS for CY 2019 |  | Asingan, Pangasinan | 28600 | 2019-12-12 | 2019-12-27 | 100% | 28584
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+55