## TFU 4th qtr 2020
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of Farm to Market Road and Stone Masonry at Brgy. Carosucan Sur, Asingan, Pangasinan (excise tax under LBM#76) |  | Carosucan Sur, Asingan, Pangasinan | 2677815 | 12/3/2019 | 2020-04-01 | 100% | 2677815 |  | Excise Tax | 0 | 0
To recognized CM from Department of Agriculture RO1 for the Enhancing Innovative Family Enterprise Development (IFED) on Improved Chicken Production |  | Asingan, Pangasinan | 500000 | 2020-06-11 | 2020-12-31 | 98.41% | 492072.58 |  | DA - IFED (staggard delivery of feeds) |  | 7927.42
Rehabilitation for the Material Recovery Facility of Asingan, Pangasinan (Funds from DENR-EMB) |  | Asingan, Pangasinan | 500000 | 2020-07-28 | 2020-09-01 | 100% | 399712.07 |  | DENR-EMB | 100287.93 | 100287.93
Rehabilitation of Asingan Triage and Isolation Facility at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 199845 | 2020-10-14 | 2020-11-04 | 100% | 199845 |  | DOE - TeaM Sual |  | 0
CONSTRUCTION OF DRAINAGE CANAL IN BRGY. MCALONG - DOMANPOT |  | MACALONG - DOMANPOT, ASINGAN, PANGASINAN | 3998766.72 | 2020-10-27 | 2021-02-04 | 100% | 3598890.05 |  | AM2020 |  | 399876.67
UPGRADING OF COLDIT - SAN VICENTE ROAD IN BRGY. COLDIT AND SAN VICENTE WEST |  | BRGY. COLDIT - SAN VICENTE WEST, ASINGAN, PANGASINAN | 2998931.85 | 2020-10-27 | 2020-12-11 | 100% | 2699038.67 |  | AM2020 |  | 299893.18
UPGRADING OF PUGONG ROAD IN BARANGAY ARISTON EAST |  | SITIO PUGONG, BRGY. ARISTON EAST, ASINGAN, PANGASINAN | 2998658.73 | 2020-10-27 | 2020-12-11 | 100% | 2698792.86 |  | AM2020 |  | 299865.87
CONSTRUCTION OF LINED CANAL & BOX CULVERT IN ZONE 1 OF BRGY. MACALONG |  | ZONE 1, BRGY. MACALONG, ASINGAN, PANGASINAN | 1622182.53 | 2020-10-27 | 2021-01-05 | 100% | 1459964.28 |  | AM2020 |  | 162218.25
Concreting of farm to market road at Carosucan Norte-Carosucan Sur, Asingan, Pangasinan |  | Carosucan Norte - Carosucan Sur, Asingan, Pangasinan | 946485 | 2020-12-04 | 2021-01-03 | 100% | 946485 |  | Excise Tax (LBM#79) |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+120

## TFU 3rd qtr 2020 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3rd QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of National Child Development Center at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 2498537.5 | 2019-10-23 | 2020-05-20 | 100% | 2498537.5 |  | NCDC | 0
To recognized CM from Department of Agriculture RO1 for the Enhancing Innovative Family Enterprise Development (IFED) on Improved Chicken Production |  | Asingan, Pangasinan | 500000 | 2020-06-11 | 2020-12-31 | 50.56% | 252799.58 |  | DA - IFED (staggard delivery of feeds)
Rehabilitation for the Material Recovery Facility of Asingan, Pangasinan (Funds from DENR-EMB) |  | Asingan, Pangasinan | 500000 | 2020-07-28 | 2020-09-01 | 100% | 399712.07 |  | DENR-EMB | 100287.93
Senior Citizen Social Pension for 1st & 2nd Qtr 2020 |  | Asingan, Pangasinan | 3261000 | 2020-06-03 | 2020-07-31 | 100% | 3261000 |  | DSWD - RO1 | 0
To C/A of wages/stipend of 525 TUPAD recipients |  | Asingan, Pangasinan | 1814400 | 2020-07-01 | 2020-09-30 | 100% | 1814400 |  | DOLE - TUPAD
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+210

## TFU 2nd qtr 2020 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of National Child Development Center at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 2498537.5 | 2019-10-23 | 2020-05-20 | 85% | 1166267.5 |  | NCDC | 1332270
To recognized CM from Department of Agriculture RO1 for the Enhancing Innovative Family Enterprise Development (IFED) on Improved Chicken Production |  | Asingan, Pangasinan | 500000 | 2020-06-11 | 2020-12-31 | 0% |  |  | DA - IFED (staggard delivery of feeds)
Rehabilitation for the Material Recovery Facility of Asingan, Pangasinan (Funds from DENR-EMB) |  | Asingan, Pangasinan | 500000 | 2020-07-28 | 2020-09-01 | 0% |  |  | DENR-EMB (not yet started) | 500000
Social Amelioration program 2020 - 1st tranche |  | Asingan, Pangasinan | 51150000 | 2020-04-01 | 2020-05-31 | 100% | 51150000 |  | DSWD - RO1 | 0
Senior Citizen Social Pension for 1st & 2nd Qtr 2020 |  | Asingan, Pangasinan | 3261000 | 2020-06-03 | 2020-07-31 | 90% | 2934900 |  | DENR-EMB (not yet started) | 326100
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+210

## TFU 1st qtr 2020 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2020
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Construction of Box Culvert, Repair/Dredging and Rehabilitation of Drainage Canal at Brgy. Domanpot, Asingan, Pangasinan. |  | Domanpot, Asingan, Pangasinan | 1511161.03 | 10/11/2019 | 2020-01-01 | 100% | 1511161.03 |  | TF - LDRRMF
Construction/ repair . Dredging and Rehabilitation of Drainage Canal at Poblacion West Asingan Pangasinan |  | Poblacion West, Asingan, Pangasinan | 1011698.25 | 10/11/2019 | 2020-01-01 | 100% | 1011698.25 |  | TF - LDRRMF | 0
Construction of National Child Development Center at Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 2498537.5 | 2019-10-23 | 2020-05-20 | 85% | 1166267.5 |  | NCDC | 1332270
Construction of Farm to Market Road at Brgy. Carosucan Norte, Asingan, Pangasinan (Excise Tax) |  | Carosucan Norte, Asingan, Pangasinan | 2678838.79 | 12/3/2019 | 2020-03-05 | 100% | 2678838.79 |  | Excise Tax | 0
Construction of Farm to Market Road and Stone Masonry at Brgy. Carosucan Sur, Asingan, Pangasinan (excise tax under LBM#76) |  | Carosucan Sur, Asingan, Pangasinan | 2677815 | 12/3/2019 | 2020-04-01 | 100% | 2410033.5 |  | Excise Tax | 267781.5
To recognized CM from Department of Agriculture RO1 for the Enhancing Innovative Family Enterprise Development (IFED) on Improved Chicken Production |  | Asingan, Pangasinan | 500000 | 2020-02-05 | 2020-04-30 | 0% |  |  | DA - IFED (delivery was suspended due to Lockdown)
Rehabilitation for the Material Recovery Facility of Asingan, Pangasinan (Funds from DENR-EMB) |  | Asingan, Pangasinan | 500000 |  |  | 0% |  |  | DENR-EMB (not yet started) | 500000
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+82