## TFU 4th qtr 2021
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Bigasan Livelihood Project |  | Toboy & San Vicente West, Asingan, Pangasinan | 999300 | 2021-05-31 | 2021-06-15 | 98.69% | 986218 |  | DOLE 1 - Bigasan Livelihood Program
Rehabilitation of drainage canal w/ cover and pathwalk along P. Ramos St., Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 8999505.77 | 2021-09-09 | 2021-12-10 | 100% | 8999505.77 |  | Local Government Support Fund - Financial Assistance (LGSF-FA)
Procurement of Medicines and Apparatus to be distributed to 21 barangays from PCSO |  | Asingan, Pangasinan | 579262.5 | 2021-09-23 | 2021-10-05 | 100% | 579262.5 |  | PCSO Fund
BNS Allowance from January 2021 to December 2021 charged under the fund coming from National Nutrition Council |  | Asingan Pangasinan | 28800 | 2021-12-13 | 2021-12-31 | 100% | 28800 |  | BNS - Funds from Provincial Capitol
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor

## TFU 3rd qtr 2021 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3RD QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Bigasan Livelihood Project |  | Toboy & San Vicente West, Asingan, Pangasinan | 999300 | 2021-05-31 | 2021-06-15 | 98.69% | 986218 |  | DOLE 1 - Bigasan Livelihood Program
Rehabilitation of drainage canal w/ cover and pathwalk along P. Ramos St., Poblacion West, Asingan, Pangasinan |  | Poblacion West, Asingan, Pangasinan | 8999505.77 | 2021-09-09 | 2022-03-08 | 53.18% | 4785657.02 |  | Local Government Support Fund - Financial Assistance (LGSF-FA)
Continuation of the Construction of Farm to Market Road at Carosucan Sur, Asingan, Pangasinan |  | Carosucan Sur, Asingan, Pangasinan | 2399314 | 2021-03-10 | 2021-04-09 | 100% | 2399314 |  | EXCISE TAX (LBC#81)
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+180

## TFU 2nd qtr 2021 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2ND QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Bigasan Livelihood Project |  | Toboy & San Vicente West, Asingan, pangasinan | 999300 | 2021-05-31 | 2021-06-15 | 1.071% | 10700
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor

## TFU 1st qtr 2021 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2021
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
CONSTRUCTION OF DRAINAGE CANAL IN BRGY. MCALONG - DOMANPOT |  | MACALONG - DOMANPOT, ASINGAN, PANGASINAN | 3998766.72 | 2020-10-27 | 2021-02-04 | 100% | 3998766.72 |  | AM2020 | 0 | 0
CONSTRUCTION OF LINED CANAL & BOX CULVERT IN ZONE 1 OF BRGY. MACALONG |  | ZONE 1, BRGY. MACALONG, ASINGAN, PANGASINAN | 1622182.53 | 2020-10-27 | 2021-01-05 | 100% | 1622182.53 |  | AM2020 | 0 | 0
UPGRADING OF PUGONG ROAD IN BARANGAY ARISTON EAST |  | SITIO PUGONG, BRGY. ARISTON EAST, ASINGAN, PANGASINAN | 2998658.73 | 2020-10-27 | 2020-12-11 | 100% | 2998658.73 |  | AM2020 |  | 0
UPGRADING OF COLDIT - SAN VICENTE ROAD IN BRGY. COLDIT AND SAN VICENTE WEST |  | BRGY. COLDIT - SAN VICENTE WEST, ASINGAN, PANGASINAN | 2998931.85 | 2020-10-27 | 2020-12-11 | 100% | 2998931.85 |  | AM2020 |  | 0
Concreting of farm to market road at Carosucan Norte-Carosucan Sur, Asingan, Pangasinan |  | Carosucan Norte - Carosucan Sur, Asingan, Pangasinan | 946485 | 2020-12-04 | 2021-01-03 | 100% | 946485 |  | Excise Tax (LBM#79) | 0 | 0
Enclosure of Cottages for Isolation at Brgy. Macalong, Asingan, Pangasinan PO Date: 03/02/2021 SWA: 03/10/2021 |  | Macalong, Asingan, Pangasinan | 49960 | 2021-03-10 | 2021-03-23 | 100% | 49960 |  | TeaM- Sual (DOE) |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+100