## TFU 4th qtr 2022
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 4th QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitaiton/improvement of Coldit Communal Irrigation System (CIS), Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 2985000 | 2022-03-22 | 2022-06-15 | 100% | 2985000 |  | Department of Agriculture (DA) under the Irrigation Network Services on the National Rice Program FY 2022 ,RA11639 | 0
National Nutrition Council Allowance for the year 2022 |  | Asingan, Pangasinan | 28800 | 2022-05-31 | 2022-09-30 | 100% | 28800 |  | National Nutrition Council | 0
Contract for the Continuation of Concreting of FMR (Zone1 Interior Road & Banaoang Road) at Car. Norte (EXCISE TAX) RI:0113050100005 |  | Carosucan Norte, Asingan, Pangasinan | 1048521.78 | 2022-11-21 | 2022-12-21 | 100% | 1048521.78 |  | Excise Taxes | 0
To payment of water pump and Knapsack sprayer to be use of the Excise Tax Beneficiaries PO:11/24/22 |  | Asingan, Pangasinan | 198900 | 2022-11-24 | 2022-12-01 | 100% | 198900 |  | Excise Taxes
Payment from the Department of Health One Covid_19 ALLOWANCE (OCA) of RHU Employees from January to February 2022 |  | Asingan, Pangasinan | 936000 | 2022-11-01 | 2022-11-29 | 100% | 936000 |  | DOH - One COVID 19 Allowance
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+85

## TFU 3rd qtr 2022 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 3rd QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitaiton/improvement of Coldit Communal Irrigation System (CIS), Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 2985000 | 2022-03-22 | 2022-06-15 | 100% | 2392314.54 |  | Department of Agriculture (DA) under the Irrigation Network Services on the National Rice Program FY 2022 ,RA11639 | -592685.46
National Nutrition Council Allowance for the year 2022 |  | Asingan, Pangasinan | 28800 | 2022-05-31 | 2022-09-30 | 100% | 28800 |  | National Nutrition Council | 0
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+85

## TFU 2nd qtr 2022 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitaiton/improvement of Coldit Communal Irrigation System (CIS), Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 2985000 | 2022-03-22 | 2022-06-15 | 100% | 2392314.54 |  | Department of Agriculture (DA) under the Irrigation Network Services on the National Rice Program FY 2022 ,RA11639 | -592685.46
National Nutrition Council Allowance for the year 2022 |  | Asingan, Pangasinan | 28800 | 2022-05-31 | 2022-12-31 | 0% |  |  | National Nutrition Council | -28800
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+85

## TFU 1st qtr 2022 (hidden)
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2022
Pangasinan, Municipality of Asingan
Program or Project | AGENCY | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
Rehabilitaiton/improvement of Coldit Communal Irrigation System (CIS), Brgy. Coldit, Asingan, Pangasinan |  | Coldit, Asingan, Pangasinan | 2985000 | 2022-03-22 | 2022-06-15 | 10% | 0 |  | Department of Agriculture (DA) under the Irrigation Network Services on the National Rice Program FY 2022 ,RA11639 | -2985000
0
0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+85