## 4th Qtr 20% LDF
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  |  | CALENDAR YEAR: | 2024
PROVINCE: PANGASINAN |  |  | QUARTER: | 4
CITY/MUNICIPALITY: ASINGAN
Program or Project | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Installation of six (6) units Solar Streetlights with post at Sitio Panagidan, Baro going to Cabaruan, Bantog, Asingan, Pangasinan NTP: 08/07/2024 SWA: 08/16/2024 100% CP: 149,281.65 | Bantog, Asingan, Pangasinan | 149281.65 | 2024-08-07 | 10 | 2024-08-16 | 100% | 149281.65 |  |  |  |  | 149280.65 | 0
Construction of Segregation Area at Material Recovery Facility at Bantog, Asingan, Pangasinan NTP: 08/06/2024 SWA: 08/22/2024 100% CP: 498,789.90 | Bantog, Asingan, Pangasinan | 498789.9 | 2024-08-06 | 17 | 2024-08-22 | 100% | 498789.9 |  |  |  |  | 498788.9 | 0
Continuation of the construction of Sobol Multi-Purpose Building, Asingan, Pangasinan NTP: 08/06/2024 SWA: 10/09/2024 CP: 998,707.20 | Sobol, Asingan, Pangasinan | 998707.2 | 2024-08-06 | 65 | 2024-10-09 | 100% | 998707.2 |  |  |  |  | 998706.2 | 0
Cementing of flooring, installation of kitchen sink & roofing extensions of Child Development Center, Brgy. Dupac, Asingan, Pang. NTP: 09/25/2024 SWA: 10/04/2024 100% CP: 119,034.07 | Dupac, Asingan, Pangasinan | 119034.07 | 2024-09-25 | 10 | 2024-10-04 | 100% | 119034.07 |  |  |  |  | 119033.07 | 0
Solar Lights for 4P's Garden of Sacrifice and White Angel Garden located at Zone 1 and Zone 3, Coldit, Asingan, Pangasinan | Coldit, Asingan, Pangasinan | 9820 | 2024-11-11 | 4 | 2024-11-15 | 100% | 9820 |  |  |  |  | 9819 | 0
Solid Waste Tipping Fee from September 10, 2024 - October 24, 2024 | Asingan, Pangasinan | 36397 | 2024-09-10 | 45 | 2024-10-24 | 100% | 36397 |  |  |  |  | 36396 | 0
Concreting of Farm to Market Road at Zone 7 Carosucan Sur, Asingan, Pangasinan NTP: 05/17/2024 SWA: 07/04/2024 100% CP: 499,799.61 | Carosucan Sur, Asingan, Pangasinan | 499799.61 | 2024-05-17 | 49 | 2024-07-04 | 100% | 499799.61 |  |  |  |  | 499798.61 | 0
Repair of court flooring of basketball court at Zone 1, Barangay Ariston West, Asingan, Pangasinan NTP: 09/05/2024 SWA: 09/13/2024 100% CP: 99,778.33 | Ariston West, Asingan, Pangasinan | 99778.33 | 2024-09-05 | 9 | 2024-09-13 | 100% | 99778.33 |  |  |  |  | 99777.33 | 0
Renovation of water drainage of the multi-purpose covered court located at Zone 3, Barangay Carosucan Sur, Asingan, Pangasinan NTP: 10/09/2024 SWA: 10/17/2024 CP: 49,619.00 | Carosucan Sur, Asingan, Pangasinan | 49619 | 2024-10-09 | 9 | 2024-10-17 | 100% | 49619 |  |  |  |  | 49618 | 0
Concreting of Farm to Market Road at Sitio Dusan, Barangay Dupac, Asingan, Pangasinan NTP: 06/18/2024 SWA: 07/03/2024 100% CP: 198,865.19 RI: 0113050180006 | Dupac, Asingan, Pangasinan | 198865.19 | 2024-06-18 | 16 | 2024-07-03 | 100% | 198865.19 |  |  |  |  | 198864.19 | 0
Construction of Bridge Culvert at Zone 6, Bobonan, Asingan, Pangasinan NTP: 05/15/2024 SWA: 05/31/2024 100% CP: 299,843.40 | Bobonan, Asingan, Pangasinan | 299843.4 | 2024-05-15 | 17 | 2024-05-31 | 100% | 299843.4 |  |  |  |  | 299842.4 | 0
Concreting of Road Shoulder at Zone 1, Barangay Bobonan, Asingan, Pangasinan NTP: 10/17/2024 SWA: 10/30/2024 100% CP: 158,566.00 RI: 0113050070001 | Bobonan, Asingan, Pangasinan | 158566 | 2024-10-17 | 14 | 2024-10-30 | 100% | 158566 |  |  |  |  | 158565 | 0
Installation of four (4) units Solar Streetlights at Barangay Macalong, Asingan, Pangasinan NTP: 07/26/2024 SWA: 08/05/2024 100% CP: 99,676.07 | Macalong, Asingan, Pangasinan | 99676.07 | 2024-07-26 | 11 | 2024-08-05 | 100% | 99676.07 |  |  |  |  | 99675.07 | 0
Installation of Solar Street Light without post for Barangay San Vicente East, Asingan, Pangasinan PO: 11/14/2024 SWA: 11/15/2024 100% CP: 9,840.00 | San Vicente East, Asingan, Pangasinan | 9840 | 2024-11-14 | 2 | 2024-11-15 | 100% | 9840 |  |  |  | 9839 | 9839 | 0
Concreting of Road Shoulder at Zone 1, Barangay Bobonan, Asingan, Pangasinan NTP: 11/27/2024 SWA: 12/04/2024 100% CP: 124,238.98 RI: 0113050070001 | Bobonan, Asingan, Pangasinan | 24238.98 | 2024-11-27 | 8 | 2024-12-04 | 100% | 24238.98 |  |  |  | 24237.98 | 24237.98 | 0
Construction of PWD Ramp at STAC Building, Barangay Macalong, Asingan, Pangasinan NTP: 12/03/2024 SWA: 12/11/2024 100% CP: 198,850.00 | Macalong, Asingan, Pangasinan | 198850 | 2024-12-03 | 9 | 2024-12-11 | 100% | 198850 |  |  |  | 198849 | 198849 | 0
Concreting of Road Shoulder along Caoacan Farm to Market Road at Barangay Ariston East, Asingan, Pangasinan NTP: 11/22/2024 SWA: 11/24/2024 100% CP: 39,700.00 | Ariston East, Asingan, Pangasinan | 39700 | 2024-11-22 | 3 | 2024-11-24 | 100% | 39700 |  |  |  | 39699 | 39699 | 0
Purchase of Cement, Sand & Gravel & 3 sets of Solar Light for Sangguniang Barangay of Poblacion East, Asingan, Pangasinan NTP: 06/18/2024 SWA: 06/21/2024 100% CP: 39,571.00 | Poblacion East, Asingan, Pangasinan | 39571 | 2024-06-18 | 4 | 2024-06-21 | 100% | 39571 |  |  | 39570 | 39570 | 39570 | 0
Purchase of Solar Street Light to be installed in Ariston West, Asingan, Pangasinan NTP: 11/19/2024 SWA: 11/22/2024 100% CP: 99,610.89 | Ariston West, Asingan, Pangasinan | 99610.89 | 2024-11-19 | 4 | 2024-11-22 | 100% | 99610.89 |  |  | 99609.89 | 99609.89 | 99609.89 | 0
Installation of Solar Streetlight with Grid/Frame at Sitio Aragaag, Bantog, Asingan, Pangasinan NTP: 07/22/2024 SWA: 07/31/2024 100% CP: 99,569.89 | Bantog, Asingan, Pangasinan | 99569.89 | 2024-07-22 | 10 | 2024-07-31 | 100% | 99569.89
Installation of two (2) units Solar Type Light at Sitio Riverside, Toboy, Asingan, Pangasinan NTP: 06/05/2024 SWA: 06/13/2024 100% CP: 49,992.55 | Toboy, Asingan, Pangasinan | 49992.55 | 2024-06-05 | 9 | 2024-06-13 | 100% | 49992.55
Installation of Solar Lights of the basketball court at Purok Inanama, Domanpot, Asingan, Pangasinan NTP: 11/21/2024 SWA: 11/28/2024 100% CP: 99,579.98 | Domanpot, Asingan, Pangasinan | 99579.98 | 2024-11-21 | 8 | 2024-11-28 | 100% | 99579.98
Installation of two (2) Solar Street Lights and one (1) Lamp for Barangay Sanchez, Asingan, Pangasinan NTP: 11/28/2024 SWA: 12/05/2024 100% CP: 59,727.65 | Sanchez, Asingan, Pangasinan | 59727.65 | 2024-11-28 | 8 | 2024-12-05 | 100% | 59727.65
Construction of Municipal Slaughterhouse at Toboy, Asingan, Pangasinan NTP: 08/06/2024 SWA: 10/09/2024 53.31% CP: 3,998,533.80 | Toboy, Asingan, Pangasinan | 3998533.8 | 2024-08-06 | 65 | 2024-10-09 | 53.31% | 2131869
Construction of Road Shoulder at Zone 7 Bobonan, Asingan, Pangasinan NTP: 12/04/2024 SWA: 12/12/2024 100% CP: 79,912.64 | Bobonan, Asingan, Pangasinan | 79912.64 | 2024-12-04 | 9 | 2024-12-12 | 100% | 79912.64
Payment for the pP100% CP: 49,715.00 | Calepaan, Asingan, Pangasinan | 49715 | 2024-06-27 | 5 | 2024-07-01 | 100% | 49715
Construction of Segregation Area at Material Recovery Facility at Barangay Bantog, Asingan, Pangasinan NTP: 11/14/2024 SWA: 12/10/2024 100% CP: 498,789.90 | Bantog, Asingan, Pangasinan | 498789.9 | 2024-11-14 | 27 | 2024-12-10 | 100% | 498789.9
Purchase of materials to be used in repair/rehabilitation of Line Canal at Zone 2 Brgy. Baro, Asingan, Pangasinan NTP: 07/31/2024 SWA: 08/05/2024 100% CP: 29,550.00 | Baro, Asingan, Pangasinan | 29550 | 07/31/2024 | 6 | 2024-08-05 | 100% | 29550
Installation of four units Solar Type Light without post to be installed at Sitio Hacienda Uno & Dos at Brgy. Toboy, Asingan, Pang. NTP: 05/03/2024 SWA: 05/06/2024 100% CP: 39,720.00 | Toboy, Asingan, Pangasinan | 39720 | 2024-05-03 | 4 | 2024-05-06 | 100% | 39720
Installation of two (2) units of Solar Type Light with Post at Barangay Palaris, Asingan, Pangasinan NTP: SWA: 12/03/2024 100% CP: 49,462.78 | Palaris, Asingan, Pangasinan | 49462.78 | 2024-12-01 | 3 | 2024-12-03 | 100% | 49462.78
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
EMELY S. BADUA | [5 empty] | ENGR. CARLOS F. LOPEZ, JR.
Local Budget Officer | [5 empty] | Municipal Mayor