## 1st Qtr 20% LDF
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
REGION: I | [5 empty] | CALENDAR YEAR: | 2023
PROVINCE: PANGASINAN | [5 empty] | QUARTER: | 1
CITY/MUNICIPALITY: ASINGAN
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Installation, drilling of shallow well for the satellite market at Toboy, Asingan, Pangasinan | Toboy, Asingan, Pangasinan | Toboy, Asingan, Pangasinan | 25501.38 | 2023-01-13 | 14 | 2023-01-27 | 100% | 25501.38 |  |  | 0
Materials used for Municipal Building Maintenance | Asingan, Pangasinan | Asingan, Pangasinan | 94970.94 | 2023-01-26 | 46 | 2023-03-13 | 100% | 94970.94 |  |  | 0
Solid Waste Tipping Fee and payment of per diems incurred while on Official business travel from January 27,2023 to March 3,2023 | Asingan, Pangasinan | Asingan, Pangasinan | 32048 | 2023-01-27 | 42 | 2023-03-10 | 52.73% | 16898 |  |  | 15150
Replacement (Fabrication & Installation) of Front Gate and Improvement of Office at Satellite Market Toboy, Asingan, Pangasinan SWA date: 2/14/23 100% PO: 1/30/23 | Toboy, Asingan, Pangasinan | Toboy, Asingan, Pangasinan | 169779.23 | 2023-01-30 | 15 | 2023-02-14 | 100% | 169779.23 |  |  | 0
Continuation of the construction of PNP Quarters (Multi-purpose Building) Asingan, Pangasinan SWA date:03/01/23 80.07% NTP:2/17/23 CP:999.694.76 | Asingan, Pangasinan | Asingan, Pangasinan | 999694.76 | 2023-02-17 | 12 | 2023-03-01 | 80.06% | 800385.58 |  |  | 199309.18
Contract for the concreting of Pavement Coldit-San Vicente West Local Access Road Asingan, Pangasinan SWA date:3/01/23 64.76% NTP:2/17/23 CP:499,761.03 | Coldit - San Vicente, Asingan, Pangasinan | Coldit - San Vicente, Asingan, Pangasinan | 499761.03 | 2023-02-17 | 12 | 2023-03-01 | 64.76% | 323633.96 |  |  | 176127.07
Contract for the concreting of pavement Don Luis Butao FMR at Domanpot, Asingan, Pangasinan | Domanpot, Asingan, Pangasinan | Domanpot, Asingan, Pangasinan | 999637.05 | 2023-02-17 | 12 | 2023-03-01 | 80.16% | 801297.11 |  |  | 198339.94
Concreting of pavement Don Luis Buato FMR at Domanpot, Asingan, Pangasinan | Domanpot, Asingan, Pangasinan | Domanpot, Asingan, Pangasinan | 198339.94 | 2023-02-17 | 19 | 2023-03-08 | 100% | 198339.94 |  |  | 0
contract for the concreting of Pavement Ariston West Going to Ariston Bantog National High school, Asingan, Pangasinan | Bantog, Asingan, Pangasinan | Bantog, Asingan, Pangasinan | 299713.87 | 2023-02-17 | 19 | 2023-03-08 | 100% | 299713.87 |  |  | 0
Continuation of the Construction of PNP Quarters (Multi-Purpose Building) Asingan, Pangasinan | Asingan, Pangasinan | Asingan, Pangasinan | 999694.76 | 2023-02-17 | 31 | 2023-03-20 | 19.94% | 199309.18 |  |  | 800385.58
Partial payment of his contract for the construction of (Stone Masonry Slope Protection, Gravel and Sand Pavement)Nambilangan FMR at Sobol, Asingan SWA | Sobol, Asingan, Pangasinan | Sobol, Asingan, Pangasinan | 999718.06 | 2023-02-17 | 24 | 2023-03-13 | 65.27% | 652478.72 |  |  | 347239.34
Installation of on Grid Solar Power Source for LGU Building Asingan, Pangasinan | Asingan, Pangasinan | Asingan, Pangasinan | 4980000 | 2023-02-17 | 26 | 2023-03-15 | 50% | 2490000 |  |  | 2490000
River mixed for the rehabilitation of Looc-Bet-Ang farm to market road Carosucan Norte, Asingan, Pangasinan | Carosucan Norte, Asingan, Pangasinan | Carosucan Norte, Asingan, Pangasinan | 49500 | 2023-03-08 | 5 | 2023-03-13 | 100% | 49500 |  |  | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor