## 1st Qtr 20% LDF
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: I |  | CALENDAR YEAR: | 2025
PROVINCE: PANGASINAN |  | QUARTER: | 1
CITY/MUNICIPALITY: ASINGAN
Program or Project | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Construction of Municipal Slaughterhouse at Toboy, Asingan, Pangasinan NTP: 08/06/2024 SWA: 10/09/2024 53.31% CP: 3,998,533.80 | Toboy, Asingan, Pangasinan | 3998533.8 | 2024-08-06 | 65 | 2024-12-03 | 100% | 3998533.8 |  | pd 12/13/24 - P2,131,869 - , pd 2/6/2025 - P1,866,664.80 | 3998532.8 | 0
1st partial payment of his contract for the construction of Covered Court at Macalong, Asingan, Pangasinan NTP: 02/12/2025 SWA: 03/07/2025 30.77% CP: 3,498,306.16 | Macalong, Asingan, Pangasinan | 3498306.16 | 2025-02-12 | 24 | 2025-03-08 | 90% | 3148475.54 |  | pd 3/8/25 - P1,076,324.23, pd 3/18/25 - P2,072,151.31 |  | 349830.62
Payment of his contract for the Installation of Solar-powered Street Lights (Baro to Carosucan Sur) Asingan, Pangasinan NTP: 02/11/2025 SWA: 03/12/2025 100% CP: 2,998,510.20 | Baro to Carosucan Sur, Asingan, Pangasinan | 2998510.2 | 2025-02-11 | 30 | 2025-03-13 | 100% | 2998510.2 |  |  |  | 0
Payment of the Disposal Fee for residual municipal solid waste rendered covering dates February 4-28, 2025 | Asingan, Pangasinan | 20162 | 2025-02-04 | 25 | 2025-03-01 | 100% | 20162 |  |  |  | 0
Payment of his contract for the power reference for On Grid Solar Power at Municipal Hall, Asingan, Pangasinan NTP: 02/12/2025 SWA: 03/29/2025 100% CP: 1,250,000.00 | Asingan, Pangasinan | 1250000 | 2025-02-12 | 46 | 2025-03-30 | 100% | 1250000 |  |  |  | 0
[9 empty] | 0 | 0 | 0
Economic Development (pls list down specific projects) | [8 empty] | 0
Environmental Management (pls list down specific projects) | [8 empty] | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
MARJORIE V. TINTE | [5 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [5 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+[Contract Duration]