## 2nd Qtr 20% LDF
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
REGION: I | [5 empty] | CALENDAR YEAR: | 2023
PROVINCE: PANGASINAN | [5 empty] | QUARTER: | 2
CITY/MUNICIPALITY: ASINGAN
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status |  | No. of Extensions, if any
[7 empty] | % of Completion | Total Cost Incurred to Date |  | Remarks
SOCIAL DEVELOPMENT
Contract for the Installation of Solar Light at Ariston East, Ariston West and Bantog, Asingan, Pangasinan SWA date: 6/02/23 100% NTP: 4/19/23 |  | Ariston East, Ariston West and Bantog, Asingan, Pangasinan | 2499727.13 | 2023-04-19 | 45 | 2023-06-03 | 100% | 2499727.13 |  |  |  | 0
Continuation of concreting the road in front of Ariston-Bantog National High school Asingan, Pangasinan SWA Date: 06/05/23 100% PO:5/25/23 RI: 0113050040001 |  | Ariston-Bantog NHS, Asingan, Pangasinan | 199940 | 2023-05-25 | 11 | 2023-06-05 | 100% | 199940 |  |  |  | 0
Materials used for Municipal Building Maintenance |  | Asingan , Pangasinan | 28474.38 | 2023-03-24 | 53 | 2023-05-16 | 100% | 28474.38 |  |  |  | 0
Replacement of Broken Analok Window at Accounting Office |  | Asingan , Pangasinan | 2150 | 2023-04-21 | 0 | 2023-04-21 | 100% | 2150 |  |  |  | 0
Materials used for Municipal Building Maintenance |  | Asingan , Pangasinan | 63306.36 | 2023-06-15 | 7 | 2023-06-22 | 100% | 63306.36 |  |  |  | 0
Installation of on Grid Solar Power Source for LGU Building Asingan, Pangasinan | Asingan, Pangasinan | Asingan, Pangasinan | 4980000 | 2023-02-17 | 90 | 2023-05-18 | 100% | 4980000 |  | P2,490,000.00 paid in 1st quarter | 0
To payment for the repair, replacement of comfort room door ans faucet at RHU II, Bantog, Asingan, Pangasinan PO:4/17/23 SWA date: 4/18/2023 |  | Bantog, Asingan, Pangasinan | 7966.2 | 2023-05-04 | 7 | 2023-05-11 | 100% | 7966.2
Procurement of Patrol Vehicle for use at the Municipality of Asingan NTP:5/02/23 (Ariston West) TOYOTA HILUX 2.4L |  | Asingan, Pangasinan | 1109760 | 2023-04-02 | 60 | 2023-06-01 | 100% | 909760 |  | P200,000.000 Brgy counterpart |  | 200000
Per diems & reimbursement of solid waste tipping fee, incurred while on official business travel from May 5, 2023 to June 16, 2023 |  | Asingan, Pangasinan | 15079 | 2023-06-09 | 14 | 2023-06-23 | 100% | 15079 |  |  |  | 0
To payment for the continuation of pavement of Brgy Covered Court at Brgy Bobonan, Asingan, Pangasinan |  | Bobonan, Asingan | 99966.35 | 2023-06-07 | 7 | 2023-06-14 | 100% | 99966.35
To payment of per diems and reimbursement of Tipping fee and gasoline incurred while on official business travel form March 28,2023 to April 28,2023 |  | Asingan, Pangasinan | 15793 | 2023-03-28 | 31 | 2023-04-28 | 100% | 15793
Renovation of Warehouse Building of Aragaag Farmers Swisa Sitio Aragaag, Bantog, Asingan, Pangasinan SAW date:4/10/23 100% PO:3/23/23 |  | Bantog, Asingan, Pangasinan | 199980.87 | 2023-03-23 | 18 | 2023-04-10 | 100% | 199980.87 |  |  | 0 | 0
Additional Works of Warehouse Building of Aragaag Swisa Sitio Aragaag Bantog, Asingan, Pangasinan SWA Date: 4/18/23 PO:4/14 |  | Bantog, Asingan, Pangasinan | 29950.8 | 2023-04-14 | 4 | 2023-04-18 | 100% | 29950.8 |  |  |  | 0
Continuation of Covered Court at Zone 1 Barangay Cabalitian, Asingan, Pangasinan SWA date: 4/11/23 100% NTP: 3/28/23 |  | Cabalitian, Asingan, Pangasinan | 49997.39 | 2023-03-28 | 14 | 2023-04-11 | 100% | 49997.39 |  |  |  | 0
Continuation of constructions of Motorpool at Barangay Carosucan Norte , Asingan, Pangasinan SWA Date: 5/3/23 100% NTP: 4/14/23 |  | Carosucan Norte, Asingan, Pangasinan | 149993 | 2023-04-14 | 19 | 2023-05-03 | 100% | 149993 |  |  |  | 0
Procurement of Patrol Vehicles for use at the Municipality of Asingan Barangay Carosucan Sur & Coldit NTP: 4/25/23 MITSUBISHI L200 |  | Carosucan sur & Coldit, Asingan, Pangasinan | 2160000 | 2023-04-25 | 16 | 2023-05-11 | 100% | 2160000 |  |  |  | 0
Regravelling for the Rehabilitation od Looc-Bet-Ang Farm to Market Road at Barangay Carosucan Sur, Asingan, Pangasinan SWA DATE:4/24/23 100% NTP:4/4/23 |  | Carosucan sur, Asingan, Pangasinan | 129980.4 | 2023-04-04 | 20 | 2023-04-24 | 100% | 129980.4 |  |  |  | 0
Contract for the concreting of Pavement Coldit-San Vicente West Local Access Road Asingan, Pangasinan | Coldit - San Vicente, Asingan, Pangasinan | Coldit - San Vicente, Asingan, Pangasinan | 499761.03 | 2023-02-17 | 25 | 2023-03-14 | 100% | 499761.03 |  | P323,633.96 paid in the 1st quarter | 0
Continuation of Road Shoulder at Zone 6 Barangay Coldit Asingan, Pangasinan SWA Date: 5/29/23 100% NTP: 5/11/23 RI:0113050120001 |  | Coldit, Asingan, Pangasinan | 149997.36 | 2023-05-11 | 18 | 2023-05-29 | 100% | 149997.36 |  |  |  | 0
Purchased of Service Drop Wire (ACSR NO. 2 @40M) for DSWD Building |  | DSWD, Asingan, Pangasinan | 5170 | 2023-05-03 | 0 | 2023-05-03 | 100% | 5170 |  |  |  | 0
Construction of Slope Protection/ Stone Masonry at Macalong-Domanpot Road, Asingan, Pangasinan SWA date:3/14/23 100% NTP:2/17/23 |  | Macalong - Domanpot, Asingan, Pangasinan | 498939 | 2023-02-17 | 25 | 2023-03-14 | 100% | 498939 |  |  |  | 0
Installation of Solar Power Street lights at Zone 4 Barangay Palaris Asingan, Pangasinan SWA date: 4/4/23 100% PO: 3/29/23 |  | Palaris, Asingan, Pangasinan | 199875 | 2023-03-29 | 6 | 2023-04-04 | 100% | 199875 |  |  |  | 0
Concreting of Farm to Market Road at Zone 4 at Barangay Palaris, Asingan, Pangasinan SWA date:5/22/23 100% NTP:5-02-23 RI: 0113050160008 |  | Palaris, Asingan, Pangasinan | 99996.66 | 2023-05-02 | 20 | 2023-05-22 | 100% | 99996.66 |  |  |  | 0
Construction of Closing of Two (2) overflow weir at Sitio Sinapog, Poblacion East, Asingan, Pangasinan SWA date: 4/24/2023 100% PO:4/17/23 |  | Poblacion East, Asingan, Pangasinan | 54896.31 | 2023-04-17 | 7 | 2023-04-24 | 100% | 54896.31 |  |  |  | 0
Construction of Multi-Purpose Pavement at Brgy. San Vicente East, Asingan, Pangasinan SWA Date: 4/18/23 100% PO:4/11/23 |  | San Vicente East, Asingan, Pangasinan | 179820 | 2023-04-11 | 7 | 2023-04-18 | 100% | 179820 |  |  |  | 0
Construction of Shed of the Pump-well at Zone 3 (interior), Barangay. San Vicente East, Asingan, Pangasinan |  | San Vicente East, Asingan, Pangasinan | 17440 | 2023-04-17 | 8 | 2023-04-25 | 100% | 17440 |  |  |  | 0
Construction of (Stone Masonry Slope Protection, Gravel and Sand Pavement)Nambilangan FMR at Sobol, Asingan | Sobol, Asingan, Pangasinan | Sobol, Asingan, Pangasinan | 999718.06 | 2023-02-17 | 24 | 2023-03-13 | 65.27% | 652478.72 |  | P652,478.72 paid in the 1st quarter | 347239.34
Concrete pavement of Barangay Road at Zone II (in front of Sobol Elementary School) Barangay Sobol, Asingan, Pangasinan SWA date: 4/12/23 100% PO: 3/30/23 |  | Sobol, Asingan, Pangasinan | 199953 | 2023-03-30 | 13 | 2023-04-12 | 100% | 199953 |  |  |  | 0
Construction of STAC Building Asingan, Pangasinan SWA date: 5/02/23 30.07% NTP:4/19/23 CP: 1999519.75 |  | STAC, Asingan, Pangasinan | 1999519.75 | 2023-04-19 | 105 | 2023-08-02 | 85% | 1203389.94 |  |  |  | 796129.81
installation of pressure tank with 1HP water pump at satellite market Toboy, Asingan, Pangasinan SWA date: 3/31/23 100% PO: 3/24/23 |  | Toboy, Asingan, Pangasinan | 29910.52 | 2023-03-24 | 7 | 2023-03-31 | 100% | 29910.52 |  |  |  | 0
[8 empty] | 15333692.42 |  |  |  | -15333692.42
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Formulas:
Target Completion Date = [Date Started]+[Contract Duration]
Date Started = [Target Completion Date]-[Contract Duration]
Note on I20: P200,000 Brgy caounterpart