## 3rd Qtr 20% LDF
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 3RD QUARTER, CY 2023
REGION: I | [5 empty] | CALENDAR YEAR: | 2023
PROVINCE: PANGASINAN | [5 empty] | QUARTER: | 3
CITY/MUNICIPALITY: ASINGAN
Program or Project | AGENCY | Location | Total Cost | Date Started | Contract Duration | Target Completion Date | Project Status
[7 empty] | % of Completion | Total Cost Incurred to Date | Remarks
SOCIAL DEVELOPMENT
Construction of (Stone Masonry Slope Protection, Gravel and Sand Pavement)Nambilangan FMR at Sobol, Asingan | Sobol, Asingan, Pangasinan | Sobol, Asingan, Pangasinan | 999718.06 | 2023-02-17 | 136 | 2023-07-03 | 100% | 999718.06 |  |  |  | 0
Concreting of pavement at Zone 3 FMR at Dupac, Asingan, Pangasinan NTP: 03/29/2023 SWA: 04/10/2023 100% Road ID: 0113050140002 |  | Dupac, Asingan, Pangasinan | 189246.56 | 2023-03-29 | 13 | 2023-04-10 | 100% | 189246.56 |  |  | 0 | 0
Construction of STAC Building Asingan, Pangasinan SWA date: 5/02/23 30.07% NTP:4/19/23 CP: 1999519.75 |  | STAC, Asingan, Pangasinan | 1999519.75 | 2023-04-19 | 100 | 2023-07-28 | 100% | 1999519.75 |  |  |  | 0
Installation of Solar Street Lights at Barangay Ariston West, Asingan, Pangasinan |  | Ariston West, Asingan, Pangasinan | 98414.69 | 2023-05-08 | 10 | 2023-05-17 | 100% | 98414.69 |  |  | 0 | 0
Installation of Two (2) units of Solar Streetlights with Post at Barangay Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 49995.96 | 2023-05-17 | 13 | 2023-05-29 | 100% | 49995.96 |  |  |  | 0
Riprapping of Pugong Local Access Road at Barangay Ariston East, Asingan, Pangasinan NTP: 05/24/2023 SWA: 06/05/2023 100% CP: 49,991.13 |  | Ariston East, Asingan, Pangasinan | 49991.13 | 2023-05-24 | 13 | 2023-06-05 | 100% | 49991.13 |  |  |  | 0
Installation of two (2) units Solar Streetlights with post at Palaris, Asingan, Pangasinan |  | Palaris, Asingan, Pangasinan | 48869.96 | 2023-06-05 | 10 | 2023-06-14 | 100% | 48869.96 |  |  | 0 | 0
Construction of Stone Masonry and Check gate at Brgy. Toboy, Asingan, Pangasinan NTP: 06/14/2023 SWA: 07/03/2023 100% CP: 119,995.88 |  | Toboy, Asingan, Pangasinan | 119995.88 | 2023-06-14 | 20 | 2023-07-03 | 100% | 119995.88 |  |  | 0 | 0
Concreting of the Eco Park at Zone 2 Barangay Ariston East, Asingan, Pangasinan NTP: 6/21/2023 SWA: 7/10/2023 100% CP: 99,957.66 |  | Ariston East, Asingan, Pangasinan | 99957.66 | 2023-06-21 | 20 | 2023-07-10 | 100% | 99957.66 |  | 0 |  | 0
Gravelling of new road namely Paracacia Road of Brgy. Ariston East, Asingan, Pangasinan NTP: 6/21/2023 SWA: 6/27/2023 CP: 46957.08 100% RI: 0113050030006 |  | Ariston East, Asingan, Pangasinan | 46957.08 | 2023-06-21 | 7 | 2023-06-27 | 100% | 46957.08 |  |  |  | 0
Installation of two (2) units Solar Streetlights at Zone 3, Brgy. Sanchez, Asingan, Pangasinan |  | Sanchez, Asingan, Pangasinan | 47816.89 | 2023-06-22 | 8 | 2023-06-29 | 100% | 47816.89 |  | 0 |  | 0
Installation of five (5) units Solar Lamp for the Sangguniang Kabataan of Brgy. Carosucan Norte, Asingan, Pangasinan |  | Carosucan Norte, Asingan, Pangasinan | 49900 | 2023-06-29 | 5 | 2023-07-03 | 100% | 49900 |  |  | 0 | 0
Solid waste tipping fee |  | Asingan, Pangasinan | 12529 | 2023-07-05 | 10 | 2023-07-14 | 100% | 12529 |  |  |  | 0
Concreting of Road Shoulder at Zone VII, Brgy. Bobonan, Asingan, Pangasinan NTP: 7/6/2023 SWA: 7/24/2023 100% CP: 99,993.56 RI: 0113080070004 |  | Bobonan, Asingan, Pangasinan | 99993.56 | 2023-07-06 | 19 | 2023-07-24 | 100% | 99993.56 |  |  | 0 | 0
Concreting of road shoulder at Zone VII Barangay Sobol, Asingan, Pangasinan NTP: 7/13/2023 SWA: 7/26/2023 100% CP: 119,993.26 RI: 011305020000 |  | Sobol, Asingan, Pangasinan | 119993.26 | 2023-07-13 | 14 | 2023-07-26 | 100% | 119993.26 |  |  | 0 | 0
Concreting of road shoulder at Zone 3, Brgy. Dupac, Asingan, Pangasinan NTP: 7/13/2023 SWA: 7/24/2023 100% CP: 79,919.00 RI: 0113050060003 |  | Dupac, Asingan, Pangasinan | 79919 | 2023-07-13 | 12 | 2023-07-24 | 100% | 79919 |  |  | 0 | 0
Replacement/upgrade of electrical meter socket of OSCA Building |  | Poblacion East, Asingan, Pangasinan | 11365.57 | 2023-07-24 | 3 | 2023-07-26 | 100% | 11365.57 |  |  | 0 | 0
Construction of Segregation Facility Building at MRF, Bantog, Asingan, Pangasinan NTP: 07/27/2023 SWA: 08/29/2023 100% CP: 499,830.07 |  | Bantog, Asingan, Pangasinan | 499830.07 | 2023-07-27 | 34 | 2023-08-29 | 100% | 499830.07 |  | 0 |  | 0
Concreting of pavement at Baro-Dumaquit FMR, Asingan, Pangasinan NTP: 7/27/2023 SWA: 8/09/2023 100% CP: 299,815.17 RI: 0113050060001 |  | Baro-Dumaquit FMR, Asingan, Pangasinan | 299815.17 | 2023-07-27 | 13 | 2023-08-09 | 100% | 299815.17 |  |  | 0 | 0
Concreting of Pavement at Palaris-Irrigation Dike Road at Palaris, Asingan, Pangasinan NTP: 07/27/2023 SWA: 08/11/2023 100% CP: 299,876.31 RI: 0113050160008 |  | Palaris, Asingan, Pangasinan | 299876.31 | 2023-07-27 | 16 | 2023-08-11 | 100% | 299876.31 |  | 0 |  | 0
Concreting of Pavement at Zone 2 FMR at San Vicente East, Asingan, Pangasinan NTP: 7/27/2023 SWA: 8/09/2023 100% CP: 299,883.55 RI: 0113050180003 |  | San Vicente East, Asingan, Pangasinan | 299883.55 | 2023-07-27 | 13 | 2023-08-09 | 100% | 299883.55 |  |  | 0 | 0
Concreting of pavement at San Vicente West-Macalong FMR, Asingan, Pangasinan NTP: 07/27/2023 SWA: 08/11/2023 100% CP: 299,790.96 |  | San Vicente West, Asingan, Pangasinan | 299790.96 | 2023-07-27 | 16 | 2023-08-11 | 100% | 299790.96 |  |  |  | 0
Concreting of pavement at San Vicente West-Macalong FMR, Asingan, Pangasinan NTP: 07/27/2023 SWA: 08/11/2023 100% CP: 299,790.96 |  | San Vicente West-Macalong FMR, Asingan, Pangasinan | 299790.96 | 2023-07-27 | 16 | 2023-08-11 | 100% | 299790.96 |  |  | 0 | 0
Payment of materials used for the improvement of Municipal Building |  | Poblacion East, Asingan, Pangasinan | 94536.53 | 2023-08-01 | 6 | 08/07/2023 | 100% | 94536.53 |  |  | 0 | 0
Solid Waste Tipping Fee |  | Asingan, Pangasinan | 17493 | 2023-08-03 | 30 | 2023-09-01 | 100% | 17493 |  |  | 0 | 0
Repair & installation of Glass Doors at side entrance & installation of Roll Up at rear door of Municipal Hall Building NTP: 08/07/2023 SWA: 08/23/2023 100% CP: 157,471.40 |  | Poblacion East, Asingan, Pangasinan | 157471.4 | 2023-08-07 | 17 | 2023-08-23 | 100% | 157471.4 |  |  | 0 | 0
Purchase of Meter Socket for Streetlights at Poblacion East, Asingan, Pangasinan |  | Poblacion East, Asingan, Pangasinan | 7548.25 | 2023-08-08 | 10 | 2023-08-17 | 100% | 7548.25 |  |  | 0 | 0
Construction of Perimeter Fence of Satellite Market at Toboy, Asingan, Pangasinan NTP: 08/09/2023 SWA: 08/30/2023 100% CP: 399,768.14 |  | Toboy, Asingan, Pangasinan | 399768.14 | 2023-08-09 | 22 | 2023-08-30 | 100% | 399768.14 |  |  | 0 | 0
Installation of four (4) units of Solar Streetlights at Zone 2 and Zone 3, Calepaan, Asingan, Pangasinan |  | Calepaan, Asingan, Pangasinan | 99994.12 | 2023-08-10 | 12 | 2023-08-21 | 100% | 99994.12 |  |  | 0 | 0
Purchase of Meter Socket for STAC Building, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 7548.25 | 2023-08-10 | 8 | 2023-08-17 | 100% | 7548.25 |  |  | 0 | 0
Installation of Water Supply at STAC Building at Zone I, Macalong, Asingan, Pangasinan |  | Macalong, Asingan, Pangasinan | 4708 | 2023-08-11 | 7 | 08/18/2023 | 100% | 4708 |  |  |  | 0
Installation of Solar Streetlights at Zone 4 & 5, Barangay Cabalitian, Asingan, Pangasinan NTP: 08/15/2023 SWA: 08/22/2023 100% CP: 99,997.00 |  | Cabalitian, Asingan, Pangasinan | 99997 | 2023-08-15 | 8 | 2023-08-22 | 100% | 99997 |  |  | 0 | 0
Payment for Extension Shed in front of the Barangay Multi-purpose Hall at Brgy. Macalong, Asingan, Pangasinan NTP: 08/22/2023 SWA: 08/30/2023 100% CP: 99,994.84 |  | Macalong, Asingan, Pangasinan | 99994.84 | 2023-08-22 | 9 | 2023-08-30 | 100% | 99994.84 |  |  | 0 | 0
Concreting of Pavement Zone 2 farm to Market Road at Dupac, Asingan, Pangasinan NTP: 08/29/2023 SWA: 09/06/2023 100% CP: 198,918.56 RI: 0113050140011 |  | Dupac, Asingan, Pangasinan | 198918.56 | 2023-08-29 | 9 | 2023-09-06 | 100% | 198918.56 |  |  | 0 | 0
Concreting of Road Shoulder at Zone 7, Brgy. Bobonan, Asingan, Pangasinan NTP: 08/31/2023 SWA: 09/11/2023 100% CP: 79,994.89 RI: 0113050070005 |  | Bobonan, Asingan, Pangasinan | 79994.89 | 2023-08-31 | 12 | 2023-09-11 | 100% | 79994.89 |  |  | -0.89 | 0
Payment of 6 rolls of Grass Cutter Nylon String for use at Municipal Cemetery, Asingan Public Plaza and Material Recovery Facility |  | Poblacion West, Asingan, Pangasinan | 3600 | 2023-08-31 | 5 | 09/04/2023 | 100% | 3600 |  |  | 0 | 0
Solar Street Lights at Brgy. Sanchez, Asingan, Pangasinan NTP: 08/14/2023 SWA: 08/23/2023 100% CP: 99,997.00 |  | Sanchez, Asingan, Pangasinan | 99997 | 08/14/2023 | 10 | 2023-08-23 | 100% | 87500 | w/ 1011-13c amounting to 12,497.00 |  | 12497 | 12497
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[10 empty] | 0 |  | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[11 empty] | 0 | 0
[8 empty] | 6482525.95 |  |  | -6482525.95
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this
document.
MARJORIE V. TINTE | [6 empty] | ENGR. CARLOS F. LOPEZ, JR.
Municipal Accountant | [6 empty] | Municipal Mayor
Note on I120: P200,000 Brgy counterpart