## Form 7 - DFU
FDP Form 7 - 20% Development Fund Utilization
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
REGION: | I |  | CALENDAR YEAR: | 2024
PROVINCE: | PANGASINAN |  | QUARTER: | 4
CITY/MUNICIPALITY: | ASINGAN
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
Social Development (pls list down specific projects)
Finishing Works of Danggay Building, Asingan, Pangasinan NTP: 11/22/2023 SWA: 11/29/2023 100% CP: 199,915.00 | Poblacion East, Asingan, Pangasinan | 199915 | 2023-11-22 | 2023-11-29 | 100% | 199915
Replacement of broken glass door at the right wing of Municipal Hall building NTP: 11/23/2023 SWA: 12/01/2023 100% CP: 38,450.00 | Poblacion East, Asingan, Pangasinan | 38450 | 2023-11-23 | 2023-12-01 | 100% | 38450
Regravelling of newly open farm to market road at Zone 1 to Zone 4, Brgy. San Vicente West, Asingan, Pangasinan NTP: 11/23/2023 SWA: 12/01/2023 100% CP: 89,278.11 | San Vicente West, Asingan, Pangasinan | 89278.11 | 2023-11-23 | 2023-12-01 | 100% | 89278.11
Repair/rehabilitation, replacement & installation of new RGB LED lights of Fountain at Public Plaza in this Municipality of Asingan NTP: 11/29/2023 SWA: 12/06/2023 100% CP: 199,900.00 | Asingan, Pangasinan | 199900 | 2023-11-29 | 2023-12-06 | 100% | 199900
Solid Waste Tipping Fee | Asingan, Pangasinan | 23120 | 2023-10-11 | 2023-11-30 | 100% | 23120
Construction of the Covered Playground of Carosucan Norte, Asingan, Pangasinan NTP: 11/14/2023 SWA: 11/24/2023 100% CP: 99,987.26 | Carosucan Norte, Asingan, Pangasinan | 99987.26 | 2023-11-14 | 2023-11-24 | 100% | 99987.26
Payment of Materials for the improvement of Municipal Building PO: 11/23/2023 Delivery Date: 11/23/2023 CP: 72,171.54 | Poblacion East, Asingan, Pangasinan | 72171.54 | 2023-11-23 | 2023-11-23 | 100% | 72171.54
Fabrication and installation of window grills, construction of divider and repainting of new COMELEC Office NTP: 11/30/2023 SWA: 12/07/2023 100% CP: 169,664.20 | Poblacion East, Asingan, Pangasinan | 169664.2 | 2023-11-30 | 2023-12-07 | 100% | 169664.2
Replacement of dilapidated pavers at Public Plaza, Restoration of Landmark and concreting of Women Center Driveway NTP: 12/01/2023 SWA: 12/11/2023 100% CP: 119,800.00 | Asingan, Pangasinan | 119800 | 2023-12-01 | 2023-12-11 | 100% | 119800
Finishing works of the PWD Building, Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/15/2023 100% CP: 399,854.87 | Asingan, Pangasinan | 399854.87 | 2023-12-05 | 2023-12-15 | 100% | 399854.87
Purchase of five (5) units of pitcher pump and ten (10) pcs. G.I. pipe at Brgy. Poblacion East, Asingan, Pangasinan PO: 05/11/2023 SWA: 05/22/2023 100% CP: 24,950.00 | Poblacion East, Asingan, Pangasinan | 24950 | 2023-05-11 | 2023-05-22 | 100% | 24950
Repair of Slaughterhouse, Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/15/2023 70.12% CP: 599,819.88 | Asingan, Pangasinan | 599819.88 | 2023-12-05 | 645084.88 | 70.12% | 420598.72
Purchase of Basketball Board and Ring to be installed at Zone 1, Brgy. San Vicente West, Asingan, Pangasinan NTP: 12/12/2023 SWA: 12/14/2023 100% CP: 59,703.25 | San Vicente West, Asingan, Pangasinan | 59703.25 | 2023-12-12 | 2023-12-14 | 100% | 59703.28
Construction of Multi-purpose Hall (Food court old DA building area) Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/12/2023 25.02% CP: 1,999,892.37 | Asingan, Pangasinan | 1999892.37 | 2023-12-05 | 1999972.37 | 25.02% | 500464.16
Water Proofing of X-Ray Room at RHU-I Asingan, Pangasinan NTP: 12/06/2023 SWA: 12/08/2023 100% CP: 7,430.00 | Poblacion East, Asingan, Pangasinan | 7430 | 2023-12-06 | 2023-12-08 | 100% | 7430
Installation of Xray Machine and calibration at RHU-I Asingan, Pangasinan NTP: 12/13/2023 SWA: 12/15/2023 100% CP: 44,750.00 | Poblacion East, Asingan, Pangasinan | 44750 | 2023-12-13 | 2023-12-15 | 100% | 44750
Concreting of FMR at barangay Macalong, Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/15/2023 100% CP: 299,377.80 | Macalong, Asingan, Pangasinan | 299377.8 | 2023-12-05 | 2023-12-15 | 100% | 299377.8
Rehabilitation of Comfort Room at Trading Post, Macalong, Asingan, Pangasinan NTP: 12/05/2023 SWA: 12/15/2023 100% CP: 99,930.00 | Macalong, Asingan, Pangasinan | 99930 | 2023-12-05 | 2023-12-15 | 100% | 99930
Economic Development (pls list down specific projects)
Environmental Management (pls list down specific projects)
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
| EMELY S. BADUA |  |  |  | ENGR. CARLOS F. LOPEZ, JR.
| Municipal Budget Officer |  |  |  | Municipal Mayor
Formulas:
Target Completion Date = [Total Cost]+[CALENDAR YEAR:]
Target Completion Date = [Total Cost]+80

## FDPP LICENSE (hidden)
CAUTION:
TO REDUCE THE RISK OF UPLOADING WRONG TEMPLATE FOR THIS DOCUMENT, DO NOT EDIT/DELETE THIS SHEET.
FROM:
FDPP TEAM
v2
43